United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

BASIS OF ESTIMATE

PROJECT INFORMATION

Project:	Oso Comida Trailhead Improvements:

| Park: | Bear Arbor NRA |
| --- | --- |
| Park Apha: | BEAR |
| PMIS: | XXXXXX |
| Estimate Date: | 1/12/2011 |
| Prepared By: | YtB |
| Company: | NPS Bear Arbor NRA |
| Address: | 123 Bruin Meadows Rd. |
| City, State Zip: | Grizzley Hollow, CA 96023 |
| Phone: | (555) 123-4567 |

BACKGROUND SUPPORTING MATERIAL (Scope of Work):

Existing parking lot will be upgraded, re-configured within existing disturbed area, for 40 car spaces, 5 ADA Spaces, 2 van spaces, 10 RV pull throughspaces, and paved. Existing pit toilets will be removed and replaced with a wet comfort station including septic system with in tank bio reactor treatment, and liquid disposal field; NEW WATER WELL NOW REQUIRED. The existing picnic area will be rehabilitated and modified to meet ABBAS accessibility standards. Trail connections will be formalized and upgraded; portions will be made accessible to facilitate access to Bruin Meadows overlook. Existing uncontrolled social trails will be restored to natural and a channelizing seat-resistant wood rail fence added to direct movement from parking area to trail connection. The septic system incorporates a new technology in-tank sanitary treatment process that will be pre ordered and supplied by NPS as GFP. Puchase cost of tank and treatment materials is included in direct cost estimate.

SOURCE OF COST DATA:

Comfort Station unit costs are based a combination of sources that include actual material take-offs and vendor quotes, review of actual final costs and project labor records for a similar facility constructed in 2009 at neighboring Ursa Hollow park. Parking lot costs are based on actual contract prices from Spring 2010 FHWA road project on Bruin Meadows Road adjacent to the site adjusted to remove previous O&P. Purchase price for the prefabricated Septic-King™ is an actual vendor quote FOB park warehouse. Supplimental cost were obtained from RS Means, Facilites Cost Data (FCCD), 25th Annusal Edition.

WHENEVER RSMEANS BARE UNIT COSTS WERE USED FROM THE FCCD DATA, 10% WAS ADDED TO MATERIALS & EQUIPMENT AND 60% TO LABOR TO ACCOUNT FOR INSTALLER (SUB) O&P

ESTIMATE ASSUMPTIONS:

Estimate assumes that all improvements will be constructed as a singe project during one construction season. East half of existing dirt parking area and trailhead will remain in operation until new paved lot and walk connections are completed. 2nd half of existing lot will be available for contractor laydown/equipment area, but contractor's labor force must park at maintenance yard 5 miles away and be shuttled into site. Shuttle costs and additional portable toilet cost impacts are included in Government Special Conditions. Septic-King™ system will be preordered by the Park to avoid long lead time from impacting installation schedule.

MAJOR CHANGES FROM PREVIOUS ESTIMATE:

Parking lot configuration changed slightly to accommodate RV pull through spaces. Existing dirt parking area will be gravel surfaced for use as overflow parking and equestrian staging area. Photo-voltaic system has been deleted for budgetary purposes, viewshed impacts, concerns over viewshed impacts and negative results of net life-cycle payback analysis. Water is not avialable in road; well added to service wet comfort station - assumes 1200 VLF depth.

BEAR Trailhead - 100% Draft Class A Cost Estimate Basis of Estimate

Page 1 of 38

Print Date: 1/24/2011

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

BASIS OF ESTIMATE

PROJECT INFORMATION

Project:	Oso Comida Trailhead Improvements:

| Park: | Bear Arbor NRA |
| --- | --- |
| Park Apha: | BEAR |
| PMIS: | XXXXXX |
| Estimate Date: | 1/12/2011 |

DESCRIPTION OF MARK-UP & ADD-ONS:

| Design Contingency: | 2.00% |
| --- | --- |
| Standard. General Conditions: | 0.00% |
| Government General Conditions: | 3.00% |

This is the 100% Draft CD submittlal, but a few design details relating to septic and electric systems are stil changing.

Precentage mark-up not used. Please refer to itemized Genral conditions estimate for each CLI

Most costs are covered in Standard GC. 3% additional as cost offset to accommodate,creww shuttle, dignitary events and multi-layer oversight disruptions.

| Contractor Overhead: | 8.50% |  | Anticipate using a small contractor with limitted fixed overhead |
| --- | --- | --- | --- |
|  |  |  |  |  | costs and austerity under current market conditons |
| Contractor Profit: | 10.00% |  | Current construction market conditions expected to improve |
|  |  |  |  |  | modestly by 2013 project date. |
| Contracting Method Adjustment: | 15.00% |  | Preliminary indications are that negotiated sole-source SBA |
|  |  |  |  |  | Section 8a or SDV procurement will be utilized. |
| Annual Inflation Escalation Factor: |  | 3.60% |  | Projected annual inflation rate. |
| Time Until Project Midpoint (Months) | 32 | January 2011 estimate data date to mid-point of construction, |
|  |  |  |  |  | August 2013 |

OTHER COMMENTS:

Since new comfort station will have deepened grade-beam/strip footing on piers w/PT slab on grade construction, insufficient spoils will be generated to backfill existing pits. After spoils from new septic system are exhausted, we assumed 50% of total backfill quantity will be imported from NPS in park-stockpile. The balance of the on-site grading appears to balance, pending verification of existing topo.

BEAR Trailhead - 100% Draft Class A Cost Estimate Basis of Estimate

Page 2 of 38

Print Date: 1/24/2011

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

PROJECT COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Estimate By: |  |  |  |  | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date: |  |  |  | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Reviewed By: |  |  |  |  | BBB |  |
| PMIS Number: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date: |  |  |  | 01/17/11 |  |
|  |  |  |  |  |  |  |  |  |  | Total | Total Direct |  | Design |  | General |  | General |  | General | Contracting | Inflation |  |  |  |
|  |  |  |  |  | Total Material | Total Labor |  |  |  |  |  |  |  |  | Contractor |  | Contractor |  | Method | Escalation |  |  |  |
| Bid Item No. |  | Bid Item Description |  |  |  |  | Equipment | Construction | Contingency |  | Conditions |  |  |  |  |  |  |  | Bid Item Total |  |
|  |  |  |  |  | Cost |  | Cost |  |  |  |  |  |  |  | Overhead |  | Profit | Adjustment |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  | Costs |  |  |  |  |  |  |  |  |  | APR |  | Month |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2.00% |  | 3.00% |  | 8.50% |  | 10.00% |  | 15.00% | 3.60% |  | 32 |  |  |  |
| Bid Item: | 1 | Replace Pit Toilets with New Comfort Station |  |  |  |  |  |  |  |  |  |  |  |  |  | TOTAL VALUE OF GOVERNMENT FURNISHED PROPERTY (if any): | $ | 46,000.00 |  |
|  |  | A10 | Foundations |  | $ | 30,028 | $ | 33,082 | $ | 7,293 | $ | 70,403 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | A20 | Basement Construction |  | $ | - | $ | - | $ | - | $ | - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | B10 | Superstructure |  | $ | 15,622 | $ | 13,198 | $ | 460 | $ | 29,280 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | B20 | Exterior Enclosure |  | $ | 35,992 | $ | 29,477 | $ | - | $ | 65,469 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | B30 | Roofing |  | $ | 18,471 | $ | 8,706 | $ | - | $ | 27,177 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | C10 | Interior Construction |  | $ | 25,573 | $ | 9,308 | $ | - | $ | 34,881 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | C30 | Interior Finishes |  | $ | 4,476 | $ | 13,424 | $ | - | $ | 17,900 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | D20 | Plumbing Systems |  | $ | 26,655 | $ | 16,121 | $ | - | $ | 42,776 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | D30 | HVAC |  | $ | 1,269 | $ | 1,170 | $ | - | $ | 2,439 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | D50 | Electrical |  | $ | 8,753 | $ | 9,366 | $ | - | $ | 18,119 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | F20 | Selective Building Demolition |  | $ | 463 | $ | 1,990 | $ | 3,862 | $ | 6,315 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | G10 | Site Preparation |  | $ | 2,188 | $ | 4,362 | $ | 6,952 | $ | 13,502 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | G20 | Site Improvements |  | $ | 8,900 | $ | 7,300 | $ | - | $ | 16,200 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | G30 | Site Mechanical |  | $ | 86,213 | $ | 32,582 | $ | 44,542 | $ | 163,337 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | G40 | Site Electrical |  | $ | 5,000 | $ | - | $ | - | $ | 5,000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | XX | Standard General Conditions |  | $ | 31,900 | $ | 101,200 | $ | 18,610 | $ | 151,710 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total - Bid Item | 1 Replace Pit Toilets with New Comfort Station |  | $ | 301,503 | $ | 281,286 | $ | 81,719 | $ | 664,508 | $ | 12,370 | $ | 18,926 | $ | 55,233 | $ | 64,980 | $ | 122,403 | $ | 92,813 | $ | 1,031,234 |  |
| Bid Item: | 2 | Construct New Parking Lot & Site Utilities |  |  |  |  |  |  |  |  |  |  |  |  |  | TOTAL VALUE OF GOVERNMENT FURNISHED PROPERTY (if any): | $ | - |  |
|  |  | G10 | Site Preparation |  | $ | 2,500 | $ | 11,711 | $ | 19,776 | $ | 33,987 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | G20 | Site Improvements |  | $ | 143,581 | $ | 36,335 | $ | 43,670 | $ | 223,586 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | G30 | Site Mechanical |  | $ | 12,153 | $ | 14,232 | $ | 4,241 | $ | 30,626 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | XX | Standard General Conditions |  | $ | 12,925 | $ | 8,350 | $ | 6,500 | $ | 27,775 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | $ | - | $ | - | $ | - | $ | - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total - Bid Item | 2 Construct New Parking Lot & Site Utilities |  | $ | 171,159 | $ | 70,628 | $ | 74,187 | $ | 315,974 | $ | 6,319 | $ | 9,669 | $ | 28,217 | $ | 33,196 | $ | 59,006 | $ | 44,742 | $ | 497,123 |  |
| Bid Item: | 3 | Picnic Area & Trailhead Improvements |  |  |  |  |  |  |  |  |  |  |  |  |  | TOTAL VALUE OF GOVERNMENT FURNISHED PROPERTY (if any): | $ | - |  |
|  |  | G10 | Site Preparation |  | $ | - | $ | 11,860 | $ | 4,845 | $ | 16,705 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | G20 | Site Improvements |  | $ | 59,448 | $ | 25,960 | $ | 12,270 | $ | 97,678 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | G30 | Site Mechanical |  | $ | 2,125 | $ | 2,275 | $ | 330 | $ | 4,730 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | XX | Standard General Conditions |  | $ | 5,775 | $ | 7,550 | $ | 2,500 | $ | 15,825 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | $ | - | $ | - | $ | - | $ | - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total - Bid Item | 3 Picnic Area & Trailhead Improvements |  | $ | 67,348 | $ | 47,645 | $ | 19,945 | $ | 134,938 | $ | 2,699 | $ | 4,129 | $ | 12,050 | $ | 14,177 | $ | 25,199 | $ | 19,107 | $ | 212,299 |  |
|  |  |  | Total Bid Items 1-3 |  | $ | 540,010 | $ | 399,559 | $ | 175,851 | $ | 1,115,420 | $ | 21,388 | $ | 32,724 | $ | 95,500 | $ | 112,353 | $ | 206,608 | $ | 156,662 | $ | 1,740,656 |  |

| BEAR Trailhead - 100% Draft Class A Cost Estimate | Page 3 of 38 |  |
| --- | --- | --- |
| Project Cost Summary |  | Print Date: 1/24/2011, 2:13 PM |

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

BID ITEM COST SUMMARY

|  | Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Estimate By: |  | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Reviewed By: |  | BBB |  |
| PMIS Number: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
|  |  | Bid Item Number | Asset / Project Element / Description |  | Size/Count |  | Units |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | BID ITEM 1 |  | Construct Wet Comfort Station |  | 1000 |  | SF |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Item | WBS | Description |  | Material | Total Material | Labor Cost/Unit | Total Labor Cost |  | Equipment | Total Equipment |  | Direct |  | Total Direct | NET Cost/Unit | Total NET Costs |  |
| No. |  |  |  | Cost/Unit | Cost |  |  |  | Cost/Unit |  | Cost |  | Cost/Unit |  | Costs |  |  |  |
| 1 | A10 | Foundations | $ | 30.03 | $ | 30,028 | $ | 33.08 | $ | 33,082 | $ | 7.29 | $ | 7,293 | $ | 70.40 | $ | 70,402 | $ | 109.26 | $ | 109,256 |  |
| 2 | A20 | Basement Construction - INC. IN FOUNDATION | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - |  |
| 3 | B10 | Superstructure | $ | 15.62 | $ | 15,622 | $ | 13.20 | $ | 13,198 | $ | 0.46 | $ | 460 | $ | 29.28 | $ | 29,279 | $ | 45.44 | $ | 45,438 |  |
| 4 | B20 | Exterior Enclosure | $ | 35.99 | $ | 35,992 | $ | 29.48 | $ | 29,477 | $ | - | $ | - | $ | 65.47 | $ | 65,469 | $ | 101.60 | $ | 101,600 |  |
| 5 | B30 | Roofing | $ | 18.47 | $ | 18,471 | $ | 8.71 | $ | 8,706 | $ | - | $ | - | $ | 27.18 | $ | 27,176 | $ | 42.17 | $ | 42,174 |  |
| 6 | C10 | Interior Construction | $ | 25.57 | $ | 25,573 | $ | 9.31 | $ | 9,308 | $ | - | $ | - | $ | 34.88 | $ | 34,881 | $ | 54.13 | $ | 54,131 |  |
| 8 | C30 | Interior Finishes | $ | 4.48 | $ | 4,476 | $ | 13.42 | $ | 13,424 | $ | - | $ | - | $ | 17.90 | $ | 17,900 | $ | 27.78 | $ | 27,778 |  |
| 9 | D20 | Plumbing Systems | $ | 26.65 | $ | 26,655 | $ | 16.12 | $ | 16,121 | $ | - | $ | - | $ | 42.78 | $ | 42,776 | $ | 66.38 | $ | 66,383 |  |
| 10 | D30 | HVAC | $ | 1.27 | $ | 1,269 | $ | 1.17 | $ | 1,170 | $ | - | $ | - | $ | 2.44 | $ | 2,438 | $ | 3.78 | $ | 3,784 |  |
| 11 | D50 | Electrical | $ | 8.75 | $ | 8,753 | $ | 9.37 | $ | 9,365 | $ | - | $ | - | $ | 18.12 | $ | 18,118 | $ | 28.12 | $ | 28,117 |  |
| 12 | F20 | Selective Building Demolition | $ | 0.46 | $ | 463 | $ | 1.99 | $ | 1,990 | $ | 3.86 | $ | 3,863 | $ | 6.32 | $ | 6,315 | $ | 9.80 | $ | 9,800 |  |
| 13 | G10 | Site Preparation | $ | 2.19 | $ | 2,188 | $ | 4.36 | $ | 4,362 | $ | 6.95 | $ | 6,952 | $ | 13.50 | $ | 13,502 | $ | 20.95 | $ | 20,953 |  |
| 14 | G20 | Site Improvements | $ | 8.90 | $ | 8,900 | $ | 7.30 | $ | 7,300 | $ | - | $ | - | $ | 16.20 | $ | 16,200 | $ | 25.14 | $ | 25,140 |  |
| 15 | G30 | Site Mechanical Utilities | $ | 86.21 | $ | 86,213 | $ | 32.58 | $ | 32,582 | $ | 44.54 | $ | 44,543 | $ | 163.34 | $ | 163,337 | $ | 253.48 | $ | 253,479 |  |
| 16 | G40 | Site Electrical Utilities | $ | 5.00 | $ | 5,000 | $ | - | $ | - | $ | - | $ | - | $ | 5.00 | $ | 5,000 | $ | 7.76 | $ | 7,759 |  |
| 17 | XX | General Conditions | $ | 31.90 | $ | 31,900 | $ | 101.20 | $ | 101,200 | $ | 18.61 | $ | 18,610 | $ | 151.71 | $ | 151,710 | $ | 235.44 | $ | 235,435 |  |
| 18 | XX |  | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - |  |
| 19 | XX |  | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - |  |
|  |  | Subtotal Direct Construction Costs | $ | 301.50 | $ | 301,501 | $ | 281.28 | $ | 281,284 | $ | 81.72 | $ | 81,720 | $ | 664.50 |  | $664,505 | $ | 1,031.23 |  | $1,031,229 |  |
|  | Total Value of Government Furnished Property (GFP) Inc. in Direct Cost . | $ | 46,000.00 |  |  | $ | - |  |  | $ | - | $ | 46,000 |  | $46,000 | In most cases GFP is normally zero - |  |
|  |  | Direct Cost Subtotal without GFP . | $ | 255,501 |  |  | $ | 281,284 |  |  | $ | 81,720 |  |  |  | $618,505 |  | see footnote- |  |  |
|  |  | Design Contingency |  | 2.00% |  |  |  |  |  |  |  |  |  |  |  |  |  | $12,370 | Notes & Comments: |  |  |
|  |  | Total Direct Construction Costs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $676,875 | Building only direct cost = $308.44/sf |  |
|  |  | Standard General Conditions |  | 0.00% | Applied to Total Direct Construction Cost less GFP |  |  |  |  |  |  |  |  | $0 | Building total NET cost = $ | 474.28/sf |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | GFP Septic King Treatment System |  |
|  |  | Government General Conditions |  | 3.00% | Applied to Total Direct Construction Cost less GFP |  |  |  |  |  |  |  |  | $18,926 |  |  |
|  |  | Subtotal NET Construction Cost |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $695,801 | Pre-Purchased by Government = |  |
|  |  | Overhead |  | 8.50% |  |  |  |  |  |  |  |  |  |  |  |  |  | $55,233 | $46,000 |  |  |  |
|  |  | Profit |  | 10.00% |  |  |  |  |  |  |  |  |  |  |  |  |  | $64,980 |  |  |  |  |  |
|  |  | Estimated NET Construction Cost |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $816,014 |  |  |  |  |  |
|  |  | Contracting Method Adjustment |  | 15.00% |  |  |  |  |  |  |  |  |  |  |  |  |  | $122,402 |  |  |  |  |  |
|  |  | Inflation Escalation |  | 32 | Months |  | Annual Rate = |  | 3.60% |  |  |  |  |  |  |  | $92,812 |  |  |  |  |  |
|  | Total Estimated NET Cost of Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $1,031,229 |  |  |  |  |  |

GFP costs only apply when the Government pre-purchases items, or provides other materials out of Government inventory, to be installed by contractor. Adjustments and Markup on GFP only include Inflation Escalation; No other adjustment factors or O&P markup have been applied.

BEAR Trailhead - 100% Draft Class A Cost Estimate

Bid Item 1 Summary

Page 4 of 38

Print Date: 1/24/2011, 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: A10 Foundations |  |  |  |  |  |  |  |  |  |  | Total Cost: | $70,402 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| A1010 | STANDARD FOUNDATIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Excavate Grade Beam 140'x48", Column |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 31.23.15 |  | footings, overdig 25%, spread spoil onsite | 40 | CY | $ | - | $0 | $ | 57.78 | $2,311 | $ | 13.85 | $554 | $ | 71.63 | $2,865 |  |
| 03.15.05 |  | Furnish & Install 6" crushable void form | 140 | LF | $ | 2.25 | $315 | $ | 0.36 | $50 | $ | - | $0 | $ | 2.61 | $365 |  |
| 03.11.13 |  | Fabricate & Erect Outside forms | 560 | SF | $ | - | $0 | $ | 4.14 | $2,318 | $ | - | $0 | $ | 4.14 | $2,318 |  |
| 03.21.10 |  | Furnish & Install Steel Reinfocement | 3200 | LB | $ | 0.66 | $2,112 | $ | 3.93 | $12,576 | $ | - | $0 | $ | 4.59 | $14,688 |  |
| 03.30.53 |  | Furnish & Pour Concrete 42"x12" | 18 | CY | $ | 95.50 | $1,719 | $ | 25.66 | $462 | $ | - | $0 | $ | 121.16 | $2,181 |  |
| 03.30.53 |  | Concrete Waste Factor 10% | 1 | Allow | $ | 171.90 | $172 | $ | - | $0 | $ | - | $0 | $ | 171.90 | $172 |  |
| 03.11.13 |  | Strip, & clean forms | 560 | SF | $ | - | $0 | $ | 0.52 | $291 | $ | - | $0 | $ | 0.52 | $291 |  |
| 03.35.29 |  | Dry Finish top 12" | 140 | SF | $ | - | $0 | $ | 3.79 | $531 | $ | - | $0 | $ | 3.79 | $531 |  |
| 07.27.13 |  | Furnish & Install 2" EPS insulation Board | 560 | SF | $ | 1.03 | $577 | $ | 0.58 | $325 | $ | - | $0 | $ | 1.61 | $902 |  |
| 31.23.23 |  | Backfill w/ Hand compact - select import | 16 | CY | $ | 32.75 | $524 | $ | 163.70 | $2,619 | $ | 48.50 | $776 | $ | 244.95 | $3,919 |  |
| SUBTOTAL | STANDARD FOUNDATIONS | 1000 | SF | $ | 5.42 | $5,419 | $ | 21.48 | $21,484 | $ | 1.33 | $1,330 | $ | 28.23 | $28,232 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| A1020 | SPECIAL FOUNDATIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 03.63.26 |  | Drilled Caisons - 10' OC x 25' -Subcontract | 16 | EA | $ | 1,120.00 | $17,920 | $ | 140.92 | $2,255 | $ | 335.00 | $5,360 | $ | 1,595.92 | $25,535 |  |
| 31.23.23 |  | Pick up & spread spoil onsite | 50 | CY | $ | - | $0 | $ | 19.30 | $965 | $ | 6.65 | $333 | $ | 25.95 | $1,298 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | SPECIAL FOUNDATIONS | 1000 | SF | $ | 17.92 | $17,920 | $ | 3.22 | $3,220 | $ | 5.69 | $5,693 | $ | 26.83 | $26,832 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1 - A10 - Foundations

5 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: A10 Foundations |  |  |  |  |  |  |  |  |  |  | Total Cost: | $70,402 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| A1030 | SLAB ON GRADE - 6" Post tentioned |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 03.11.13 |  | Edge form Included in std. foundation | 0 | Unit | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| 31.23.23 |  | F & I Crushed Aggregate Base - 6" | 50 | Tons | $ | 22.75 | $1,138 | $ | 36.82 | $1,841 | $ | - | $0 | $ | 59.57 | $2,979 |  |
| 31.23.23 |  | Fine Grade & Install 4" leveling sand | 1000 | SF | $ | 0.55 | $550 | $ | 1.40 | $1,400 | $ | - | $0 | $ | 1.95 | $1,950 |  |
| 07.27.13 |  | F & I Rigid EPS and Vapor Barrier | 1000 | SF | $ | 1.09 | $1,090 | $ | 0.58 | $580 | $ | - | $0 | $ | 1.67 | $1,670 |  |
| 03.23.05 |  | Furnish & Install Pre-stressing Tendon | 1000 | SF | $ | 0.78 | $780 | $ | 0.47 | $470 | $ | - | $0 | $ | 1.25 | $1,250 |  |
| 03.23.05 |  | F & I Supplimental Reinforcing Mesh | 1000 | SF | $ | 0.30 | $300 | $ | 0.36 | $360 | $ | - | $0 | $ | 0.66 | $660 |  |
|  |  | Furnish & Pour concrete - Quantity includes 6" |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 03.30.53 |  | topping on grade beam | 26 | CY | $ | 95.50 | $2,483 | $ | 118.56 | $3,083 | $ | 6.55 | $170 | $ | 220.61 | $5,736 |  |
| 03.35.22 |  | Power trowel finish | 1000 | SF | $ | - | $0 | $ | 0.58 | $580 | $ | 0.10 | $100 | $ | 0.68 | $680 |  |
| 03.39.23 |  | Misc. ST&S (cure, etc.) | 1 | Allow | $ | 100.00 | $100 | $ | 65.00 | $65 | $ | - | $0 | $ | 165.00 | $165 |  |
| 03.30.53 |  | Concrete Waste Factor 10% | 1 | LS | $ | 248.30 | $248 | $ | - | $0 | $ | - | $0 | $ | 248.30 | $248 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | SLAB ON GRADE - 6" Post tentioned | 1000 | SF | $ | 6.69 | $6,689 | $ | 8.38 | $8,379 | $ | 0.27 | $270 | $ | 15.34 | $15,338 |  |
| Summary Item: A10 Foundations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
| Uniformat II WBS | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| A10 | Foundations | 1000 | SF | $ | 30.03 | $30,028 | $ | 33.08 | $33,082 | $ | 7.29 | $7,293 | $ | 70.40 | $70,402 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1 - A10 - Foundations

6 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: B10 Superstructure |  |  |  |  |  |  |  |  |  |  | Total Cost: | $29,279 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| B1010 | FLOOR CONSTRUCTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | SEE FOUNDATION - SLAB ON GRADE | 0 | Unit | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | FLOOR CONSTRUCTION | 1000 | SF | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| B1020 | ROOF CONSTRUCTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 06.17.53 |  | Furnish & Install Wood Trusses 25' span | 36 | EA | $ | 151.00 | $5,436 | $ | 75.11 | $2,704 | $ | 10.00 | $360 | $ | 236.11 | $8,500 |  |
| 06.16.36 |  | F&I Plywood sheating - 5/8 CDX | 1960 | SF | $ | 0.72 | $1,411 | $ | 0.77 | $1,509 | $ | - | $0 | $ | 1.49 | $2,920 |  |
| 06.13.23 |  | 6x12 Rough Sawn Beams | 300 | BF | $ | 1.88 | $564 | $ | 1.11 | $333 | $ | - | $0 | $ | 2.99 | $897 |  |
| 05.12.23 |  | 4x4 x 1/4 HSS steel posts w/ Beam Bracket | 4 | EA | $ | 194.00 | $776 | $ | 195.00 | $780 | $ | 25.00 | $100 | $ | 414.00 | $1,656 |  |
| 06.05.23 |  | Hurricane Clips | 72 | EA | $ | 5.20 | $374 | $ | 2.34 | $168 | $ | - | $0 | $ | 7.54 | $543 |  |
| 04.43.10 |  | Stone Veneer on End Columns 24"x24"x8' | 320 | SF | $ | 20.50 | $6,560 | $ | 23.76 | $7,603 | $ | - | $0 | $ | 44.26 | $14,163 |  |
| 06.17.53 |  | Temp Bracing & Blocking Allowance | 1 | LS | $ | 500.00 | $500 | $ | 100.00 | $100 | $ | - | $0 | $ | 600.00 | $600 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | ROOF CONSTRUCTION | 1000 | SF | $ | 15.62 | $15,622 | $ | 13.20 | $13,198 | $ | 0.46 | $460 | $ | 29.28 | $29,279 |  |
| Summary Item: B10 Superstructure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
| Uniformat II WBS | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| B10 | Superstructure | 1000 | SF | $ | 15.62 | $15,622 | $ | 13.20 | $13,198 | $ | 0.46 | $460 | $ | 29.28 | $29,279 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1-B10 Superstructure

7 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: B20 Exterior Enclosure |  |  |  |  |  |  |  |  |  |  | Total Cost: | $65,469 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| B2010 | EXTERIOR WALLS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 06.11.10 |  | 2"x6"x8' studwall , 16" OC | 140 | LF | $ | 3.72 | $521 | $ | 7.96 | $1,114 | $ | - | $0 | $ | 11.68 | $1,635 |  |
| 06.16.36 |  | Exterior Sheating 1/2" CDX Plywood | 1120 | SF | $ | 0.78 | $874 | $ | 0.88 | $986 | $ | - | $0 | $ | 1.66 | $1,859 |  |
| 06.11.01 |  | Headers, Blocking, Bracing, & Bridging | 1 | LS | $ | 500.00 | $500 | $ | 500.00 | $500 | $ | - | $0 | $ | 1,000.00 | $1,000 |  |
| 07.21.16 |  | R-21 Batt Insullation | 1120 | SF | $ | 1.24 | $1,389 | $ | 0.41 | $459 | $ | - | $0 | $ | 1.65 | $1,848 |  |
| 07.46.23 |  | Vertical B&B Rough Sawn Cedar Siding | 450 | SF | $ | 5.62 | $2,529 | $ | 1.57 | $707 | $ | - | $0 | $ | 7.19 | $3,236 |  |
| 04.43.10 |  | Stone Wainscot | 560 | SF | $ | 20.50 | $11,480 | $ | 23.76 | $13,306 | $ | - | $0 | $ | 44.26 | $24,786 |  |
| 04.72.10 |  | Precast Wall Coping | 130 | LF | $ | 13.20 | $1,716 | $ | 10.24 | $1,331 | $ | - | $0 | $ | 23.44 | $3,047 |  |
| 06.11.10 |  | 2"x4"x4' Privacy Panel framing | 40 | LF | $ | 1.70 | $68 | $ | 7.96 | $318 | $ | - | $0 | $ | 9.66 | $386 |  |
|  |  | 2"x4"x4' Privacy Panel Sheating 1/2" CDX |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 06.16.36 |  | Plywood - 2 sides | 320 | SF | $ | 0.78 | $250 | $ | 0.88 | $282 | $ | - | $0 | $ | 1.66 | $531 |  |
| 07.25.10 |  | Building Wrap | 1120 | SF | $ | 0.32 | $358 | $ | 0.18 | $202 | $ | - | $0 | $ | 0.50 | $560 |  |
| SUBTOTAL | EXTERIOR WALLS | 1000 | SF | $ | 19.68 | $19,684 | $ | 19.20 | $19,204 | $ | - | $0 | $ | 38.89 | $38,888 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| B2020 | EXTERIOR WINDOWS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Wood Awning Windows, 34"x22", Dbl. pane, |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 08.52.10 |  | extra width sill, pre-finished custom color | 16 | EA | $ | 416.00 | $6,656 | $ | 220.48 | $3,528 | $ | - | $0 | $ | 636.48 | $10,184 |  |
| 06.22.13 |  | Interior and Exterior trim packages | 16 | ea | $ | 92.00 | $1,472 | $ | 162.24 | $2,596 | $ | - | $0 | $ | 254.24 | $4,068 |  |
| SUBTOTAL | EXTERIOR WINDOWS | 1000 | SF | $ | 8.13 | $8,128 | $ | 6.12 | $6,124 | $ | - | $0 | $ | 14.25 | $14,252 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1-B20 Exterior Enclosure

8 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: B20 Exterior Enclosure |  |  |  |  |  |  |  |  |  |  | Total Cost: | $65,469 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| B2030 | EXTERIOR DOORS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Hollow Metal Door Frames,14 Ga., 8-3/4 deep, |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 08.12.13 |  | 7-0x3-6 | 5 | EA | $ | 356.00 | $1,780 | $ | 117.10 | $586 | $ | - | $0 | $ | 473.10 | $2,366 |  |
|  |  | Hollow metal Door, Insulated 1-3/4 thick full |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 08.13.13. |  | panel, 18 ga., 7-0x3-6 | 5 | EA | $ | 670.00 | $3,350 | $ | 88.82 | $444 | $ | - | $0 | $ | 758.82 | $3,794 |  |
| 08.71.20 |  | Door Closer Heavy duty top jamb mount | 5 | EA | $ | 274.00 | $1,370 | $ | 549.12 | $2,746 | $ | - | $0 | $ | 823.12 | $4,116 |  |
| 08.71.20 |  | Door hardware, deadbolt, lock set, etc. | 5 | EA | $ | 336.00 | $1,680 | $ | 74.88 | $374 | $ | - | $0 | $ | 410.88 | $2,054 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | EXTERIOR DOORS | 1000 | SF | $ | 8.18 | $8,180 | $ | 4.15 | $4,150 | $ | - | $0 | $ | 12.33 | $12,330 |  |
| Summary Item: B20 Exterior Enclosure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
| Uniformat II WBS | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| B20 | Exterior Enclosure | 1000 | SF | $ | 35.99 | $35,992 | $ | 29.48 | $29,477 | $ | - | $0 | $ | 65.47 | $65,469 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1-B20 Exterior Enclosure

9 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: B30 Roofing |  |  |  |  |  |  |  |  |  |  | Total Cost: | $27,176 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| B3010 | ROOF COVERINGS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 07.41.13 |  | 22 Ga. Raised seam steel roof - standard finish | 1960 | SF | $ | 7.85 | $15,386 | $ | 3.04 | $5,958 | $ | - | $0 | $ | 10.89 | $21,344 |  |
| 07.41.13 |  | Roof Ridge Cap | 70 | LF | $ | 4.95 | $347 | $ | 4.99 | $349 | $ | - | $0 | $ | 9.94 | $696 |  |
| 07.65.23 |  | Ice And Water Shield - 3' at all edges | 500 | SF | $ | 2.92 | $1,460 | $ | 1.82 | $910 | $ | - | $0 | $ | 4.74 | $2,370 |  |
| 07.65.23 |  | Flashing allowance | 1 | LS | $ | 500.00 | $500 | $ | 150.00 | $150 | $ | - | $0 | $ | 650.00 | $650 |  |
| 07.71.23 |  | 5" Galvanized Gutters | 140 | LF | $ | 2.10 | $294 | $ | 6.19 | $867 | $ | - | $0 | $ | 8.29 | $1,161 |  |
| 07.71.23 |  | Downspouts | 56 | LF | $ | 2.65 | $148 | $ | 4.12 | $231 | $ | - | $0 | $ | 6.77 | $379 |  |
| 07.71.23 |  | Downspout Elbows | 12 | EA | $ | 7.15 | $86 | $ | 7.55 | $91 | $ | - | $0 | $ | 14.70 | $176 |  |
| 23.34.23 |  | Roof Jacks at Plumbing penetrations | 1 | Allow | $ | 250.00 | $250 | $ | 150.00 | $150 | $ | - | $0 | $ | 400.00 | $400 |  |
| SUBTOTAL | ROOF COVERINGS | 1000 | SF | $ | 18.47 | $18,471 | $ | 8.71 | $8,706 | $ | - | $0 | $ | 27.18 | $27,176 |  |
| Summary Item: B30 Roofing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
| Uniformat II WBS | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| B30 | Roofing | 1000 | SF | $ | 18.47 | $18,471 | $ | 8.71 | $8,706 | $ | - | $0 | $ | 27.18 | $27,176 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1-B30 Roofing

10 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: C10 Interior Construction |  |  |  |  |  |  |  |  |  |  | Total Cost: | $34,881 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| C1010 | INTERIOR PARTITIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 5/8" Gypsum; Mold resistant; on inside of |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 09.29.1 |  | exterior walls; Level 5 tape & skim coat | 1120 | SF | $ | 0.82 | $918 | $ | 1.65 | $1,848 | $ | - | $0 | $ | 2.47 | $2,766 |  |
|  |  | Interior partition framing - 2x4 x8' @ 16" O.C., |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 06.11.10 |  | single bottom & double top plate | 40 | LF | $ | 3.11 | $124 | $ | 10.66 | $426 | $ | - | $0 | $ | 13.77 | $551 |  |
| 06.11.10 |  | Add Pressure Treated Bottom Plate 2x4 | 40 | LF | $ | 0.86 | $34 | $ | 1.32 | $53 | $ | - | $0 | $ | 2.18 | $87 |  |
|  |  | 5/8" Gypsum; Mold resistant; on finish side of |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 09.29.10 |  | interior partions; Level 5 tape & skim coat | 320 | SF | $ | 0.82 | $262 | $ | 1.65 | $528 | $ | - | $0 | $ | 2.47 | $790 |  |
| 06.22.13 |  | Wood Base Molding | 156 | LF | $ | 2.85 | $445 | $ | 3.20 | $499 | $ | - | $0 | $ | 6.05 | $944 |  |
| 06.22.13 |  | Wood Rail Molding | 140 | LF | $ | 1.89 | $264 | $ | 2.36 | $331 | $ | - | $0 | $ | 4.25 | $595 |  |
| SUBTOTAL | INTERIOR PARTITIONS | 1000 | SF | $ | 2.05 | $2,048 | $ | 3.68 | $3,685 | $ | - | $0 | $ | 5.73 | $5,733 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| C1030 | FITTINGS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10.21.13 |  | Toilet Partitions F&C dual hung, Stainless Steel | 5 | EA | $ | 2,151.39 | $10,757 | $ | 255.36 | $1,277 | $ | - | $0 | $ | 2,406.75 | $12,034 |  |
| 10.21.13 |  | Handicap Addition | 2 | EA | $ | 404.89 | $810 | $ | - | $0 | $ | - | $0 | $ | 404.89 | $810 |  |
| 10.21.13 |  | Unrinal Screens, Floor mounted, Stainless Stl. | 2 | EA | $ | 815.00 | $1,630 | $ | 210.00 | $420 | $ | - | $0 | $ | 1,025.00 | $2,050 |  |
| 10.21.13 |  | Entrance Screens | 2 | EA | $ | 1,180.00 | $2,360 | $ | 88.00 | $176 | $ | - | $0 | $ | 1,268.00 | $2,536 |  |
| 05.50.00 |  | Fabricated Metal counter supports | 2 | Allow | $ | 450.00 | $900 | $ | 265.00 | $530 | $ | - | $0 | $ | 715.00 | $1,430 |  |
| 12.36.61 |  | Engineered Stone/Concrete Counter top | 16 | LF | $ | 98.00 | $1,568 | $ | 115.00 | $1,840 | $ | - | $0 | $ | 213.00 | $3,408 |  |
| 10.28.13 |  | Toilet Accessories | 1 | Allow | $ | 5,500.00 | $5,500 | $ | 1,380.00 | $1,380 | $ | - | $0 | $ | 6,880.00 | $6,880 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | FITTINGS | 1000 | SF | $ | 23.52 | $23,525 | $ | 5.62 | $5,623 | $ | - | $0 | $ | 29.15 | $29,148 |  |
| Summary Item: C10 Interior Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
| Uniformat II WBS | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| C10 | Interior Construction | 1000 | SF | $ | 25.57 | $25,573 | $ | 9.31 | $9,308 | $ | - | $0 | $ | 34.88 | $34,881 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1-C10 Interior Construct.

11 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: | C30 Interior Finishes |  |  |  |  |  |  |  |  |  |  | Total Cost: | $17,900 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| C3010 |  | WALL FINISHES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 09.96.56 |  | Epoxy Wall Coating, High Build 50 mil | 1280 | SF | $ | 1.48 | $1,894 | $ | 4.20 | $5,376 | $ | - | $0 | $ | 5.68 | $7,270 |  |
| 09.91.23 |  | Miscelaneous Interior paint | 1280 | SF | $ | 0.15 | $192 | $ | - | $0 | $ | - | $0 | $ | 0.15 | $192 |  |
| 09.91.23 |  | Interior Trim Painting | 650 | LF | $ | 0.16 | $104 | $ | 1.75 | $1,138 | $ | - | $0 | $ | 1.91 | $1,242 |  |
| 09.91.23 |  | Interior Window Casing Painting | 16 | EA | $ | 2.85 | $46 | $ | 60.00 | $960 | $ | - | $0 | $ | 62.85 | $1,006 |  |
| SUBTOTAL |  | WALL FINISHES | 1000 | SF | $ | 2.24 | $2,236 | $ | 7.47 | $7,474 | $ | - | $0 | $ | 9.71 | $9,710 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| C3020 |  | FLOOR FINISHES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 03.35.29 |  | 2 Coat Wpoxy Floor finish | 1000 | SF | $ | 0.32 | $320 | $ | 0.85 | $850 | $ | - | $0 | $ | 1.17 | $1,170 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL |  | FLOOR FINISHES | 1000 | SF | $ | 0.32 | $320 | $ | 0.85 | $850 | $ | - | $0 | $ | 1.17 | $1,170 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| C3030 |  | CEILING FINISHES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 09.29.10 |  | 5/8" Mold resistant Gypsum Drywall | 1000 | SF | $ | 0.82 | $820 | $ | 2.85 | $2,850 | $ | - | $0 | $ | 3.67 | $3,670 |  |
| 09.22.36 |  | Ceiling Lath | 1000 | SF | $ | 0.72 | $720 | $ | 1.15 | $1,150 | $ | - | $0 | $ | 1.87 | $1,870 |  |
| 09.91.23 |  | Paint Ceiling, Latex primer, 2 coats | 1000 | SF | $ | 0.38 | $380 | $ | 1.10 | $1,100 | $ | - | $0 | $ | 1.48 | $1,480 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL |  | CEILING FINISHES | 1000 | SF | $ | 1.92 | $1,920 | $ | 5.10 | $5,100 | $ | - | $0 | $ | 7.02 | $7,020 |  |
| Summary Item: | C30 Interior Finishes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
| Uniformat II WBS | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| C30 |  | Interior Finishes | 1000 | SF | $ | 4.48 | $4,476 | $ | 13.42 | $13,424 | $ | - | $0 | $ | 17.90 | $17,900 |  |

| BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1-C30 Interior Finishes | 12 of 38 |
| --- | --- |

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: D20 Plumbing Systems |  |  |  |  |  |  |  |  |  |  | Total Cost: | $42,776 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| D2010 | PLUMBING FIXTURES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 22.42.13 |  | F&I Urinals, Waterless | 2 | EA | $ | 510.00 | $1,020 | $ | 72.00 | $144 | $ | - | $0 | $ | 582.00 | $1,164 |  |
| 22.42.13 |  | Rough-in Urinals | 2 | EA | $ | 305.00 | $610 | $ | 372.48 | $745 | $ | - | $0 | $ | 677.48 | $1,355 |  |
| 22.42.13 |  | F&I Water Closets | 5 | EA | $ | 640.00 | $3,200 | $ | 240.00 | $1,200 | $ | - | $0 | $ | 880.00 | $4,400 |  |
| 22.42.13 |  | Rough-in Water Closets | 5 | EA | $ | 1,306.25 | $6,531 | $ | 390.67 | $1,953 | $ | - | $0 | $ | 1,696.92 | $8,485 |  |
| 22.41.16 |  | F&I Vanity Sinks, Self Rimming SS | 5 | EA | $ | 460.00 | $2,300 | $ | 225.00 | $1,125 | $ | - | $0 | $ | 685.00 | $3,425 |  |
| 22.41.16 |  | Rough-in F&I Vanity Sinks | 5 | EA | $ | 332.64 | $1,663 | $ | 624.00 | $3,120 | $ | - | $0 | $ | 956.64 | $4,783 |  |
| 22.42.39 |  | Faucets. Automatic Sensor | 5 | EA | $ | 488.00 | $2,440 | $ | 130.00 | $650 | $ | - | $0 | $ | 618.00 | $3,090 |  |
| 22.42.16 |  | Service floor sink | 1 | EA | $ | 920.00 | $920 | $ | 325.00 | $325 | $ | - | $0 | $ | 1,245.00 | $1,245 |  |
| 22.42.16 |  | Rough-in Floor sink | 1 | EA | $ | 115.00 | $115 | $ | 880.00 | $880 | $ | - | $0 | $ | 995.00 | $995 |  |
| SUBTOTAL | PLUMBING FIXTURES | 1000 | SF | $ | 18.80 | $18,799 | $ | 10.14 | $10,142 | $ | - | $0 | $ | 28.94 | $28,942 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| D2020 | DOMESTIC WATER DISTRIBUTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 22.11.13 |  | Additional 1" water Distribution Pipe | 160 | LF | $ | 8.18 | $1,309 | $ | 11.70 | $1,872 | $ | - | $0 | $ | 19.88 | $3,181 |  |
| 22.11.13 |  | Fitting Allowance 10% | 1 | Allow | $ | 130.88 | $131 | $ | - | $0 | $ | - | $0 | $ | 130.88 | $131 |  |
| 22.34.36 |  | Water Heater | 1 | EA | $ | 2,609.89 | $2,610 | $ | 570.24 | $570 | $ | - | $0 | $ | 3,180.13 | $3,180 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 |  |  | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | DOMESTIC WATER DISTRIBUTION | 1000 | SF | $ | 4.05 | $4,050 | $ | 2.44 | $2,442 | $ | - | $0 | $ | 6.49 | $6,492 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1-D20 Plumbing

13 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: D20 Plumbing Systems |  |  |  |  |  |  |  |  |  |  | Total Cost: | $42,776 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| D2030 | SANITARY WASTE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 22.13.16 |  | 4" Waste Collection Trunk line | 80 | LF | $ | 17.92 | $1,433 | $ | 26.21 | $2,097 | $ | - | $0 | $ | 44.12 | $3,530 |  |
| 22.13.16 |  | Floor drains | 4 | EA | $ | 349.87 | $1,399 | $ | 120.00 | $480 | $ | - | $0 | $ | 469.87 | $1,879 |  |
| 22.13.15 |  | 2" Waste Collection to Floor Drains | 40 | LF | $ | 13.83 | $553 | $ | 24.00 | $960 | $ | - | $0 | $ | 37.83 | $1,513 |  |
| 22.13.16 |  | Fitting Allowance 10% | 1 | Allow | $ | 419.77 | $420 | $ | - | $0 | $ | - | $0 | $ | 419.77 | $420 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | SANITARY WASTE | 1000 | SF | $ | 3.81 | $3,806 | $ | 3.54 | $3,537 | $ | - | $0 | $ | 7.34 | $7,342 |  |
| Summary Item: D20 Plumbing Systems |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
| Uniformat II WBS | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| D20 | Plumbing Systems | 1000 | SF | $ | 26.65 | $26,655 | $ | 16.12 | $16,121 | $ | - | $0 | $ | 42.78 | $42,776 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1-D20 Plumbing

14 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: D30 HVAC |  |  |  |  |  |  |  |  |  |  | Total Cost: | $2,438 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| D3040 | DISTRIBUTION SYSTEMS (HVAC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 23.31.13 |  | Ductwork | 80 | Lbs | $ | 0.66 | $53 | $ | 8.99 | $719 | $ | - | $0 | $ | 9.65 | $772 |  |
| 23.34.14 |  | 210 CFM Exhaust Blowers | 2 | EA | $ | 402.06 | $804 | $ | 91.20 | $182 | $ | - | $0 | $ | 493.26 | $987 |  |
| 32.37.13 |  | Intlet Grilles | 2 | EA | $ | 46.55 | $93 | $ | 42.24 | $84 | $ | - | $0 | $ | 88.79 | $178 |  |
| 36.37.15 |  | Exhaust Louvers | 2 | EA | $ | 59.25 | $119 | $ | 26.98 | $54 | $ | - | $0 | $ | 86.23 | $172 |  |
| 23.19.33 |  | Exhaust Controls | 2 | EA | $ | 100.00 | $200 | $ | 65.00 | $130 | $ | - | $0 | $ | 165.00 | $330 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | DISTRIBUTION SYSTEMS (HVAC) | 1000 | SF | $ | 1.27 | $1,269 | $ | 1.17 | $1,170 | $ | - | $0 | $ | 2.44 | $2,438 |  |
| Summary Item: D30 HVAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| D30 | HVAC | 1000 | SF | $ | 1.27 | $1,269 | $ | 1.17 | $1,170 |  | 0 | $0 | $ | 2.44 | $2,438 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1-D30 HVAC

15 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: | Oso Comida Trailhead Improvements: | Estimate By: | YtB |
| --- | --- | --- | --- |
| Park: | Bear Arbor NRA | Date: | 01/12/11 |
| Park Alpha: | BEAR | Reviewed By: | BBB |
| PMIS: | XXXXXX | Date: | 01/17/11 |

| Summary Item: D50 Electrical |  |  |  |  |  |  |  |  |  |  | Total Cost: | $18,118 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |
| Code |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |
|  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |
|  |  |  |  |  |  |  |  |  | Cost |  |  |
| D5010 | ELECTRICAL SERVICE & DISTRIBUTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1phz. 225 Amp, 120/208V, Service Panel & |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 26.24.16 | feeders | 1 | EA | $ | 1,551.83 | $1,552 | $ | 2,736.00 | $2,736 | $ | - | $0 | $ | 4,287.83 | $4,288 |
| SUBTOTAL | DISTRIBUTION | 1000 | SF | $ | 1.55 | $1,552 | $ | 2.74 | $2,736 | $ | - | $0 | $ | 4.29 | $4,288 |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |
| Code |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |
|  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |
|  |  |  |  |  |  |  |  |  | Cost |  |  |
| D5020 | LIGHTING & BRANCH WIRING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 26.51.13 | Energy Saving Fluorescent lighting fixtures | 8 | EA | $ | 349.13 | $2,793 | $ | 235.00 | $1,880 | $ | - | $0 | $ | 584.13 | $4,673 |
| 26.51.13 | Utility Chase lighting Fixtures | 2 | EA | $ | 160.00 | $320 | $ | 235.00 | $470 | $ | - | $0 | $ | 395.00 | $790 |
| 26.05.90 | Receptacles GFCI | 15 | EA | $ | 64.19 | $963 | $ | 70.08 | $1,051 | $ | - | $0 | $ | 134.27 | $2,014 |
| 26.05.90 | Switches | 3 | EA | $ | 38.87 | $117 | $ | 52.80 | $158 | $ | - | $0 | $ | 91.67 | $275 |
| 23.05.19 | 230V wiring to septic system | 1 | Allow | $ | 800.00 | $800 | $ | 350.00 | $350 | $ | - | $0 | $ | 1,150.00 | $1,150 |
| 26.05.80 | Wire Up Septic system | 1 | EA | $ | 45.00 | $45 | $ | 220.00 | $220 | $ | - | $0 | $ | 265.00 | $265 |
| 26.05.19 | Additional Building Wiring | 1 | Allow | $ | 500.00 | $500 | $ | 350.00 | $350 | $ | - | $0 | $ | 850.00 | $850 |
| SUBTOTAL | LIGHTING & BRANCH WIRING | 1000 | SF | $ | 5.54 | $5,538 | $ | 4.48 | $4,480 | $ | - | $0 | $ | 10.02 | $10,017 |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |
| Code |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |
|  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |
|  |  |  |  |  |  |  |  |  | Cost |  |  |
| D5090 | OTHER ELECTRICAL SYSTEMS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 23.83.33 | Baseboard Heaters for shoulder season | 10 | Ea | $ | 126.78 | $1,268 | $ | 188.16 | $1,882 | $ | - | $0 | $ | 314.94 | $3,149 |
| 23.83.33 | Wall thermostat | 3 | Ea | $ | 106.98 | $321 | $ | 67.00 | $201 | $ | - | $0 | $ | 173.98 | $522 |
| 26.05.19 | Wiring allowance | 1 | Allow | $ | 75.00 | $75 | $ | 67.00 | $67 | $ | - | $0 | $ | 142.00 | $142 |
| SUBTOTAL | OTHER ELECTRICAL SYSTEMS | 1000 | SF | $ | 1.66 | $1,664 | $ | 2.15 | $2,150 | $ | - | $0 | $ | 3.81 | $3,813 |
| Summary Item: D50 Electrical |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |
| Code |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |
|  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |
|  |  |  |  |  |  |  |  |  | Cost |  |  |
| D50 | Electrical | 1000 | SF | $ | 8.75 | $8,753 | $ | 9.37 | $9,365 | $ | - | $0 | $ | 18.12 | $18,118 |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1-D50 Electrical

16 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: F20 | Selective Building Demolition |  |  |  |  |  |  |  |  |  |  | Total Cost: | $6,315 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| F2010 | BUILDING ELEMENTS DEMOLITION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 02.41.19 |  | Demo structures- haul to dump; | 1 | Day | $ | - | $0 | $ | 1,650.00 | $1,650 | $ | 3,250.00 | $3,250 | $ | 4,900.00 | $4,900 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | BUILDING ELEMENTS DEMOLITION | 1000 | SF | $ | - | $0 | $ | 1.65 | $1,650 | $ | 3.25 | $3,250 | $ | 4.90 | $4,900 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| F2020 | HAZARDOUS COMPONENTS ABATEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 02.81.20 |  | Pump & Flush Existing pit toilets | 1 | LS | $ | - | $0 | $ | 165.00 | $165 | $ | 375.00 | $375 | $ | 540.00 | $540 |  |
| 31.23.23 |  | Import & Backfill pits | 50 | CY | $ | 9.25 | $463 | $ | 3.50 | $175 | $ | 4.75 | $238 | $ | 17.50 | $875 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | ABATEMENT | 1000 | SF | $ | 0.46 | $463 | $ | 0.34 | $340 | $ | 0.61 | $613 | $ | 1.42 | $1,415 |  |
| Summary Item: F20 | Selective Building Demolition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| F20 | Selective Building Demolition | 1000 | SF | $ | 0.46 | $463 | $ | 1.99 | $1,990 | $ | 3.86 | $3,863 | $ | 6.32 | $6,315 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1-F20 Selective Demo.

17 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: G10 Site Preparation |  |  |  |  |  |  |  |  |  |  | Total Cost: | $13,502 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G1010 | SITE CLEARING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 31.13.13 |  | Brush Mowing for Building Pad Area | 1 | Acre | $ | - | $0 | $ | 452.64 | $453 | $ | 265.32 | $265 | $ | 717.96 | $718 |  |
| 31.13.13 |  | Selective Tree Removal | 3 | Ea | $ | - | $0 | $ | 178.75 | $536 | $ | 154.44 | $463 | $ | 333.19 | $1,000 |  |
| 31.13.13 |  | Stump Removal | 3 | Ea | $ | - | $0 | $ | 36.22 | $109 | $ | 94.38 | $283 | $ | 130.60 | $392 |  |
| 31.14.13 |  | Strip & Stockpile Topsoil | 1000 | CY | $ | - | $0 | $ | 0.79 | $787 | $ | 1.37 | $1,373 | $ | 2.16 | $2,160 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | SITE CLEARING | 1000 | SF | $ | - | $0 | $ | 1.88 | $1,885 | $ | 2.38 | $2,385 | $ | 4.27 | $4,269 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G1030 | SITE EARTHWORK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 31.23.23 |  | Imported fill for building Pad | 250 | CY | $ | 8.75 | $2,188 | $ | 4.55 | $1,138 | $ | 6.55 | $1,638 | $ | 19.85 | $4,963 |  |
| 31.23.16 |  | Onsite Cut to fill | 500 | CY | $ | - | $0 | $ | 1.25 | $625 | $ | 3.55 | $1,775 | $ | 4.80 | $2,400 |  |
| 31.22.16 |  | Fine Grade Building Pad | 2000 | SF | $ | - | $0 | $ | 0.12 | $240 | $ | 0.24 | $480 | $ | 0.36 | $720 |  |
| 31.22.16 |  | Clean-up and Fine Grade around Building | 5000 | SF | $ | - | $0 | $ | 0.07 | $350 | $ | 0.10 | $500 | $ | 0.17 | $850 |  |
| 31.23.23 |  | Backfill & Compact existing pits | 50 | CY | $ | - | $0 | $ | 2.50 | $125 | $ | 3.50 | $175 | $ | 6.00 | $300 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | SITE EARTHWORK | 1000 | SF | $ | 2.19 | $2,188 | $ | 2.48 | $2,478 | $ | 4.57 | $4,568 | $ | 9.23 | $9,233 |  |
| Summary Item: G10 Site Preparation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G10 | Site Preparation | 1000 | SF | $ | 2.19 | $2,188 | $ | 4.36 | $4,362 | $ | 6.95 | $6,952 | $ | 13.50 | $13,502 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1-G10 Site Preparation

18 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: G20 Site Improvements |  |  |  |  |  |  |  |  |  |  | Total Cost: | $16,200 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G2030 | PEDESTRIAN PAVING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 32 06 10 |  | Concrete Flatwork at Building | 2000 | SF | $ | 4.45 | $8,900 | $ | 3.65 | $7,300 | $ | - | $0 | $ | 8.10 | $16,200 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | PEDESTRIAN PAVING | 1000 | SF | $ | 8.90 | $8,900 | $ | 7.30 | $7,300 | $ | - | $0 | $ | 16.20 | $16,200 |  |
| Summary Item: G20 Site Improvements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G20 | Site Improvements | 1000 | SF | $ | 8.90 | $8,900 | $ | 7.30 | $7,300 | $ | - | $0 | $ | 16.20 | $16,200 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1-G20  Site Improvements

19 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: G30 Site Mechanical Utilities |  |  |  |  |  |  |  |  |  |  | Total Cost: | $163,337 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G3010 | WATER SUPPLY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 33.21.13 |  | Drill water well | 1200 | VLF |  |  | $0 | $ | 14.39 | $17,265 | $ | 31.68 | $38,016 | $ | 46.07 | $55,281 |  |
| 33.21.13 |  | Install 8" Casing | 1200 | VLF | $ | 22.50 | $27,000 | $ | 2.50 | $3,000 | $ | 0.75 | $900 | $ | 25.75 | $30,900 |  |
| 33.21.13 |  | Install 2" Well pump | 1 | EA | $ | 641.89 | $642 | $ | 150.00 | $150 | $ | 100.00 | $100 | $ | 891.89 | $892 |  |
| 33.21.13 |  | 2" HDPE pump riser | 1200 | VLF | $ | 3.50 | $4,200 | $ | - | $0 | $ | - | $0 | $ | 3.50 | $4,200 |  |
| 22.11.13 |  | 2" Supply Line to building | 150 | LF | $ | 3.50 | $525 | $ | 2.50 | $375 | $ | 4.00 | $600 | $ | 10.00 | $1,500 |  |
| 22.11.19 |  | Pressure equilization tank in Building | 1 | Ea | $ | 250.00 | $250 | $ | 100.00 | $100 | $ | 50.00 | $50 | $ | 400.00 | $400 |  |
| 33.21.13 |  | Pump control system with alarm | 1 | Allow | $ | 250.00 | $250 | $ | 100.00 | $100 | $ | 50.00 | $50 | $ | 400.00 | $400 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | WATER SUPPLY | 1000 | SF | $ | 32.87 | $32,867 | $ | 20.99 | $20,990 | $ | 39.72 | $39,716 | $ | 93.57 | $93,572 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G3020 | SANITARY SEWER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 33.36.13 |  | Install Septic King Tank & Treatment system | 1 | LS | $ | 46,000.00 | $46,000 | $ | 4,500.00 | $4,500 | $ | 2,500.00 | $2,500 | $ | 53,000.00 | $53,000 |  |
| 33.36.13 |  | Excavate Leach Field | 90 | CY |  |  | $0 | $ | 11.20 | $1,008 | $ | 3.80 | $342 | $ | 15.00 | $1,350 |  |
| 33.36.13 |  | Install Leach Field Chamber System | 16 | EA | $ | 395.00 | $6,320 | $ | 265.00 | $4,240 | $ | 72.50 | $1,160 | $ | 732.50 | $11,720 |  |
| 33.36.13 |  | Backfill with Drain Rock | 25 | Tons | $ | 23.50 | $588 | $ | 19.50 | $488 | $ | 8.50 | $213 | $ | 51.50 | $1,288 |  |
| 33.36.13 |  | Common Backfill Leach Field Mound | 90 | CY | $ | - | $0 | $ | 11.20 | $1,008 | $ | 3.80 | $342 | $ | 15.00 | $1,350 |  |
| 36.31.13 |  | Sewer outfall from building | 75 | LF | $ | 5.85 | $439 | $ | 4.65 | $349 | $ | 3.60 | $270 | $ | 14.10 | $1,058 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | SANITARY SEWER | 1000 | SF | $ | 53.35 | $53,346 | $ | 11.59 | $11,592 | $ | 4.83 | $4,827 | $ | 69.77 | $69,765 |  |
| Summary Item: G30 Site Mechanical Utilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G30 | Site Mechanical Utilities | 1000 | SF | $ | 86.21 | $86,213 | $ | 32.58 | $32,582 |  | 44.5425 | $44,543 | $ | 163.34 | $163,337 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1-G30  Site Mechanical

20 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: G40 Site Electrical Utilities |  |  |  |  |  |  |  |  |  |  | Total Cost: | $5,000 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G4010 | ELECTRICAL DISTRIBUTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 33.71.19 |  | Electrical Service Drop by utility company | 1 | LS | $ | 2,500.00 | $2,500 | $ | - | $0 | $ | - | $0 | $ | 2,500.00 | $2,500 |  |
| 33.71.19 |  | Transformer & Main disconnect | 1 | EA | $ | 2,500.00 | $2,500 | $ | - | $0 | $ | - | $0 | $ | 2,500.00 | $2,500 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | ELECTRICAL DISTRIBUTION | 1000 | SF | $ | 5.00 | $5,000 | $ | - | $0 | $ | - | $0 | $ | 5.00 | $5,000 |  |
| Summary Item: G40 Site Electrical Utilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G40 | Site Electrical Utilities | 1000 | SF | $ | 5.00 | $5,000 | $ | - | $0 | $ | - | $0 | $ | 5.00 | $5,000 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1-G40  Site Electrical

21 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: XX | General Conditions |  |  |  |  |  |  |  |  |  |  | Total Cost: | $151,710 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| 01 31 |  | Project Management & Coordination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01.31.13 |  | Project Superintendent | 20 | Weeks | $ | - | $0 | $ | 2,500.00 | $50,000 | $ | - | $0 | $ | 2,500.00 | $50,000 |  |
| 01.31.13 |  | Project Manager - Half Time | 18 | Weeks | $ | - | $0 | $ | 750.00 | $13,500 | $ | - | $0 | $ | 750.00 | $13,500 |  |
| 01.31.13 |  | General Pupose Laborer - Part Time | 15 | Weeks | $ | - | $0 | $ | 1,500.00 | $22,500 | $ | - | $0 | $ | 1,500.00 | $22,500 |  |
| 01.31.13 |  | Builders Risk Insurance | 1 | LS | $ | 3,500.00 | $3,500 | $ | - | $0 | $ | - | $0 | $ | 3,500.00 | $3,500 |  |
| 01.31.13 |  | General Liabiity Insurance | 1 | LS | $ | 2,000.00 | $2,000 | $ | - | $0 | $ | - | $0 | $ | 2,000.00 | $2,000 |  |
| 01.31.13 |  | Payment & Performance Bond 1.5% | 1 | Unit | $ 15,000.00 | $15,000 | $ | - | $0 | $ | - | $0 | $ 15,000.00 | $15,000 |  |
| 01.31.xx | Labor down time due to payroll interviews | 1 | LS | $ | - | $0 | $ | 3,500.00 | $3,500 | $ | - | $0 | $ | 3,500.00 | $3,500 |  |
| 01.31.xx | Certified Payrol Costs | 0 | Unit | $ | - | $0 | $ | 500.00 | $0 | $ | - | $0 | $ | 500.00 | $0 |  |
| SUBTOTAL | Project Management & Coordination | 1000 | SF | $ | 20.50 | $20,500 | $ | 89.50 | $89,500 | $ | - | $0 | $ | 110.00 | $110,000 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| 01 32 |  | Scheduling & Documentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01.32.13 |  | Prepare Initial Schedule | 1 | LS | $ | - | $0 | $ | 3,000.00 | $3,000 | $ | - | $0 | $ | 3,000.00 | $3,000 |  |
| 01.32.13 |  | Schedule Updates | 13 | EA | $ | - | $0 | $ | 250.00 | $3,250 | $ | - | $0 | $ | 250.00 | $3,250 |  |
| 01.32.13 |  | Schedule Printing & Reproduction | 1 | Allow | $ | 300.00 | $300 | $ | - | $0 | $ | - | $0 | $ | 300.00 | $300 |  |
| 01.50.00 |  | Prepare SWMPP | 1 | LS | $ | 50.00 | $50 | $ | 1,500.00 | $1,500 | $ | - | $0 | $ | 1,550.00 | $1,550 |  |
| SUBTOTAL | Scheduling & Documentation | 1000 | SF | $ | 0.35 | $350 | $ | 7.75 | $7,750 | $ | - | $0 | $ | 8.10 | $8,100 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| 01 45 |  | Quality control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01.45.23 |  | Concrete Testing | 5 | EA | $ | 150.00 | $750 | $ | - | $0 | $ | - | $0 | $ | 150.00 | $750 |  |
| 01.45.23 |  | Compaction Testing | 10 | EA | $ | 75.00 | $750 | $ | - | $0 | $ | - | $0 | $ | 75.00 | $750 |  |
| 01.45.23 |  | Other Testing | 1 | LS | $ | 500.00 | $500 | $ | - | $0 | $ | - | $0 | $ | 500.00 | $500 |  |
| 01.40.00 |  | Special Inspections | 1 | Allow |  |  | $0 | $ | 1,500.00 | $1,500 | $ | - | $0 | $ | 1,500.00 | $1,500 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | Quality control | 1000 | SF | $ | 2.00 | $2,000 | $ | 1.50 | $1,500 | $ | - | $0 | $ | 3.50 | $3,500 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1 General Conditions

22 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: XX | General Conditions |  |  |  |  |  |  |  |  |  |  | Total Cost: | $151,710 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| 01 51 |  | Temporary Utilites |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01.51.13 |  | Install Temporary Power | 1 | LS | $ | 500.00 | $500 | $ | - | $0 | $ | - | $0 | $ | 500.00 | $500 |  |
| 01.51.13 |  | Temporary Electricity | 7 | Month | $ | 150.00 | $1,050 | $ | - | $0 | $ | - | $0 | $ | 150.00 | $1,050 |  |
| 01.51.13 |  | Chemical Toilets | 12 | Ea-Mo. | $ | 175.00 | $2,100 | $ | - | $0 | $ | - | $0 | $ | 175.00 | $2,100 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | Temporary Utilites | 1000 | SF | $ | 3.65 | $3,650 | $ | - | $0 | $ | - | $0 | $ | 3.65 | $3,650 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| 01 52 |  | Construction Facilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01.52.13 |  | Office Trailer Set Up | 1 | LS | $ | - | $0 | $ | 1,200.00 | $1,200 | $ | 300.00 | $300 | $ | 1,500.00 | $1,500 |  |
| 01.52.13 |  | Trailer Rental | 7 | Month | $ | - | $0 | $ | - | $0 | $ | 380.00 | $2,660 | $ | 380.00 | $2,660 |  |
| 01.52.13 |  | Storage Bin Rental | 15 | Ea-Mo | $ | - | $0 | $ | - | $0 | $ | 75.00 | $1,125 | $ | 75.00 | $1,125 |  |
| 01.52.13 |  | Temporary Fence | 300 | LF | $ | - | $0 | $ | - | $0 | $ | 6.50 | $1,950 | $ | 6.50 | $1,950 |  |
| 01.52.13 |  | Gravel Surrface For Yard | 50 | Tons | $ | 18.00 | $900 | $ | 5.00 | $250 | $ | 7.50 | $375 | $ | 30.50 | $1,525 |  |
| 01.52.13 |  | Erosion control | 1 | LS | $ | 2,000.00 | $2,000 | $ | 1,000.00 | $1,000 | $ | 500.00 | $500 | $ | 3,500.00 | $3,500 |  |
| 01.54.16 |  | Sky Trac Fork Lift Rental | 6 | Months | $ | - | $0 | $ | - | $0 | $ | 700.00 | $4,200 | $ | 700.00 | $4,200 |  |
| 01.52.13 |  | Miscelaneous Facilties | 1 | Allow | $ | 2,500.00 | $2,500 | $ | - | $0 | $ | - | $0 | $ | 2,500.00 | $2,500 |  |
| SUBTOTAL | Construction Facilities | 1000 | SF | $ | 5.40 | $5,400 | $ | 2.45 | $2,450 | $ | 11.11 | $11,110 | $ | 18.96 | $18,960 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1 General Conditions

23 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: XX | General Conditions |  |  |  |  |  |  |  |  |  |  | Total Cost: | $151,710 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| 01 54 36 |  | Mobilizaton |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01.54.36 |  | Mobilization | 1 | Allw | $ | - | $0 | $ | - | $0 | $ | 7,500.00 | $7,500 | $ | 7,500.00 | $7,500 |  |
| 01.54.36 |  | Demobilization | 0 | Unit | $ | - | $0 | $ | - | $0 | $ | 5,000.00 | $0 | $ | 5,000.00 | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | Mobilizaton | 1000 | SF | $ | - | $0 | $ | - | $0 | $ | 7.50 | $7,500 | $ | 7.50 | $7,500 |  |
| Summary Item: XX | General Conditions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| XX | General Conditions | 1000 | SF | $ | 31.90 | $31,900 | $ | 101.20 | $101,200 | $ | 18.61 | $18,610 | $ | 151.71 | $151,710 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 1 General Conditions

24 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

BID ITEM COST SUMMARY

|  | Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Estimate By: |  | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date: |  | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Reviewed By: |  |  |  |
| PMIS Number: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date: |  |  |  |
|  |  | Bid Item Number | Asset / Project Element / Description |  | Size/Count |  | Units |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | BID ITEM 2 |  | New Parking Lot & Site Utilities |  | 1 |  | LS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Item | WBS | Description |  | Material |  | Total Material | Labor Cost/Unit | Total Labor Cost |  | Equipment | Total Equipment |  | Direct |  | Total Direct | NET Cost/Unit | Total NET Costs |  |
| No. |  |  |  | Cost/Unit |  | Cost |  |  |  | Cost/Unit |  | Cost |  | Cost/Unit |  | Costs |  |  |  |
| 1 | G10 | Site Preparation | $ | 2,500.00 | $ | 2,500 | $ | 11,710.58 | $ | 11,711 | $ | 19,775.94 | $ | 19,776 | $ | 33,987 | $ | 33,987 | $ | 53,471.16 | $ | 53,471 |  |
| 2 | G20 | Site Improvements | $ | 143,581.04 | $ | 143,581 | $ | 36,335.00 | $ | 36,335 | $ | 43,670.00 | $ | 43,670 | $ | 223,586 | $ | 223,586 | $ | 351,769.04 | $ | 351,769 |  |
| 3 | G30 | Site Mechanical Utilities | $ | 12,153.36 | $ | 12,153 | $ | 14,232.07 | $ | 14,232 | $ | 4,240.55 | $ | 4,241 | $ | 30,626 | $ | 30,626 | $ | 48,184.01 | $ | 48,184 |  |
| 4 | XX | Bid Item 2 General Conditions | $ | 12,925.00 | $ | 12,925 | $ | 8,350.00 | $ | 8,350 | $ | 6,500.00 | $ | 6,500 | $ | 27,775 | $ | 27,775 | $ | 43,698.55 | $ | 43,699 |  |
|  |  | Subtotal Direct Construction Costs | $ | 171,159.40 | $ | 171,159 | $ | 70,627.65 | $ | 70,628 | $ | 74,186.49 | $ | 74,186 | $ | 315,974 |  | $315,974 | $ | 497,122.76 |  | $497,123 |  |
|  | Total Value of Government Furnished Property (GFP) Inc. in Direct Cost . |  | $0.00 |  |  | $ | - |  |  | $ | - | $ | - |  | $0 | In most cases GFP is normally zero - |  |
|  |  | Direct Cost Subtotal without GFP . | $ | 171,159 |  |  | $ | 70,628 |  |  | $ | 74,186 |  |  |  | $315,974 |  | see footnote- |  |
|  |  | Design Contingency |  | 2.00% |  |  |  |  |  |  |  |  |  |  |  |  |  | $6,319 |  |  |  |  |  |
|  |  | Total Direct Construction Costs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $322,293 |  |  |  |  |  |
|  |  | Standard General Conditions |  | 0.00% | Applied to Total Direct Construction Cost less GFP |  |  |  |  |  |  |  |  | $0 |  |  |  |  |  |
|  |  | Government General Conditions |  | 3.00% | Applied to Total Direct Construction Cost less GFP |  |  |  |  |  |  |  |  | $9,669 |  |  |  |  |  |
|  |  | Subtotal NET Construction Cost |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $331,962 |  |  |  |  |  |
|  |  | Overhead |  | 8.50% |  |  |  |  |  |  |  |  |  |  |  |  |  | $28,217 |  |  |  |  |  |
|  |  | Profit |  | 10.00% |  |  |  |  |  |  |  |  |  |  |  |  |  | $33,196 |  |  |  |  |  |
|  |  | Estimated NET Construction Cost |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $393,375 |  |  |  |  |  |
|  |  | Contracting Method Adjustment |  | 15.00% |  |  |  |  |  |  |  |  |  |  |  |  |  | $59,006 |  |  |  |  |  |
|  |  | Inflation Escalation |  | 32 |  | Months |  | Annual Rate = |  | 3.60% |  |  |  |  |  |  |  | $44,742 |  |  |  |  |  |
|  | Total Estimated NET Cost of Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $497,123 |  |  |  |  |  |

GFP costs only apply when the Government pre-purchases items, or provides other materials out of Government inventory, to be installed by contractor. Adjustments and Markup on GFP only include Inflation Escalation; No other adjustment factors or O&P markup have been applied.

BEAR Trailhead - 100% Draft Class A Cost Estimate

Bid Item 2 Summary

Page 25 of 38

Print Date: 1/24/2011, 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: G10 Site Preparation |  |  |  |  |  |  |  |  |  |  | Total Cost: | $33,987 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G1010 | SITE CLEARING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 31.25.13 |  | Erosion Control | 1 | LS | $ | 2,500.00 | $2,500 | $ | 1,450.00 | $1,450 | $ | 1,250.00 | $1,250 | $ | 5,200.00 | $5,200 |  |
| 31.13.13 |  | Clear & Grub Parking Area | 40000 | SF | $ | - | $0 | $ | 0.12 | $4,800 | $ | 0.19 | $7,600 | $ | 0.31 | $12,400 |  |
| 31.13.13 |  | Selective Tree Removal | 7 | Ea | $ | - | $0 | $ | 178.75 | $1,251 | $ | 154.44 | $1,081 | $ | 333.19 | $2,332 |  |
| 31.13.13 |  | Stump Removal | 7 | Ea | $ | - | $0 | $ | 36.22 | $254 | $ | 94.38 | $661 | $ | 130.60 | $914 |  |
| 31.13.13 |  | Strip & Stockpile Topsoil | 1500 | CY | $ | - | $0 | $ | 0.79 | $1,181 | $ | 1.37 | $2,059 | $ | 2.16 | $3,240 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | SITE CLEARING | 1 | LS | $ 2,500.00 | $2,500 | $ 8,935.58 | $8,936 | $ | 12,650.94 | $12,651 | $ | 24,086.52 | $24,087 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G1030 | SITE EARTHWORK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 31.23.16 |  | Onsite Cut to Fill | 1500 | CY | $ | - | $0 | $ | 1.25 | $1,875 | $ | 3.55 | $5,325 | $ | 4.80 | $7,200 |  |
| 31.23.13 |  | Scarify & Recompact Parking area | 30000 | SF | $ | - | $0 | $ | 0.03 | $900 | $ | 0.06 | $1,800 | $ | 0.09 | $2,700 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | SITE EARTHWORK | 1 | LS | $ | - | $0 | $ 2,775.00 | $2,775 | $ 7,125.00 | $7,125 | $ 9,900.00 | $9,900 |  |
| Summary Item: G10 Site Preparation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G10 | Site Preparation | 1 | LS | $ 2,500.00 | $2,500 | $ 11,710.58 | $11,711 | $ 19,775.94 | $19,776 | $ 33,986.52 | $33,987 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 2-G10 Site Preparation

26 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: G20 Site Improvements |  |  |  |  |  |  |  |  |  |  |  | Total Cost: | $223,586 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |  |
| G2020 | PARKING LOTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 31.21.16 |  | Subgrade Prep Parking Lot | 4500 | SY | $ | - | $0 | $ | 0.07 | $315 | $ | 0.75 | $3,375 | $ | 0.82 | $3,690 |  |
| 32.11.23 |  | Furnish & Install 6" Roadbase | 4500 | SY | $ | 6.79 | $30,543 | $ | 1.25 | $5,625 | $ | 3.15 | $14,175 | $ | 11.19 | $50,343 |  |
| 32.12.16 |  | Furnish & Install 3" Asphalt Paving | 4500 | SY | $ | 11.85 | $53,325 | $ | 1.28 | $5,760 | $ | 3.15 | $14,175 | $ | 16.28 | $73,260 |  |
| 32.17.23 |  | Striping | 40 | Spaces | $ | 14.11 | $564 | $ | 27.00 | $1,080 | $ | 8.00 | $320 | $ | 49.11 | $1,964 |  |
| 32.17.23 |  | Accessible spaces | 7 | EA | $ | 92.00 | $644 | $ | 145.00 | $1,015 | $ | 35.00 | $245 | $ | 272.00 | $1,904 |  |
| 10.14.53 |  | Sign Allowance | 1 | Allow | $ | 2,500.00 | $2,500 | $ | 500.00 | $500 | $ | - | $0 | $ | 3,000.00 | $3,000 |  |
| 32.16.13 |  | Curb & Gutter | 1000 | LF | $ | 12.83 | $12,825 | $ | 4.50 | $4,500 | $ | 8.00 | $8,000 | $ | 25.33 | $25,325 |  |
| 32.17.23 |  | Striping - RV Spaces | 10 | EA | $ | 98.00 | $980 | $ | 47.00 | $470 | $ | 18.00 | $180 | $ | 163.00 | $1,630 |  |
| SUBTOTAL | PARKING LOTS | 1 | LS | $ | 101,381.04 | $101,381 | $ | 19,265.00 | $19,265 | $ | 40,470.00 | $40,470 | $ | 161,116.04 | $161,116 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |  |
| G2030 | PEDESTRIAN PAVING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 03.30.53 |  | Pedestrian Sidewalks at parking lot | 3500 | SF | $ | 5.20 | $18,200 | $ | 3.12 | $10,920 | $ | - | $0 | $ | 8.32 | $29,120 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | PEDESTRIAN PAVING | 1 | LS | $ | 18,200.00 | $18,200 | $ | 10,920.00 | $10,920 | $ | - | $0 | $ | 29,120.00 | $29,120 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 2-G20  Site Improvement

27 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: | Estimate By: | YtB |
| --- | --- | --- |
| Park: Bear Arbor NRA | Date: | 01/12/11 |
| Park Alpha: BEAR | Reviewed By: | BBB |
| PMIS: XXXXXX | Date: | 01/17/11 |
| Summary Item: G20 Site Improvements | Total Cost: | $223,586 |

| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  |  | Cost/Unit |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G2050 | LANDSCAPING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 32.90.00 | Parking lot landscape allowance | 1 | LS | $ | 17,500.00 | $17,500 | $ | 4,250.00 | $4,250 | $ | 2,500.00 | $2,500 | $ | 24,250.00 | $24,250 |
| 32.93.43 | Install Selective Trees | 20 | EA | $ | 325.00 | $6,500 | $ | 95.00 | $1,900 | $ | 35.00 | $700 | $ | 455.00 | $9,100 |
| SUBTOTAL | LANDSCAPING | 1 | LS | $ | 24,000.00 | $24,000 | $ | 6,150.00 | $6,150 | $ | 3,200.00 | $3,200 | $ | 33,350.00 | $33,350 |

Summary Item: G20 Site Improvements

| Uniformat II WBS |  |  |  | MATERIAL | LABOR | EQUIPMENT | TOTALS |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Description | Quantity | Unit | Material | Total Material | Labor | Total Labor | Equipment | Total | Total |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Equipment |  | Total Cost |
|  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |
|  |  |  |  |  |  |  |  |  | Cost |  |  |
| G20 | Site Improvements | 1 | LS | $ 143,581.04 | $143,581 | $ 36,335.00 | $36,335 | $ 43,670.00 | $43,670 | $ 223,586.04 | $223,586 |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 2-G20  Site Improvement

28 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: G30 Site Mechanical Utilities |  |  |  |  |  |  |  |  |  |  | Total Cost: | $30,626 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G3030 | STORM SEWER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 33.41.13 |  | 18" Reinforced concrete Pipe | 300 | LF | $ | 26.03 | $7,809 | $ | 24.29 | $7,286 | $ | 3.50 | $1,050 | $ | 53.82 | $16,145 |  |
| 33.41.13 |  | 18" Flared End Section | 3 | EA | $ | 86.95 | $261 | $ | 11.89 | $36 | $ | 6.85 | $21 | $ | 105.69 | $317 |  |
| 33.41.13 |  | Water Quality Detention Pond | 1 | Allow | $ | 1,500.00 | $1,500 | $ | 3,500.00 | $3,500 | $ | 3,000.00 | $3,000 | $ | 8,000.00 | $8,000 |  |
| 33 44 13 |  | Storm Drain inlets | 2 | EA | $ | 1,292.00 | $2,584 | $ | 1,705.00 | $3,410 | $ | 85.00 | $170 | $ | 3,082.00 | $6,164 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | STORM SEWER | 1 | LS | $ | 12,153.36 | $12,153 | $ | 14,232.07 | $14,232 | $ | 4,240.55 | $4,241 | $ | 30,625.98 | $30,626 |  |
| Summary Item: G30 Site Mechanical Utilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G30 | Site Mechanical Utilities | 1 | LS | $ 12,153.36 | $12,153 | $ 14,232.07 | $14,232 |  | 4240.55 | $4,241 | $ 30,625.98 | $30,626 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 2-G30  Site Mechanical

29 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: XX | Bid Item 2 General Conditions |  |  |  |  |  |  |  |  |  |  | Total Cost: | $27,775 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| 01 31 |  | Project Management & Coordination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01.31.13 |  | Project Superintendent | 2 | Weeks | $ | - | $0 | $ | 2,500.00 | $5,000 | $ | - | $0 | $ | 2,500.00 | $5,000 |  |
| 01.31.13 |  | Project Manager - Half Time | 1 | Weeks | $ | - | $0 | $ | 750.00 | $750 | $ | - | $0 | $ | 750.00 | $750 |  |
| 01.31.13 |  | General Pupose Laborer - Part Time | 1 | Weeks | $ | - | $0 | $ | 1,500.00 | $1,500 | $ | - | $0 | $ | 1,500.00 | $1,500 |  |
| 01.31.13 |  | Builders Risk Insurance | 1 | LS | $ | 500.00 | $500 | $ | - | $0 | $ | - | $0 | $ | 500.00 | $500 |  |
| 01.31.13 |  | General Liabiity Insurance | 1 | LS | $ | 250.00 | $250 | $ | - | $0 | $ | - | $0 | $ | 250.00 | $250 |  |
| 01.31.13 |  | Payment & Performance Bond 1.5% | 1 | Unit | $ | 7,500.00 | $7,500 | $ | - | $0 | $ | - | $0 | $ | 7,500.00 | $7,500 |  |
| 01.31.xx | Labor down time due to payroll interviews | 1 | LS | $ | - | $0 | $ | 500.00 | $500 | $ | - | $0 | $ | 500.00 | $500 |  |
| 01.31.xx | Certified Payroll Costs | 0 | Unit | $ | - | $0 | $ | 150.00 | $0 | $ | - | $0 | $ | 150.00 | $0 |  |
| SUBTOTAL | Project Management & Coordination | 1000 | SF | $ | 8.25 | $8,250 | $ | 7.75 | $7,750 | $ | - | $0 | $ | 16.00 | $16,000 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| 01 45 |  | Quality control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.45.23 |  | Concrete Testing | 12 | EA | $ | 150.00 | $1,800 | $ | - | $0 | $ | - | $0 | $ | 150.00 | $1,800 |  |
| 01.45.23 |  | Compaction Testing | 25 | EA | $ | 75.00 | $1,875 | $ | - | $0 | $ | - | $0 | $ | 75.00 | $1,875 |  |
| 01.45.23 |  | Other Testing | 1 | LS | $ | 1,000.00 | $1,000 | $ | - | $0 | $ | - | $0 | $ | 1,000.00 | $1,000 |  |
| 01.45.23 |  | Special Inspections | 1 | Allow |  |  | $0 | $ | 600.00 | $600 | $ | - | $0 | $ | 600.00 | $600 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | Quality control | 1 | LS | $ 4,675.00 | $4,675 | $ | 600.00 | $600 | $ | - | $0 | $ 5,275.00 | $5,275 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 2 General Conditions

30 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: XX | Bid Item 2 General Conditions |  |  |  |  |  |  |  |  |  |  | Total Cost: | $27,775 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| 01 54 |  | Mobilizaton |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01.54.36 |  | Mobilization | 1 | Allow | $ | - | $0 | $ | - | $0 | $ | 6,500.00 | $6,500 | $ | 6,500.00 | $6,500 |  |
| 01.54.36 |  | Demobilization | 0 | Unit | $ | - | $0 | $ | - | $0 | $ | 4,000.00 | $0 | $ | 4,000.00 | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | Mobilizaton | 1 | LS | $ | - | $0 | $ | - | $0 | $ 6,500.00 | $6,500 | $ 6,500.00 | $6,500 |  |
| Summary Item: XX Bid Item 2 General Conditions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| XX | Bid Item 2 General Conditions | 1 | LS | $ 12,925.00 | $12,925 | $ 8,350.00 | $8,350 | $ 6,500.00 | $6,500 | $ 27,775.00 | $27,775 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 2 General Conditions

31 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

BID ITEM COST SUMMARY

|  | Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Estimate By: |  | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date: |  | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Reviewed By: |  | BBB |  |
| PMIS Number: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date: |  | 01/17/11 |  |
|  |  | Bid Item Number | Asset / Project Element / Description |  | Size/Count |  | Units |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | BID ITEM 3 | Picnic Area & Trailhead Improvement |  | 1 |  | LS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Item | WBS | Description |  | Material |  | Total Material | Labor Cost/Unit | Total Labor Cost |  | Equipment | Total Equipment |  | Direct |  | Total Direct | NET Cost/Unit | Total NET Costs |  |
| No. |  |  |  | Cost/Unit |  | Cost |  |  |  | Cost/Unit |  | Cost |  | Cost/Unit |  | Costs |  |  |  |
| 1 | G10 | Site Preparation | $ | - | $ | - | $ | 11,860.00 | $ | 11,860 | $ | 4,845.00 | $ | 4,845 | $ | 16,705 | $ | 16,705 | $ | 26,282.06 | $ | 26,282 |  |
| 2 | G20 | Site Improvements | $ | 59,447.50 | $ | 59,448 | $ | 25,960.00 | $ | 25,960 | $ | 12,269.50 | $ | 12,270 | $ | 97,677 | $ | 97,677 | $ | 153,675.72 | $ | 153,676 |  |
| 3 | G30 | Site Mechanical Utilities | $ | 2,124.73 | $ | 2,125 | $ | 2,274.65 | $ | 2,275 | $ | 330.37 | $ | 330 | $ | 4,730 | $ | 4,730 | $ | 7,441.34 | $ | 7,441 |  |
| 6 | XX | Bid Item 3 General Conditions | $ | 5,775.00 | $ | 5,775 | $ | 7,550.00 | $ | 7,550 | $ | 2,500.00 | $ | 2,500 | $ | 15,825 | $ | 15,825 | $ | 24,897.55 | $ | 24,898 |  |
| 7 | XX |  | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - |  |
| 8 | XX |  | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - | $ | - |  |
|  |  | Subtotal Direct Construction Costs | $ | 67,347.23 | $ | 67,347 | $ | 47,644.65 | $ | 47,645 | $ | 19,944.87 | $ | 19,945 | $ | 134,937 |  | $134,937 | $ | 212,296.67 |  | $212,297 |  |
|  | Total Value of Government Furnished Property (GFP) Inc. in Direct Cost . |  | $0.00 |  |  | $ | - |  |  | $ | - | $ | - |  | $0 | In most cases GFP is normally zero - |  |
|  |  | Direct Cost Subtotal without GFP . | $ | 67,347 |  |  | $ | 47,644.65 |  |  | $ | 19,944.87 |  |  |  | $134,937 |  | see footnote- |  |
|  |  | Design Contingency |  | 2.00% |  |  |  |  |  |  |  |  |  |  |  |  |  | $2,699 |  |  |  |  |  |
|  |  | Total Direct Construction Costs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $137,635 |  |  |  |  |  |
|  |  | Standard General Conditions |  | 0.00% | Applied to Total Direct Construction Cost less GFP |  |  |  |  |  |  |  |  | $0 |  |  |  |  |  |
|  |  | Government General Conditions |  | 3.00% | Applied to Total Direct Construction Cost less GFP |  |  |  |  |  |  |  |  | $4,129 |  |  |  |  |  |
|  |  | Subtotal NET Construction Cost |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $141,765 |  |  |  |  |  |
|  |  | Overhead |  | 8.50% |  |  |  |  |  |  |  |  |  |  |  |  |  | $12,050 |  |  |  |  |  |
|  |  | Profit |  | 10.00% |  |  |  |  |  |  |  |  |  |  |  |  |  | $14,176 |  |  |  |  |  |
|  |  | Estimated NET Construction Cost |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $167,991 |  |  |  |  |  |
|  |  | Contracting Method Adjustment |  | 15.00% |  |  |  |  |  |  |  |  |  |  |  |  |  | $25,199 |  |  |  |  |  |
|  |  | Inflation Escalation |  | 32 |  | Months |  | Annual Rate = |  | 3.60% |  |  |  |  |  |  |  | $19,107 |  |  |  |  |  |
|  | Total Estimated NET Cost of Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $212,297 |  |  |  |  |  |

GFP costs only apply when the Government pre-purchases items, or provides other materials out of Government inventory, to be installed by contractor. Adjustments and Markup on GFP only include Inflation Escalation; No other adjustment factors or O&P markup have been applied.

BEAR Trailhead - 100% Draft Class A Cost Estimate

Bid Item 3 Summary

Page 32 of 38

Print Date: 1/24/2011, 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: G10 Site Preparation |  |  |  |  |  |  |  |  |  |  | Total Cost: | $16,705 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G1010 | SITE CLEARING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 31.11.10 |  | Misc. Site Clearing | 1 | LS | $ | - | $0 | $ | 2,200.00 | $2,200 | $ | 1,650.00 | $1,650 | $ | 3,850.00 | $3,850 |  |
| 31.13.13 |  | Hand Clear New Trail Alignment | 500 | LF | $ | - | $0 | $ | 6.20 | $3,100 | $ | 1.25 | $625 | $ | 7.45 | $3,725 |  |
| SUBTOTAL | SITE CLEARING | 1 | LS | $ | - | $0 | $ 5,300.00 | $5,300 | $ 2,275.00 | $2,275 | $ | 7,575.00 | $7,575 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G1020 | SITE DEMOLITION & RELOCATIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 02.41.13 |  | Misc. Site Demolition | 1 | LS | $ | - | $0 | $ | 1,270.00 | $1,270 | $ | 485.00 | $485 | $ | 1,755.00 | $1,755 |  |
| 02.41.13 |  | Remove Existing Picnic Tables & Grills | 1 | LS | $ | - | $0 | $ | 2,350.00 | $2,350 | $ | 500.00 | $500 | $ | 2,850.00 | $2,850 |  |
| SUBTOTAL | SITE DEMOLITION & RELOCATIONS | 1 | LS | $ | - | $0 | $ 3,620.00 | $3,620 | $ | 985.00 | $985 | $ 4,605.00 | $4,605 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G1030 | SITE EARTHWORK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 31.22.16 |  | Fine Grade & Compact Picnic subgrades | 3500 | SF | $ | - | $0 | $ | 0.15 | $525 | $ | 0.20 | $700 | $ | 0.35 | $1,225 |  |
| 31.22.16 |  | Hand Grade Trail | 3000 | SF | $ | - | $0 | $ | 0.58 | $1,740 | $ | 0.05 | $150 | $ | 0.63 | $1,890 |  |
| 31.23.23 |  | Scarify & recompact existing dirt parking lot | 10000 | SF | $ | - | $0 | $ | 0.03 | $300 | $ | 0.06 | $600 | $ | 0.09 | $900 |  |
| 31.23.23 |  | Scarify Existing Trail 500' x 3' | 1500 | SF | $ | - | $0 | $ | 0.25 | $375 | $ | 0.09 | $135 | $ | 0.34 | $510 |  |
| SUBTOTAL | SITE EARTHWORK | 1 | LS | $ | - | $0 | $ 2,940.00 | $2,940 | $ 1,585.00 | $1,585 | $ 4,525.00 | $4,525 |  |
| Summary Item: G10 Site Preparation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G10 | Site Preparation | 1 | LS | $ | - | $0 | $ 11,860.00 | $11,860 | $ 4,845.00 | $4,845 | $ 16,705.00 | $16,705 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 3-G10 Site Preparation

33 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: G20 Site Improvements |  |  |  |  |  |  |  |  |  |  | Total Cost: | $97,677 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G2030 | PEDESTRIAN PAVING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 32.06.10 |  | Furnish & Install Decomposed Granite DG | 170 | Tons | $ | 76.75 | $13,048 | $ | 11.50 | $1,955 | $ | 8.35 | $1,420 | $ | 96.60 | $16,422 |  |
|  |  | Mix, spread, finegrade & compact organic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 31.32.13 |  | binder | 6500 | SF | $ | 1.30 | $8,450 | $ | 0.72 | $4,680 | $ | 0.15 | $975 | $ | 2.17 | $14,105 |  |
| 03.30.53 |  | Pedestrian Sidewalks-Trial Connection | 1500 | SF | $ | 5.13 | $7,695 | $ | 3.10 | $4,650 | $ | 0.25 | $375 | $ | 8.48 | $12,720 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | PEDESTRIAN PAVING | 1 | LS | $ | 29,192.50 | $29,193 | $ | 11,285.00 | $11,285 | $ 2,769.50 | $2,770 | $ | 43,247.00 | $43,247 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G2040 | SITE DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 32.31.29 |  | Install new seat resistant single rail fence | 500 | LF | $ | 32.00 | $16,000 | $ | 5.50 | $2,750 | $ | 2.00 | $1,000 | $ | 39.50 | $19,750 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | SITE DEVELOPMENT | 1 | LS | $ | 16,000.00 | $16,000 | $ 2,750.00 | $2,750 | $ 1,000.00 | $1,000 | $ | 19,750.00 | $19,750 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G2050 | LANDSCAPING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 32.90.00 |  | Picnic Area landscape repairs & improvements | 1 | LS | $ | 500.00 | $500 | $ | 1,800.00 | $1,800 | $ | 600.00 | $600 | $ | 2,900.00 | $2,900 |  |
| 32.90.00 |  | Trail landscape repairs & improvements | 1 | LS | $ | 500.00 | $500 | $ | 1,600.00 | $1,600 | $ | 750.00 | $750 | $ | 2,850.00 | $2,850 |  |
| 32.91.13 |  | Soil amenders | 11500 | SF | $ | 0.13 | $1,495 | $ | 0.05 | $575 | $ | 0.10 | $1,150 | $ | 0.28 | $3,220 |  |
| 32.32.60 |  | Place Barrier Rocks | 1 | Allow | $ | - | $0 | $ | 500.00 | $500 | $ | 2,000.00 | $2,000 | $ | 2,500.00 | $2,500 |  |
| 32.93.33 |  | Install native shrubs | 150 | EA | $ | 36.50 | $5,475 | $ | 12.00 | $1,800 | $ | 5.00 | $750 | $ | 53.50 | $8,025 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | LANDSCAPING | 1 | LS | $ 7,970.00 | $7,970 | $ 6,275.00 | $6,275 | $ 5,250.00 | $5,250 | $ | 19,495.00 | $19,495 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item -G20  Site Improvement

34 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: G20 Site Improvements |  |  |  |  |  |  |  |  |  |  | Total Cost: | $97,677 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G2060 | SITE FURNISHINGS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12.93.43 |  | Misc Site Furnishings | 1 | Allow | $ | 1,685.00 | $1,685 | $ | 1,150.00 | $1,150 | $ | 250.00 | $250 | $ | 3,085.00 | $3,085 |  |
| 12.93.43 |  | Reinstall Site Furninshings at Picnic area | 1 | LS | $ | 4,600.00 | $4,600 | $ | 4,500.00 | $4,500 | $ | 3,000.00 | $3,000 | $ | 12,100.00 | $12,100 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | SITE FURNISHINGS | 1 | LS | $ 6,285.00 | $6,285 | $ 5,650.00 | $5,650 | $ 3,250.00 | $3,250 | $ | 15,185.00 | $15,185 |  |
| Summary Item: G20 Site Improvements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| G20 | Site Improvements | 1 | LS | $ 59,447.50 | $59,448 | $ 25,960.00 | $25,960 | $ 12,269.50 | $12,270 | $ 97,677.00 | $97,677 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item -G20  Site Improvement

35 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: | Oso Comida Trailhead Improvements: | Estimate By: | YtB |
| --- | --- | --- | --- |
| Park: | Bear Arbor NRA | Date: | 01/12/11 |
| Park Alpha: | BEAR | Reviewed By: |  |
| PMIS: | XXXXXX | Date: |  |

| Summary Item: G30 Site Mechanical Utilities |  |  |  |  |  |  |  |  |  |  | Total Cost: | $4,730 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |
| Uniformat II WBS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |
|  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |
|  |  |  |  |  |  |  |  |  | Cost |  |  |
| G3030 | STORM SEWER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 33 41 13 | 12 CMP" Trail Crossing Culverts | 60 | LF | $ | 17.35 | $1,041 | $ | 15.77 | $946 | $ | 2.13 | $128 | $ | 35.25 | $2,115 |
| 33 41 13 | 12" Flared End Sections | 12 | EA | $ | 77.80 | $934 | $ | 85.69 | $1,028 | $ | 12.74 | $153 | $ | 176.23 | $2,115 |
|  | Misc Drainage Improvemments | 1 | LS | $ | 150.00 | $150 | $ | 300.00 | $300 | $ | 50.00 | $50 | $ | 500.00 | $500 |
|  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |
|  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |
|  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |
|  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |
|  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |
| SUBTOTAL | STORM SEWER | 1 | LS | $ 2,124.73 | $2,125 | $ 2,274.65 | $2,275 | $ | 330.37 | $330 | $ 4,729.75 | $4,730 |
| Summary Item: G30 Site Mechanical Utilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |
|  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |
|  |  |  |  |  |  |  |  |  | Cost |  |  |
| G30 | Site Mechanical Utilities | 1 | LS | $ 2,124.73 | $2,125 | $ 2,274.65 | $2,275 |  | 330.368 | $330 | $ 4,729.75 | $4,730 |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 3-G30  Site Mechanical

36 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: XX | Bid Item 3 General Conditions |  |  |  |  |  |  |  |  |  |  | Total Cost: | $15,825 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| 01 31 |  | Project Management & Coordination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 31.23.15 |  | Project Superintendent | 2 | Weeks | $ | - | $0 | $ | 2,500.00 | $5,000 | $ | - | $0 | $ | 2,500.00 | $5,000 |  |
| 03.15.05 |  | Project Manager - Half Time | 1 | Weeks | $ | - | $0 | $ | 750.00 | $750 | $ | - | $0 | $ | 750.00 | $750 |  |
| 03.11.13 |  | General Pupose Laborer - Part Time | 1 | Weeks | $ | - | $0 | $ | 1,500.00 | $1,500 | $ | - | $0 | $ | 1,500.00 | $1,500 |  |
| 03.21.10 |  | Builders Risk Insurance | 1 | LS | $ | 200.00 | $200 | $ | - | $0 | $ | - | $0 | $ | 200.00 | $200 |  |
| 03.30.53 |  | General Liabiity Insurance | 1 | LS | $ | 125.00 | $125 | $ | - | $0 | $ | - | $0 | $ | 125.00 | $125 |  |
| 03.11.13 |  | Payment & Performance Bond 1.5% | 1 | Unit | $ | 3,000.00 | $3,000 | $ | - | $0 | $ | - | $0 | $ | 3,000.00 | $3,000 |  |
| 03.35.29 |  | Labor down time due to payroll interviews | 1 | LS | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| 07.27.13 |  | Certified Payroll Costs | 0 | Unit | $ | - | $0 | $ | 25.00 | $0 | $ | - | $0 | $ | 25.00 | $0 |  |
| SUBTOTAL | Project Management & Coordination | 1000 | SF | $ | 3.33 | $3,325 | $ | 7.25 | $7,250 | $ | - | $0 | $ | 10.58 | $10,575 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| 01 45 |  | Quality control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01 45 23 |  | Concrete Testing | 8 | EA | $ | 150.00 | $1,200 | $ | - | $0 | $ | - | $0 | $ | 150.00 | $1,200 |  |
| 01 45 23 |  | Compaction Testing | 10 | EA | $ | 75.00 | $750 | $ | - | $0 | $ | - | $0 | $ | 75.00 | $750 |  |
| 01 45 23 |  | Other Testing | 1 | LS | $ | 500.00 | $500 | $ | - | $0 | $ | - | $0 | $ | 500.00 | $500 |  |
| 01 40 00 |  | Special Inspections | 1 | Allow |  |  | $0 | $ | 300.00 | $300 | $ | - | $0 | $ | 300.00 | $300 |  |
| MF-2004 Code | Description | 0 | Unit | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| MF-2004 Code | Description | 0 | Unit | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| MF-2004 Code | Description | 0 | Unit | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| MF-2004 Code | Description | 0 | Unit | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | Quality control | 1 | LS | $ 2,450.00 | $2,450 | $ | 300.00 | $300 | $ | - | $0 | $ 2,750.00 | $2,750 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 3-General Conditions

37 of 38

1/24/2011 2:13 PM

United States Department of the Interior

National Park Service

Class A Construction Cost Estimate

LINE ITEM COST SUMMARY

| Project: Oso Comida Trailhead Improvements: |  |  |  |  |  |  |  |  |  |  | Estimate By: | YtB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Park: Bear Arbor NRA |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/12/11 |  |
| Park Alpha: BEAR |  |  |  |  |  |  |  |  |  |  | Reviewed By: | BBB |  |
| PMIS: XXXXXX |  |  |  |  |  |  |  |  |  |  |  |  | Date: | 01/17/11 |  |
| Summary Item: XX | Bid Item 3 General Conditions |  |  |  |  |  |  |  |  |  |  | Total Cost: | $15,825 |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| 01 54 36 |  | Mobilizaton |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01 54 36.5 |  | Mobilization | 1 | Allow | $ | - | $0 | $ | - | $0 | $ | 2,500.00 | $2,500 | $ | 2,500.00 | $2,500 |  |
|  |  | Demobilization | 0 | Unit | $ | - | $0 | $ | - | $0 | $ | 1,500.00 | $0 | $ | 1,500.00 | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
|  |  |  |  |  | $ | - | $0 | $ | - | $0 | $ | - | $0 | $ | - | $0 |  |
| SUBTOTAL | Mobilizaton | 1 | LS | $ | - | $0 | $ | - | $0 | $ 2,500.00 | $2,500 | $ 2,500.00 | $2,500 |  |
| Summary Item: XX Bid Item 3 General Conditions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Uniformat II WBS |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT |  | TOTALS |  |
|  | Description | Quantity | Unit |  | Material | Total Material |  | Labor | Total Labor | Equipment | Total |  | Total |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | Total Cost |  |
|  |  |  |  |  | Cost/Unit | Cost | Cost/Unit | Cost | Cost/Unit |  | Cost/Unit |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost |  |  |  |
| XX | Bid Item 3 General Conditions | 1 | LS | $ 5,775.00 | $5,775 | $ 7,550.00 | $7,550 | $ 2,500.00 | $2,500 | $ 15,825.00 | $15,825 |  |

BEAR Trailhead - 100% Draft Class A Cost Estimate, Item 3-General Conditions

38 of 38

1/24/2011 2:13 PM