## Budget
PROJECT BUDGET
Project Name
Program Manager
Project Manager
Purpose: This document with project forecasts should be approved at the Planning Checkpoint. The budget documents the forecasted and actual project costs as the project progresses. The project manager or delegate will assume ownership of the budget for the entire project. Refer to the Budget Guideline for more detail.
The categories should align with the accounting categories for the Project Funding process.
Use the Categories below and delete categories that do not apply. The Total Labor dollar amount should correspond and match the number of labor hours that are documented in the Project Plan. Many formulas are built into the spreadsheet.
See the tab at the bottom of the page for instructions.
Project Categories | Jan | Feb | Mar | Apr | May | Jun | July | Estimate at Completion | Budget | Variance | % Var. | Actual to Date
Capital
Employee Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Applications Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Vendor Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Applications Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Hardware | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Item A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Item B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Software | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Item A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Item B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total Capital | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Expense
Travel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
License | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Requirements Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Applications Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Support Personnel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | 0
Project Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0

## Instructions
Instructions for Simple Budget Preparation
The sample spreadsheet will be used for explanation of instructions.
Field | Description
Project Categories | These categories should line up with the items listed for accounting on the CER Form. Example under Software items A or B, be sure the list Software license cost. Add as appropriate such as a line for Vendors.
Month | List the months of the project in consecutive order. Type the first month, full name or 3 letters and then take the lower right hand corner with a line black cross and drag to fill in. Type actual in per month and distribute the rest of the budget based on work across the appropriate months.
Estimate at Completion | Actual plus forecasted total. Example: F19 would have a formula such as: =sum(C19:E19)
Budget | Planned totals that are allocated across each month based on work.
Variance | Difference of Budget and Total in dollars.
% Variance | Difference of Budget and Total in percent.
Actual to Date | The monies of each month that have been spent to date.

## Example of Budget
Example of a Completed Budget
Project Categories | Oct | Nov Forecasted | Dec Forecasted | Estimate at Completion | Budget | Variance | % Var. | Actual to Date
Labor | 700 | 350 | 300 | 1350 | 1350 | 0 | 0% | 700
Applications Development | 500 | 250 | 250 | 1000 | 1000 | 0 | 0% | 500
Documentation | 200 | 100 | 50 | 350 | 350 | 0 | 0% | 200
Hardware | 90000 | 95000 | 65000 | 250000 | 250000 | 0 | 0% | 90000
Item A - Servers | 75000 | 75000 | 50000 | 200000 | 200000 | 0 | 0% | 75000
Item B - Laptops | 15000 | 20000 | 15000 | 50000 | 50000 | 0 | 0% | 15000
Software | 88500 | 8500 | 8000 | 105000 | 105000 | 0 | 0% | 0
Item A - Software | 87000 | 7000 | 6000 | 100000 | 100000 | 0 | 0% | 0
Item B - License | 1500 | 1500 | 2000 | 5000 | 5000 | 0 | 0% | 0
Total Capital | 179200 | 103850 | 73300 | 356350 | 356350 | 0 | 0% | 179200
Travel | 3000 | 3000 | 3000 | 9000 | 9000 | 0 | 0% | 0
Maintenance | 2000 | 2000 | 4000 | 8000 | 8000 | 0 | 0% | 0
Expense labor | 100 | 100 | 100 | 300 | 300 | 0 | 0% | 0
Support personnel | 200 | 200 | 400 | 800 | 800 | 0 | 0% | 0
Total Expense | 5300 | 5300 | 7500 | 18100 | 18100 | 0 | 0% | 0
Project Total | 184500 | 109150 | 80800 | 374450 | 374450 | 0 | 0% | 184500

## Formula Example
Formula Example
Project Categories | Oct | Nov Forecasted | Dec Forecasted | Estimate at Completion | Budget | Variance | % Var. | Actual to Date
Labor | 700 | 350 | 300 | 1350 | 1350 | 0 | 0% | 700
Applications Development | 500 | 250 | 250 | 1000 | 1000 | 0 | 0% | 500
Documentation | 200 | 100 | 50 | 350 | 350 | 0 | 0% | 200
Hardware | 90000 | 95000 | 65000 | 250000 | 250000 | 0 | 0% | 90000
Item A - Servers | 75000 | 75000 | 50000 | 200000 | 200000 | 0 | 0% | 75000
Item B - Laptops | 15000 | 20000 | 15000 | 50000 | 50000 | 0 | 0% | 15000
Software | 88500 | 8500 | 8000 | 105000 | 105000 | 0 | 0% | 88500
Item A - Software | 87000 | 7000 | 6000 | 100000 | 100000 | 0 | 0% | 87000
Item B - License | 1500 | 1500 | 2000 | 5000 | 5000 | 0 | 0% | 1500
Total Capital | 179200 | 103850 | 73300 | 356350 | 356350 | 0 | 0% | 179200
Travel | 3000 | 3000 | 3000 | 9000 | 9000 | 0 | 0% | 3000
Maintenance | 2000 | 2000 | 4000 | 8000 | 8000 | 0 | 0% | 2000
Expense labor | 100 | 100 | 100 | 300 | 300 | 0 | 0% | 100
Support personnel | 200 | 200 | 400 | 800 | 800 | 0 | 0% | 200
Total Expense | 5300 | 5300 | 7500 | 18100 | 18100 | 0 | 0% | 5300
Project Total | 184500 | 109150 | 80800 | 374450 | 374450 | 0 | 0% | 184500

## Estimating Worksheet
ESTIMATING SHEET
Purpose: This is to assist with calculations and information prior to documenting on the Budget. If this worksheet is not needed do not use it.
Labor
Project Categories | # of Resources | % of Effort | Duration (in days or hours) | Resource Cost (Option 1) | Resource Cost (Option 2) | Total Resource (Option 1) | Total Resource (Option 2) | Assumptions/ Constraints | Total (Resources) | Funding Source
Capital
Employee Labor
Applications Development |  |  |  | 0 | 0
Name |  | 0%
Name |  | 0%
Documentation |  |  |  | 0 | 0
Name
Name
Testing |  |  |  | 0 | 0
Name |  | 0% |  | 0 | 0
Name |  | 0% |  | 0 | 0
Vendor Labor
Applications Development |  | 0% |  | 0 | 0
Name |  | 0%
Other |  | 0% |  | 0 | 0
Total Capital
Items
Project Categories | # of Units | Unit Cost | Duration (if applicable) | Assumptions/ Constraints | Total (Units) | Funding Source
Hardware
Item A |  | 0
Item B |  | 0
Software
Item A |  | 0
Item B |  | 0
Total Capital |  | 0
Expense
Project Categories | # of Units | Unit Cost | # of Locations (if applicable) | Duration (if applicable) | Assumptions/ Constraints | Total (Units) | Funding Source
Travel |  | 0
License |  | 0
Labor |  | 0
Requirements Development |  | 0
Applications Development |  | 0
Support Personnel |  | 0
Total Expense |  | 0