## Project Plan
Persona Project Plan Template |  |  | Project Manager: John Doe |  |  |  | Portfolio Marketer: Jane Doe
Incremental
Component | Owner | Contributor(s) | Approver(s) | Weeks | Start Date | Finish Date | Budget | Status
Scope Definition |  |  |  | Est. 4 weeks
Define Persona Project Goals | [7 empty] | Not Started
Prioritize Target Personas (include Firmagraphics) | [7 empty] | Planning
Define Research Plan Requirements | [7 empty] | In Process
Define In-house Staff Requirements | [7 empty] | Completed
Deifine Vendor Requirements
Defne Timing and Budget Requirements
Gain Sales, Marketing, and Product Approvals
Gain Executive Approval
Vendor Selection |  |  |  | Est. 4-6 weeks
Define vendor selection criteria
Develop vendor selection RFP
Develop Statement of Work
Evaluate proposal
Select vendor
Research Design |  |  |  | 4 weeks
Identify Information (Attributes) To Be Gathered in Research
Identify Secondary Research Methods (e.g., internal, 3rd party publications)
Identify Primary Research Methods (e.g., phone, in-person, survey)
Create Interview Guide
Identify Research Participants
Create Research Plan (including timing and budget)
Gain Research Plan Approval
Conduct Research |  |  |  | Est. 5-8 weeks
Document Findings from Primary Research
Document Findings from Secondary Research
Define and Validate Personas |  |  |  | Est. 4 weeks
Identify Cross-Functional Team for Data Analysis
Team Working Session(s) to Consolodiate and Mine Findings
Construct Individual Personas
Vet Persona Definitions with Sales, Marketing, and Product Leaders
Test Persona Definitions with Customers
Final Approval |  |  |  | Est. 2 weeks
Present Final Personas for Executive Approval
Develop a Plan for Persona Deployment

## Status
Not Started
Planning
In Process
Completed