## Project plan 2019
Project Plan Template | [16 empty] | Last updated: |  |  | 2019-06-12
Team involved
| Process | IT | Vendor | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec
calendar week |  |  |  | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
national holidays
parallel project 1 | bar: Feb 7 to Jun 24
CONCEPT PHASE
Project Kick-off | X | X | X | bar: Jan 3 to Jan 4
Process workshops | X | bar: Jan 3 to Jan 5
Requirement specification | X | bar: Jan 5 to Feb 6
Workshops with vendors | X | X | X | bar: Feb 7
Vendor evaluation | X | X | X | bar: Feb 6 to Feb 7
Technical concept |  | X | X | bar: Feb 8 to Feb 9
Project status meeting | X | X | X | bar: Mar 10
IMPLEMENTATION PHASE
Kick-off implementation phase | X | X | X | bar: Mar 11
Software implementation |  | X | X | bar: Mar 11 to Apr 14
Connection with vendor platform |  | X | X | bar: Apr 14
Pre-test |  | X | X | bar: Apr 15
Migration of test data |  | X | bar: Apr 15 to Apr 16
Functional test | X | X | X | bar: Apr 17 to May 18
Integration test | X | X | X | bar: May 19 to May 21
Re-test of open issues | X | X | X | bar: May 22
Create user documentation | X | bar: May 18 to May 22
Project status meeting | X | X | X | bar: Jun 23
CLOSING PHASE
Kick-off closing phase | X | X | X | bar: Jun 24
End-user training | X | bar: May 22 to Jun 24
Data migration |  | X | bar: Jun 24
Perform changes in live system |  | X | bar: Jun 24 to Jun 25
Go-Live | X | X | X | bar: Jun 25
Go-Live support | X | X | X | bar: Jun 25 to Jul 30
Project status meeting | X | X | X | bar: Jul 30