|  | NHS WLCCG |  | PROJECT PLAN TEMPLATE |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Primary Medical Care Workplan | Month |  |  | Apr-15 | May-15 | Jun-15 | Jul-15 | Aug-15 | Sep-15 | Oct-15 | Nov-15 | Dec-15 | Jan-16 | Feb-16 | Mar-16 |  |
|  |  | (a) Excellent Primary Medical Care |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | (b) Supporting the Capacity and Capability of Primary Medical Care |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Primary Care Commissioning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Committee Meeting Dates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Federated Localities Making General Practice Thrive | Expected Outcome(s) on Completion | Comments only where task / | Leads |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | project NOT on track |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1 | By April 2015 have an agreed plan in place to support the |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | development of federations. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1 | Formal process to to review federation submissions agreed and completed. | Approved federations receive funding. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.2 | Contract agreed and signed | Contract issued |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.3 | Concordat outlining how CCG will work with Federations developed and | Signed Concordat with 4 federations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | agreed. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.4 | By June 2015 establish process for regular engagement, discussion and | Robust process in place to engage and review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | progress monitoring with all WLCCG federations | delivery with federations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.5 | By September 2015 federations to develop and agree business plan and | Business plans in place and used to inform |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | business case setting out objectives including improving efficiency and | CCG Commissioning Plans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | effectiveness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Better Collaboration and Reducing Bureaucracy | Expected Outcome(s) on Completion | Comments only where task / | Leads |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | project NOT on track |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.1 | By April 2015 CCG to agree a QIPP programme on a federated locality level | 2015/16 QIPP scheme approved by CCG and |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | delivered at federated locality level. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.2 | Contract agreed and signed by CCG and Federations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.3 | Quarterly contract meetings set up commencing June 2015 to review | Quarterly contact meetings established |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | performance and implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.4 | Establish process to reduce bureaucracy and improve quality of community | Revised process in place Q1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | based services monitoring process |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Co Commissioning of Primary Medical Care | Expected Outcome(s) on Completion | Comments only where task / | Leads |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | project NOT on track |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.1 | Governance Arrangements established and Primary Care |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Commissioning Team in place to support CCG to discharge |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | delegated fucnctions. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.1 | Primary Care Commissioning Committee established and operational by April | PCCC established and safely discharging |  | AB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 2015 | delegated functions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.2 | Effective mechanism in place to support commissioning of Direct Enhanced | Process established to commission and |  | IP/RB/JEC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Services. | monitor services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.3 | Effective mechanism in place to support commissioning of Community Based | Process established to commission and |  | IP/RB/JEC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Services. | monitor services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4 | Action plan agreed to review and procure existing community based services | Agreed plan in place to support |  | IP/RB/JEC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | commissioning of CBS services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.5 | Process established to support commissioning of Public Health DESs | Process established to commission and |  | IP/RB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | monitor services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.6 | Process established to support rollout of QOF | All practices deliver QOF |  | RB/KB/JEC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Process established to support management of CQRS | Agreed process to ensure effective |  | RB/KB/JEC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | management of CQRS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Review and agree process to monitor GP contracts inline with national | Effective process in place to monitor GP |  | RB/KB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.7 | guidance, including engagement with practices to ensure completion of self | contract supporting the delivery of high quality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | declaration | patient care, reviewed quarterly |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Establish process to ensure timely undertaking of contractual requirements and | Process established and in place |  | RB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | changes, nationally and locally, including the issue of regulatory amendments, |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | contract variations, partnership changes, management of splits and mergers, |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | list closures and boundary changes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Establish robust procurement and care taking protocols pertinent to general | Protocol agreed and in place |  | RB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | practice, including patient and stakeholder engagement and impact |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | assessments, in line with national and local process |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Review and update triangulation process between CCG and NHS England (to | Triangulation process revised and in place |  | RB/KB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | include E-Dec, GPOS, NHS Choices, Appraisal, Risk Sharing, Complaints and |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | local knowledge) to support escalation of issues and concerns in primary care |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Review general practice core opening hours across all 49 practices within the |  |  | RB/KB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | CCG, including protocols in place for afternoon and lunchtime closures, bank |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | holidays, Christmas and Easter opening hours |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Undertake comprehensive PMS Review exercise and determine reinvestment |  |  | IP/RB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | of funding as a result of the review for 2016/17 and subsequent financial years |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | up to 2020/21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 18/12/2015 |  |  | Paper D - Excellence in PMC - July |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Status: Please | Actions are on |
| --- | --- |
|  | target |
| select when |  |
| complete or |  |
|  | Delay of more than |
| Time extended |  |
|  | 30 days |
|  | Project Plan |
|  | Milestones |

Actions are on

target

Project Plan

Milestones

Actions are on

target

Project Plan

Milestones

1/3

|  | NHS WLCCG |  | PROJECT PLAN TEMPLATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Primary Medical Care Workplan | Month |  | Apr-15 | May-15 | Jun-15 | Jul-15 | Aug-15 | Sep-15 | Oct-15 | Nov-15 | Dec-15 | Jan-16 | Feb-16 | Mar-16 | Status: Please | Actions are on |  |  |
|  |  | (a) Excellent Primary Medical Care |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | target |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | select when |  |  |  |
|  |  | (b) Supporting the Capacity and Capability of Primary Medical Care |  |  |  |  |  |  |  |  |  |  |  |  |  |  | complete or |  |  |  |
|  |  |  | Primary Care Commissioning |  |  |  |  |  |  |  |  |  |  |  |  |  | Delay of more than |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Time extended |  |  |  |
|  |  |  |  | Committee Meeting Dates |  |  |  |  |  |  |  |  |  |  |  |  |  | 30 days |  |  |
|  | 3.8 | Review commissioning arrangements for Occupational health services, | Process established to commission and |  | TBC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | language line interpretation services and clinical waste. | monitor services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.9 | By March 2016 undertake practice appraisals with all 49 practices in WLCCG. | 49 appraisals undertaken |  | IP/RB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4 | Premises |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | By August 2015 complete a primary care premises audit to inform the | Audit completed and premises strategy |  | IP/RB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.1 | development of federated locality based premises strategy | developed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.2 | Support practices to apply for Primary Care Infrastructure Fund, and determine | National funding secured to support local |  | IP/RB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | funds available to practices | premises developments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Review impact of PCIF upon practice notional rent to ensure that any increase | Notional rent implications established and |  | RB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.3 | to current financial envelope is affordable and within CCG resources | CCG funding apportioned appropriately |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Establish clear links with NHS England to ensure that practices are supported to | Practices supported to access S106 funds as |  | RB/KB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | access Section 106 monies as relevant during 2015/16 and onwards; ensuring | appropriate and within locally set timescales; |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | smooth transition of this workstream in to the CCG's remit once agreed | handover of S106 function to CCG agreed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5 | Helping practices to be attractive places to work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5.1 | By August 2015, complete and analyse WLCCG work force audit. | Audit completed by 90% of WLCCG practices |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5.2 | Work the LLR General Practice Delivery Group to develop a training needs | TNA agreed and funding secured to deliver |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | assessment based on audit results | programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6 | Exploiting Technology |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | By August establish the number of practices choosing to move from existing | 10 practices moved clinical system. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6.1 | clinical system to S1 and agreed implementation programme to transfer 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | practices by March 2016. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6.2 | Support the further development and implementation of PRISM for member | Greater use of PRISM and adherance to |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | practices increasing adherence to planned care pathways | planned car pathways |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 7 | Listening to increasing the participation of patients |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | By March 2016, federations to develop a locality based communication and | Robust engagement plan in place. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 7.1 | engagement plan, including the identification and training of community |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | champions. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 7.2 | By September 2015, agree a prevention plan with partners covering major areas | Plan agreed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | of health and social inequalities. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 8 | Improving Quality and Patient outcomes through integrated |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | working. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | By September 2015, in partnership with key stakeholders identify and agree | Services identified for provision closer to |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 8.1 | opportunities at a locality level to develop out of hospital services to provide | home |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | care closer to home. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 8.2 | By March 2016, develop an integrated approach to patient care at a locality/ | New model of care agreed by March 2016 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | virtual ward level. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6 | ADD MEDS Management | Expected Outcome(s) on Completion | Comments only where task / | Leads |  |  |  |  |  |  |  |  |  |  |  |  |  | Project Plan |  |  |
|  |  |  |  | project NOT on track |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Milestones |  |  |
|  | 6.1 | Organise a PLT for GPs by end of September 2015 | 100% uptake by GPs for PLT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Good -excellent rating |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6.2 | Achievement of QIPP target £1.1 million by end March 2016 | QIPP realised |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6.3 | Sign up of 80% practices to Prescribing Incentive Scheme June 2015, | 80% target achieved, impact monitored via |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | completion of phase 1 audit by October 2015 and phase 2 audit by March | audit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Acheivement of Quality Premium Targets around antimicrobial prescribing by | National targets achieved: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | end March 2016 | Reduction in antibiotic prescribing by 1% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Reduction in the proportion of broad spectum |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6.4 |  | antibiotics by 10% from 2013-2014 baseline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | or stay below the NHS benchmark |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6.4 | Evaluation of pharmacist intervention on PINCER patient safety tool | Evaluation completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6.5 | Evaluation of a community based Gluten Free service | Evaluation completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6.6 | Full evaluation of GP prescribing software or refresh of existing software | Evaluation completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6.7 | Review of LLR PGDs required for the urgent care centre and AVS service | All PGDs reviewed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6.8 | Evaluation of pharmacist intervention on wastage incurred as a result of repeat | Evaluation completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | prescribing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 18/12/2015 |  |  | Paper D - Excellence in PMC - July |  |  |  |  |  |  |  |  |  |  |  |  |  | 2/3 |

| NHS WLCCG | PROJECT PLAN TEMPLATE |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Primary Medical Care Workplan | Month | Apr-15 | May-15 | Jun-15 | Jul-15 | Aug-15 | Sep-15 | Oct-15 | Nov-15 | Dec-15 | Jan-16 | Feb-16 | Mar-16 | Status: Please | Actions are on |
|  | (a) Excellent Primary Medical Care |  |  |  |  |  |  |  |  |  |  |  |  |  |  | target |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | select when |  |
|  | (b) Supporting the Capacity and Capability of Primary Medical Care |  |  |  |  |  |  |  |  |  |  |  |  |  |  | complete or |  |
|  |  | Primary Care Commissioning |  |  |  |  |  |  |  |  |  |  |  |  |  | Delay of more than |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Time extended |  |
|  |  |  | Committee Meeting Dates |  |  |  |  |  |  |  |  |  |  |  |  |  | 30 days |

18/12/2015	Paper D - Excellence in PMC - July	3/3