## 1.1
To-do list | [7 empty] | In progress
Done
Work package 1 Preparation |  | Lead RUB University | [5 empty] | N/A
Deadline: |  | 30.03.2019 (proposed 30.05.2019)
Deliverable 1.1. Assesment and analysis of R&D&I potential of alliances among universitites and companies in Bosnia and Hercegovina and Armenia Status at May 15, 2019
Phase | Task | Due By | Who | Outputs | Indicators | Status | Comments
Preparation | Development of guidelines for the assessment, data collection and analysis | 2019-01-10 | IECE; peer review by UKIM | Guidelines | Document with guidelines | N/A
Preparation | Drafting questionnaire to assess the collaboration between universities and industry | 2019-01-15 | IECE; peer review by UKIM | Draft questionnaires | Document | N/A
Document - output | Final version of the questionnaire | 2019-01-25 | IECE; peer review by UKIM | Questionnaire | Document | N/A
Communication | Distribution of the questionnaire to all partners | 2019-01-25 | UKIM | Communication via mail | Google Form | N/A
Document - output | Translation of the questionnaire in Macedonian, Bosnian and Armenian | 2019-02-05 | Partner countries partners | Document | 2 version of questionnaires - Bosnian and Armenian | N/A
Document - output | Creating on-line survey questionnaire | 2019-02-07 | UKIM | On-line survey | 3 versions of the on-line survey (English, Bosnian and Armenian) | N/A
Document - output | Creating list of relevant stakeholders to whom the questionnaire will be sent (each partner their own list) | 2019-02-10 | all partners | Template excel file | 13 excel files from each partner | N/A
Communication | Sending questionnaires to relevant stakeholders | 2019-03-20 | all partners | Communication via mail | Mail messages | N/A
Preparation | Drafting concept for the report of the analysis | 2019-02-25 | RUB & UKIM | Template document | Document | N/A
Document - output | Creating raw data table and graphic results from the responses | 2019-03-20 | UKIM; with contribution from all partners | Raw data table | Excel table | N/A
Preparation | Creating the analysis report - comparison of the current situation in B&H, Armenia and other European countries. Recommendations for strengthening the collaboration | 2019-05-10 | RUB, UKIM | Report document | Report done | N/A
Preparation | Collecting good practices of university-industry collaboration from all European partners - guidelines for the case studies | 2019-03-20 | Universities and institutes from Program Countries | Draft content template presentation | Presentation send to all Program countries partners | N/A
Document - output | Creating report on good practices of university-industry collaboration | 2019-05-15 | UKIM & IECE | Draft content | Compilation of all presentation on good practices | N/A
Preparation | Preparation of two national events in B&H and Armenia - agenda, presentations, administrative issues, speakers, etc. | 2019-02-25 | Partner countries parnters | National event | National event - draft agenda, questionnaire from QA | N/A
Promotion | Two national events in B&H and Armenia - implementation and reporting | 2019-03-15 | Partner countries partners | National event | National event - agenda, list of participants, photos, minutes, answers from questionnaires from QA | N/A
Promotion | Promoting the results from WP1 through different communications channels | 2019-05-15 | all partners | Dromotional materials, press releases | Number of press releasess | N/A
Reporting | Drafting report for WP1 | 2019-03-10 | UKIM &RUB | Template of content of the report | Draft document | N/A
Reporting | Final report for WP1 | 2019-05-30 | UKIM &RUB with contribution from all partners | Report document | Report done | N/A

## 1.2
To-do list | [7 empty] | In progress
Done
Work package 1 Preparation |  | Lead RUB University | [5 empty] | N/A
Deadline: |  | 2019-03-30
Deliverable 1.2. Kick-off seminar and project team building Status at May 15, 2019
Phase | Task | Due By | Who | Outputs | Indicators | Status | Comments
Preparation | Logistic arrangements for the Kick-off seminar (venue, travel, accommodation, etc.) | 2019-01-15 | UKIM | Communication with all partners; table with contact information from all partners coming to the Kick-off seminar; Guide for travel info and useful information. | e-mails, telephone calls, excel file, document Guide for travel | N/A
Document | Preparation of agenda for the Kick-off seminar | 2019-01-15 | UKIM; IECE | Draft agenda, peer review; final agenda | Document Agenda | N/A
Document | Gathering data and preparing presentations on good practices | 2019-01-20 | UKIM; all partners | Template presentation, presentations from all partners | Presentations | N/A
Report | Moderation of the Kick-off seminar | 2019-01-25 | UKIM/IECE | Minutes from the Kick-Off seminar; moderating the communicating; coordination among all partners, efficient time management, lead by UKIM | Report | N/A
Communication | Input for the further development of the concept of Development work packages | 2019-01-25 | All partners | Overview of the project activities and partners role | Presentation | N/A
| Input for further activities in Quality plan, Dissemination and Management | 2019-01-25 | UKIM and WUS | Concepts of Quality plan, Dissemination and Management of the project | Presentation | N/A
Document | Project team building and reconfirmation of division of roles and responsibilities | 2019-02-05 | All partners, lead by UKIM | Template for each WP | Excel file completed | N/A
Document | Signing of partnership agreements | 2019-01-25 | All partners | Project agreements | Agreements signed | N/A
Report | Minutes and reporting detailed scheduling of project activities | 2019-02-05 | All partners, lead by UKIM | Agreed date for next events, workshops and project meetings, deadline for each WP and activities | Minutes | N/A