## To-do list
To-do list: ABET Self-Study Preparations (2013-14)
2013-08-07
Department: |  | College of Engineering Skeleton Template
Completed by: |  | Darrell Hoy, Asst. Dean for Assessments & Extended Programs, CoE
Summer 2013: Pre-Self-Study Activities
% done | Phase | Due By | Notes
100% | ABET Review sessions: J. Matson | 2013-08-15 | 6 sessions covering ABET Criteria 1-9 and Program Criteria
75% | Make-up up missed review sessions | 2013-08-21 | Videos & PPTs avaialble on CAE Server, "ABET" share
60% | CoE/Dept websites | 2013-08-31 | Create a common top-level ABET webpage template for all Depts in the CoE; have Public Affairs implement it
10% | ABET Leads/Dept Chairs review ABET Self-Study Criteria and Documents (www.ABET.org) | 2013-08-31 | 1. Criteria for Engineering Programs 2. Accreditation Policy & Procedures Manual 3. SElf-Study Questionnaire: Template for the Self-Study Report
0% | ABET Leads/Dept Chairs review the gneral state of their departmental assessment and improvement process since the last ABET visit | 2013-08-31 | 1. Mission/Vision statement 2. Program Objectives and Learning Outcomes 3. Assessment Tools and Data 4. Actions Taken for Imrpovement
0% | ABET Dept Leads create a planning schedule for their dept from the CoE common schedule | 2013-08-31 | Strongly Suggested
10% | Dept Chairs provide list of UG labs and facilities to Assit Dean | 2013-09-10 | Provide list to Asst. Dean to coordinate the safety inspection and personnel training of all CoE UG lab facilities through the TTU Safety Office
Fall 2013: Start Preparation of Self-Study
% done | Phase | Due By | Notes
0% | Departmental ABET "kick-off" meetings with their faculty & staff | 2013-09-06 | Suggested topics: 1. Overview of this year's ABET Self-Study process and the importance of faculty involvment and external review of projects; foucs on Criteria 2-5 2. Discuss course material collection by faculty and the importance of demonstrating course outcomes and their linkage to program learning objectives 3. Importanc of Capstone Design couses to the ABET process 4. Updating ABET course syllabi requirements 5. Documentation of all program improvement activities (faculty advisory board minutes, interviews with students, external individuals, etc)
0% | Meeting - - ABET Leads Group/Dept Chairs | 2013-09-10 | Laboratory and shop safety inspections and training
0% | Departments review and re-approve their Mission/Vision statements and ABET Objectives and Outcomes | 2013-09-24 | To be presented to the ABET Dept Leads group at its second meeting
0% | Meeting - - ABET Leads Group/Dept Chairs | 2013-09-24 | Presentation by each Dept of its Mission/Vision/Program Objectives/Program Outcomes/Course Outcomes to Learning Outcomes Linkages
0% | Departmental task(s)
0% | Meeting - - ABET Leads Group/Dept Chairs | 2013-10-08 | Data collection needs of departments discusseed
0% | Departmental task(s)
0% | Meeting - - ABET Leads Group/Dept Chairs | 2013-10-22
0% | Departmental task(s)
0% | Meeting - - ABET Leads Group/Dept Chairs | 2013-11-05
0% | Departmental task(s)
0% | Meeting - - ABET Leads Group/Dept Chairs | 2013-11-19
0% | Departmental task(s)
0% | Meeting - - ABET Leads Group/Dept Chairs | 2013-12-03
0% | Departmental task(s)
0% | Meeting - - ABET Leads Group/Dept Chairs | 2013-12-17
0% | Departmental task(s)
0% | Meeting - - ABET Leads Group/Dept Chairs | 2013-10-22
0% | Request for Evalaution from Institution | 2014-01-31 | Due to ABET along with fee
Spring 2014: Continue Preparation of Self-Study
% done | Phase | Due By | Notes
0% | Departmental task(s)
0% | Meeting - - ABET Leads Group/Dept Chairs | 2014-01-14
0% | Departmental task(s)
0% | Meeting - - ABET Leads Group/Dept Chairs | 2014-01-28
0% | Departmental task(s)
0% | Meeting - - ABET Leads Group/Dept Chairs | 2014-02-11
0% | Discuss ABET Faculty Resume requirements | 2013-02-15 | Faculty should update their resumes as they prepare for the Annual Evalautions
0% | Departmental task(s)
0% | Meeting - - ABET Leads Group/Dept Chairs | 2014-02-25
0% | Departmental task(s)
0% | Meeting - - ABET Leads Group/Dept Chairs | 2014-03-11
0% | Departmental task(s)
0% | Meeting - - ABET Leads Group/Dept Chairs | 2014-03-25
0% | Departmental task(s)
0% | Meeting - - ABET Leads Group/Dept Chairs | 2014-04-08
0% | Departmental task(s)
0% | Meeting - - ABET Leads Group/Dept Chairs | 2014-04-22
0% | First Draft of ABET Self-Sudy Due to CoE | 2014-05-01
0% | Meeting - - ABET Leads Group/Dept Chairs | 2014-05-06
0% | Departmental task(s)
Summer 2014: Self-Study Report Due
% done | Phase | Due By | Notes
0% | Meeting - - ABET Leads Group/Dept Chairs | 2014-05-20
0% | Second Draft of ABET Self-Study Due to CoE | 2014-06-01
0% | Meeting - - ABET Leads Group/Dept Chairs | 2014-06-03
0% | Departmental task(s)
0% | Meeting - - ABET Leads Group/Dept Chairs | 2014-06-17
0% | Departmental task(s)
0% | Meeting - - ABET Leads Group/Dept Chairs | 2014-07-01
0% | Final Version of Departmental Self-Study Due to College | 2014-07-01
0% | College Sends Final Self-Study to ABET | 2014-07-15
0% | ABET Deadline for Self-Study Reports | 2014-07-31
0% | All UG lab and facility inspections completed | 2014-08-15
Fall, 2014: ABET Team Visit
% done | Phase | Due By | Notes
0% | Departmental task(s)
0% | Departmental task(s)
0% | Departmental task(s)
0% | Departmental task(s)