## Closeout Plan
PROJECT PUNCH LIST
PROJECT TITLE |  |  | SUBSTANTIAL COMPLETION |  |  | XX/XX/20XX
11-XXXX-000 |  |  | CLOSEOUT TARGET |  |  | #VALUE!
1.0 | ADMINISTRATION
1.1 | Team Focus
| Task |  |  | Responsible | Status | Target | Actual
Enter Tasks pertinent to project | Task 1.1.1 | Project management commits to managing closeout process and helping team personnel in execution of closeout plan. |  | Enter Initials | Pending/In Progress/ Complete/Etc. | Enter Date Here | Enter Date Here
Task 1.1.2
Task 1.1.3
Task 1.1.4
1.2 | Closeout Plan
| Task |  |  | Responsible | Status | Target | Actual
| Task 1.2.1 | Team drafts Closeout Plan.
| Task 1.2.2 | Team updates Closeout Plan regularly (minimum of weekly) Submit to PX monthly.
1.3 | Closeout Manual
| Task |  |  | Responsible | Status | Target | Actual
| Task 1.3.1 | Team sets up Closeout Manual base.
| Task 1.3.2 | Review Closeout Manual structure with Owner.
| Task 1.3.3 | Team updates Closeout Manual with Items as they come in.
| Task 1.3.4 | Team regularly (weekly) transmits list of outstanding items to Trade Contractors.
| Task 1.3.5 | Transmit Closeout Manual to Owner. Have Owner sign transmittal indicating receipt.
1.4 | Trade Contractor Closeout Matrix
| Task |  |  | Responsible | Status | Target | Actual
| Task 1.4.1 | Team sets up Trade Contractor Closeout Matrix.
| Task 1.4.2 | Team makes the Trade Contractor Closeout Matrix available electronically or posted in the project trailer.
| Task 1.4.3 | Team updates Trade Contractor Closeout Matrix with Items as they come in.
1.5 | Client Satisfaction
| Task |  |  | Responsible | Status | Target | Actual
| Task 1.5.1 | Set up Client Survey schedule for entire project.
| Task 1.5.2 | Secure 100% A/E and Owner Client Surveys.
1.6 | Gilbane Internal Reports
| Task |  |  | Responsible | Status | Target | Actual
| Task 1.6.1 | Prepare Final Project Completion Report base.
| Task 1.6.2 | Transmit Final Project Completion Report to appropriate Gilbane personnel.
1.7 | Lessons Learned
| Task |  |  | Responsible | Status | Target | Actual
| Task 1.7.1 | Team creates internal system for capturing lessons learned throughout project.
| Task 1.7.2 | Team enters lessons learned into LL Database periodically.
| Task 1.7.3 | Schedule a Lessons Learned session with Regional Quality Manager.
| Task 1.7.4 | Transmit Lessons Learned session notes to Regional Quality Manager and enter items into LL Database.
1.8 | Document / Information Retention
| Task |  |  | Responsible | Status | Target | Actual
| Task 1.8.1 | Determine document retention requirements for project.
| Task 1.8.2 | Determine electronic file backup plan for project.
| Task 1.8.3 | Determine correspondence backup plan. Use scanned documents if possible.
| Task 1.8.4 | Burn CDs of project electronic files.
| Task 1.8.5 | Obtain CD of Prolog database from IS Department if applicable.
1.9 | Special Contract Terms
| Task |  |  | Responsible | Status | Target | Actual
| Task 1.9.1 | Project team identifies special contract terms for closeout.
| Task 1.9.2 | Determine Architect's signing requirements for closeout items.
| Task 1.9.3 | Special contract term #1.
| Task 1.9.4 | Special contract term #2.
| Task 1.9.5 | Special contract term #3.
1.10 | Last Man Out Final Tasks
| Task |  |  | Responsible | Status | Target | Actual
| Task 1.10.1 | Send all documents to be retained to Iron Mountain.
| Task 1.10.2 | Transmit Iron Mountain box content itemization to Providence.
| Task 1.10.3 | Notify region and corporate of demobilization.
| Task 1.10.4 | Terminate temporary construction services and facilities.
| Task 1.10.5 | Terminate trailer and services.
| Task 1.10.6 | Close Post Office box and have mail transferred.
| Task 1.10.7 | Reconcile Petty Cash and closeout.
Task 1.10.8
Task 1.10.9
2.0 | FIELD
2.1 | Rolling Completion List
| Task |  |  | Responsible | Status | Target | Actual
| Task 2.1.1 | Team commits to entering all quality deficiencies into Rolling Completion List module in Prolog/iBuild.
| Task 2.1.2 | Team customizes specific Prolog reports to aid in RCL execution.
| Task 2.1.3 | Discuss with Owner who has sign-off authority during RCL phase. [Standard is whomever authored the item.]
| Task 2.1.4 | Team notifies or distributes RCL to Trade Contractors daily/weekly with the expectation that all of the items will be reworked by the next week.
| Task 2.1.5 | Periodically review RCL and make calls to PMs of non-performing Trade Contractors.
2.2 | Punchlist
| Task |  |  | Responsible | Status | Target | Actual
| Task 2.2.1 | Define with Owner the Punchlisting procedure for the project.
| Task 2.2.2 | Define with Owner who has sign-off authority for all punchlist items, including rolled over RCL items.
| Task 2.2.3 | Convert RCL items to Punchlist items in iBuild, if applicable.
| Task 2.2.4 | Prepare Punchlisting schedule for entire project, breaking the facility into manageable pieces. Include a schedule for whomever has sign-off authority to be available to walk completed items.
| Task 2.2.5 | Discuss updated punchlisting schedule with the A/E and Owner at each Owner/Designer/Gilbane meeting.
| Task 2.2.6 | Team distributes Punchlist to Trade Contractors frequently, indicating that it is preliminary until the final area is punched.
| Task 2.2.7 | PM weekly reviews Punchlist with Superintendent and makes calls to PMs of non-performing Trade Contractors.
| Task 2.2.8 | Transmit completed Punchlist to Owner. Have Owner sign transmittal indicating receipt.
2.3 | Building Acceptance
| Task |  |  | Responsible | Status | Target | Actual
| Task 2.3.1 | Determine from the Contract the terms and requirements of building acceptance.
| Task 2.3.2 | Ensure that the building acceptance requirements are in the project schedule.
| Task 2.3.3 | Review the building acceptance requirements with the Owner.
| Task 2.3.4 | Create a Certificate of Substantial Completion draft.
| Task 2.3.5 | Review the Certificate of Substantial Completion draft with the Owner and decide upon a final form.
| Task 2.3.6 | Determine the A/E's responsibility for signing the Certificate of Substantial Completion.
| Task 2.3.7 | Obtain a signed Certificate of Substantial Completion from the Owner for all areas of the project.
2.4 | Certificate of Occupancy
| Task |  |  | Responsible | Status | Target | Actual
| Task 2.4.1 | Determine from the Contract the terms and requirements regarding the Certificate of Occupancy.
| Task 2.4.2 | Determine from the Governing Authorities the requirements for a Certificate of Occupancy, and any temporary ToCs, if needed.
| Task 2.4.3 | Set up a schedule of reoccurring, regular meetings with the Governing Authorities to review their concerns and the progress of project.
| Task 2.4.4 | Set up an easy and accessible tracking system for Governing Authority interim sign-offs (by floor, building, area, etc.).
| Task 2.4.5 | Ensure that the building acceptance requirements are in the project schedule.
| Task 2.4.6 | Obtain the Certificate of Occupancy for the facility.
2.5 | Special Certificates + Inspections
| Task |  |  | Responsible | Status | Target | Actual
| Task 2.5.1 | Determine from the Contract and project Contract Documents any special certificates and/or inspections required.
| Task 2.5.2 | Determine from the Governing Authorities any special certificates and/or inspections required.
Task 2.5.3
Task 2.5.4
2.6 | Commissioning / Validation
| Task |  |  | Responsible | Status | Target | Actual
| Task 2.6.1 | Determine from the Contract, Gilbane's responsibilities regarding Testing & Balancing, Commissioning, and/or Validation.
Task 2.6.2
Task 2.6.3
Task 2.6.4
3.0 | ACCOUNTING
3.1 | Trade Contractors
| Task |  |  | Responsible | Status | Target | Actual
| Task 3.1.1 | Determine any special accounting requirements from the Owner contract.
| Task 3.1.2 | Create Closeout Package for Trade Contractors. Include Engineering items if desired.
| Task 3.1.3 | Send Closeout Packages as Trade Contractors reach 50% complete.
| Task 3.1.4 | Create Final Payment Checklists as Trade Contractors reach 50% complete.
| Task 3.1.5 | Obtain Final Approval from PX for each Trade Contractor.
3.2 | Owner
| Task |  |  | Responsible | Status | Target | Actual
| Task 3.2.1 | Produce the Final Cost Report.
| Task 3.2.2 | Create and have signed the Final Change Order, reconciling the GMP and closing out any Owner allowances.
| Task 3.2.3 | Submit the Final Requisition to the Owner.
| Task 3.2.4 | Obtain Final Payment from the Owner.
| Task 3.2.5 | Transfer general conditions items to the Owner.
4.0 | ENGINEERING
4.1 | Change Management - Owner
| Task |  |  | Responsible | Status | Target | Actual
| Task 4.1.1 | Set up periodic CCA review time to relieve pressure of out-of-scope changes on work progress.
| Task 4.1.2 | Reconcile all outstanding changes with the Owner.
4.2 | Change Management - Trade Contractors
| Task |  |  | Responsible | Status | Target | Actual
| Task 4.2.1 | Reconcile all outstanding changes with Trade Contractors.
| Task 4.2.2 | Periodically review CR Log and make calls to PMs of non-performing Trade Contractors.
| Task 4.2.3 | Send Final Amendments to Trade Contractors.
4.3 | Submittals
| Task |  |  | Responsible | Status | Target | Actual
| Task 4.3.1 | Determine list of required submittals.
| Task 4.3.2 | Discuss how Owner wants submittals at end of project [ Location, Copies, etc. ].
| Task 4.3.3 | Transmit list of required submittals to Trade Contractors.
| Task 4.3.4 | Nearing project completion, review submittal log for unsubmitted items and items with statuses of "R&R" or "Resubmit for Record".
| Task 4.3.5 | Transmit list of submittals needed for completion to Trade Contractors weekly.
| Task 4.3.6 | Transmit final submittal log to Owner and A/E.
4.4 | As-Builts
| Task |  |  | Responsible | Status | Target | Actual
| Task 4.4.1 | Determine contractual obligations for as-builts.
| Task 4.4.2 | Set up system for periodic review of as-builts if not already required for payment.
| Task 4.4.3 | Transmit completed as-builts to Owner. Have Owner sign transmittal indicating receipt.
4.5 | Attic Stock
| Task |  |  | Responsible | Status | Target | Actual
| Task 4.5.1 | Determine list of required attic stock with responsible Trade Contractors.
| Task 4.5.2 | Determine from Owner where specific attic stock items will be stored and to whom items shall be delivered.
| Task 4.5.3 | Verify that attic stock is in specified quantities and styles, and is organized before transmitting to Owner.
| Task 4.5.4 | Transmit attic stock to Owner. Have Owner sign transmittal indicating receipt.
4.6 | Keys
| Task |  |  | Responsible | Status | Target | Actual
| Task 4.6.1 | Determine keying schedule for facility with Owner.
| Task 4.6.2 | Determine to whom keys should be transmitted with Owner.
| Task 4.6.3 | Ensure that keys are properly organized and work at their stated locations before transmitting to Owner.
| Task 4.6.4 | Transmit keys to Owner. Have Owner sign transmittal indicating receipt.
4.7 | O&M Manual
| Task |  |  | Responsible | Status | Target | Actual
| Task 4.7.1 | Determine O&M Manual requirements from contract and specifications.
| Task 4.7.2 | Team sets up O&M Manual base.
| Task 4.7.3 | Review O&M Manual structure with Owner.
| Task 4.7.4 | Team updates O&M Manual with Items as they come in.
| Task 4.7.5 | Team regularly (weekly) transmits list of outstanding items to Trade Contractors.
| Task 4.7.6 | Transmit O&M Manual to Owner. Have Owner sign transmittal indicating receipt.
4.8 | Owner Training
| Task |  |  | Responsible | Status | Target | Actual
| Task 4.8.1 | Determine Owner Training requirements from contract and specifications.
| Task 4.8.2 | Develop a schedule for Owner Training, including when systems will be complete, O&M submission, and attendees.
| Task 4.8.3 | Review Owner Training attendees list with Owner.
| Task 4.8.4 | Update Owner Training schedule weekly and review at Owner/Designer/Gilbane meeting.
| Task 4.8.5 | Transmit Owner Training videos to Owner. Have Owner sign transmittal indicating receipt.
4.9 | Warranties & Guarantees
| Task |  |  | Responsible | Status | Target | Actual
| Task 4.9.1 | Determine Warranty & Guarantee requirements from contract and specifications.
| Task 4.9.2 | Team regularly (weekly) transmits list of outstanding items to Trade Contractors.
| Task 4.9.3 | Transmit Warranty & Guarantees to Owner. Have Owner sign transmittal indicating receipt.