Final Inspection & Punch List

Final Inspection Date & Time: 7/3/14 - NOT FINALInspector:  Carol Fittell

|  |  | Rock Chalk Park |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project: __________________________________________________________________________ |
|  |  |  |  | Invitation List |
| Contractor:Bliss Sports |  | Owner: KU & City of Lawrence |
| Project Engineer: |  | Project Manager: Casey Thomas |
| Design Engineer: Paul Werner |  | City Engineer:David Cronin |
| Fire Dept: |  | Police Dept: |
| Other: |  |  |  |
|  |  |  |  |  | Sign In |
|  |  | Name | Phone No. |  | e-mail |
|  | Carol Fittell |  | 785-764-6951 |  | cfittell@lawrenceks.org |
|  |  |  |  |  | PUNCH LIST |
| 1 Complete seeding, mulching and fertilizing. |  |  |
| 2 | Re-backfill areas where dirt has settled/eroded behind curbs and next to sidewalks. |
| 3 Reseed areas as needed. |  |  |  |
| 4Maintain erosion control until vegetation is established. |
| 5 | Excavate silt from three detention ponds to establish full design capacity. |
| 6 |  | Re-grade ditch in southeast corner of South Lot to drain. |
| 7 | Complete tennis courts. |  |  |  |
| 8 | Complete tennis court lights. |  |  |
| 9 |  | Complete 5k natural trail. |  |  |  |
| 10 | Remove form boards from inside curb inlets. |
| 11 Clean curb inlets of sediment and debris. |  |  |
| 12 | Backfill around curb inlets. |  |  |  |
| 13 | Completion of trees. |  |  |  |

Form: project final inspection and punch list pg 1 and 2. 10/10

PUNCH LIST (con't)

- Straighten crooked trees.

- Completion of shrubs.

- Completion of site entry sign.

- Completion of irrigation.

- Construct sidewalk ramp on County Road connection RCD sidewalk to pre-existing rec path.

- Install corner monument box at George Williams Way and Rock Chalk Drive.

- Complete grading in Overflow Lot and establish seeding.

- Construct drive approaches off Rock Chalk Lane to the Overflow Lot.

- Complete curb and gutter in North Lot.

- Complete storm sewer installation in North Lot.

- Chip and seal county road.

- Repair all chips in concrete.

- Clean concrete slobbers off pavement.

- Complete joint sealing.

- Complete routing and sealing of cracks.

- Recommend installing bollards on all sidewalk ramps greater than 10 feet wide to prevent vehicular traffic.

- Cleanup of site and surrounding area from trash and debris.

- Rectify undermining of sidewalk and pavement subgrade washed out by irrigation leak in North Lot.

- Clean streets, lots, and sidewalk.

- Replace out of spec/tolerance sidewalk; especially east of GWW near connection to existing.

- Construct Fire Pit.

- Install waterline for water fountain at tennis courts.

- Stripe parking lots.

- Clean rock checks of sediment and debris, especially into pond areas.

- Repair crack on George Williams way where construction entrance was jumping the curb.

- Repair crack on Rock Chalk Lane near softball building.

- Replace sidewalk panel cracked east of Soccer Field due to loading within 24 hours of pour.

- Seal curb joints with MP-1.

42

43

44

45

46

47

48

49

Form: project final inspection and punch list pg 1 and 2. 10/10