## Sheet1
Excel Gantt Chart
Task | Duration | Start date | End date
Clear site of rocks and stumps | 5 | 2012-02-17 | 2012-02-22
Install drainage pipes | 2 | 2012-02-22 | 2012-02-24
Replace topsoil | 3 | 2012-02-24 | 2012-02-27
Add basic fertilizer | 3 | 2012-02-27 | 2012-03-01
Apply seed | 3 | 2012-02-29 | 2012-03-03
Apply mulch | 3 | 2012-03-01 | 2012-03-04
Formulas:
End date = [Start date]+[Duration]
Use the table in the left create a Gantt chart
similar to the one below
Dates are really numbers; day 0 = 1/1/1900
Click on a date; use Home|Number|Comma to view numerical value; sue Ctrl+Z (undo) to restore date fromat
1 Make a stacked bar chart from 3 columns (task, duration & start date) (A)
2 Change horizontal axis min & max (40956, 40972)
3 Right click chart. use Select Data, click up arrow to move Start date to top (B)
4 Format vertical axis: reverse categories (C)
5 Remove legend; change fill colour No Fill so gridline are not hidden by white bars. Format horizontal axis - Major axis set to 2 (shows dates with 2 day jumps) or whatever number lets us see the dates clearly on the axis

## Sheet2
| Start | End
Task A | 2011-12-15 | 2012-07-31
Task B | 2012-01-05 | 2012-08-15
Task C | 2012-02-01 | 2012-09-01
Task D | 2012-03-30 | 2012-09-01
Task E | 2012-06-01 | 2012-12-31
Task F | 2012-08-01 | 2012-12-31