EVENT MANAGEMENT FLOW CHART

| Date & Time | Sponsorship | Vendors |
| --- | --- | --- |

|  | Media List, |  |  |
| --- | --- | --- | --- |
| Venue | Press Releases | Children’s Area | Run of Show |
|  | and Press |  |  |

Invites

| VIP Night | Community | Layout | Revenue |
| --- | --- | --- | --- |
|  | Council |  | Enhancers |

| Invitation | Mailing List | Walk-thru | Volunteers |
| --- | --- | --- | --- |

Food & Drink	Entertainment	Décor	Program Book

dmariani@marianimarke*ng.com

(561) 512-­‐1440

EVENT TIMELINE

Annual Event

• 	Plan on a 10 month schedule

• 	Main event, with a few smaller events prior

– 	Smaller events are hosted to spark enthusiasm, increase awareness and membership, generate action and contributions

7-10 months prior to the event

• 	Type of event

• 	Goals & budget

• 	Timeline

• 	Recruit committee members

• 	Solicit proposals from vendors – venue, caterers, etc.

• 	Determine target audience and start creating a mailing list

• 	Reserve event site

• 	Make sure the charity has representation at your meetings

• 	Create media list

• 	Schedule pre-events

• 	Get event printed in calendar sections of local paper, magazines, etc.

• 	Schedule monthly meetings, then weekly meetings closer to event, and as needed

dmariani@marianimarke*ng.com

(561) 512-­‐1440

EVENT TIMELINE

6 months prior to event

• 	Assemble your team

• 	Assign Duties

• 	Refine invitation list – Design and Send Save the Date

• 	Contact state, local or national organizations to schedule announcement or speaking engagements for your event

• 	Prepare sponsor package and any presentation materials

• 	Send press releases

• 	Update Website, add online ticket sales – unless it’s a gala

• 	Check to see if you need insurance, liquor licenses, permits etc.

• 	Hire photographer

5 months prior to event

• 	Continue to refine mailing list

• 	Design invitation

• 	Offer to speak to local clubs and organizations

• 	Contact local companies for contributions and sponsorships

• 	Confirm – location, food, entertainment and AV needs

| • | Parking |  |  |
| --- | --- | --- | --- |
| • | Media | dmariani@marianimarke*ng.com |
| • | Continue your outreach efforts | (561) 512-­‐1440 |

EVENT TIMELINE

4 months prior to event

• 	Order invitations

• 	Media efforts

• 	Select and order take-away gifts, souvenirs, etc.

3 months prior to event

•  Send advance invitations to Sponsors & Underwriters •  Send invitations to prominent people

• 	If you have a charity spokesperson, celebrity guest, etc. make sure arrangements are confirmed

•  Network with officials and community leaders •  Press release and picture of the event team •  Follow up with caterer, rentals, etc. •  Finalize invitation and mailing list

dmariani@marianimarke*ng.com

(561) 512-­‐1440

EVENT TIMELINE

2 months prior to event

• 	Prepare to mail invitations

• 	Schedule meeting to address invitations

• 	Have committee members write personal notes with the invitation

• 	Follow up with the key invitees to make sure they are attending

• 	Meet with key officials or community business leaders to discuss the event and stimulate more interest and involvement

• 	Send press release with photo of key people – Honorary Chair, Chair, Celebrity, Spokesperson, etc.

1 month prior to event

• 	Determine your receiving line (if extremely formal) – Honorary Chair, Chair, Charity Director of Development & President, Board of Directors

• 	Confirm speaker, entertainment

• 	Track RSVP

• 	Prepare Run of Show

• 	Seating Chart

• 	Prepare program

• 	Program book printed

• 	Press release

• 	Establish a Plan B – speaker, bad weather, etc.

dmariani@marianimarke*ng.com

(561) 512-­‐1440

EVENT TIMELINE

1 week prior to event

• 	Send final press release to media

• 	Confirm catering, AV, seating, rest rooms, first aid, photographer, supplies, flowers, décor, entertainment, etc.

• 	Review RSVP list

• 	Provide caterer with final numbers

• 	Tweak run of show and talking points

• 	Brief your keynote speaker, Emcee, etc.

• 	Create event layout – send out prior to event

• 	Walk through with committee & volunteers

Event Day!

• 	Follow event layout – have extra copies

• 	Provide transportation for dignitaries, speakers, etc.

• 	Set up registration table

• 	Set up media registration table with press kits (if appropriate)

• 	Display table assignments at the entry

• 	Be sure greeters and ushers are in place

• 	Circulate!

• 	For any last minute cancellations, have your volunteers fill in at the tables

| for a seated event | dmariani@marianimarke*ng.com |
| --- | --- |
|  | (561) 512-­‐1440 |

EVENT CHECKLIST

- Facilities

- rental of meeting or reception room(s)

- overnight accommodations:

______number of rooms ______rate

rental of:

- chairs

- tables

- props (specify)

- lectern

- tent

- canopy

- lighting

- extra help

- coat checkroom

- special electrical or telephone hookups

- setup charges

- cleanup charges

- Food Service

- number of people to be served

Cost per person for:

- coffee hour

- luncheon

- dinner

- afternoon break

- cocktail hour

- liquor

- wine

- other beverages

- table linen

- rented table service

- gratuities

- test meal

dmariani@marianimarke*ng.com

(561) 512-­‐1440

EVENT CHECKLIST

| 3. | Equipment Rental | 4. | Decorations |
| --- | --- | --- | --- |
| � tables |  | � flowers |
| � canopy or tent | � table decorations |
| � chairs |  | � extra plants |
| � flooring or carpeting | � props |  |
| � risers |  | � corsages, boutonnieres |
| � ropes or stanchions | � candles |
| � props |  | � direction signs |
| � registration desks and stools | � other decorations (such as ribbon, |
| � outdoor toilets | balloons) |  |

- booths

- lighting

- backdrop

- trash containers

- fencing

dmariani@marianimarke*ng.com

(561) 512-­‐1440

EVENT CHECKLIST

| 5. | Design and Printing | 6. | Postage and Shipping |
| --- | --- | --- | --- |
| � fee for design concept and package | � postage for invitations and reply |
| � advance announcements | cards |  |
| � invitations | � bulk mailing of promotional |
| � programs | materials |
| � promotional flyers | � mailing-house charges |
| � posters/signs | � shipping |

- tickets

- maps

- place cards

- registration packets

- name tags and holders

- any other printed materials

dmariani@marianimarke*ng.com

(561) 512-­‐1440

EVENT CHECKLIST

- Recognition Items

� awards, plaques, trophies � engraving

� calligraphy � framing

� shipping and handling

- Miscellaneous

- VIP travel and expenses

- honoraria

- gifts

- mementos

- extra help

- security

- insurance

- first-aid station

- taping and transcribing proceedings

- visitor's-center materials and staff

- electrical connections

- water hookups

- Transportation

� buses � vans � parking � valets

- Entertainment

� fees

� additional equipment � promoter fees

dmariani@marianimarke*ng.com

(561) 512-­‐1440

EVENT CHECKLIST

- Publicity

� advertising � photographer � printed photos � slides

� duplicating � mailing

� entertaining/hospitality for the press � press-room equipment

� banners

•  12. Audio-Visual Equipment •  � slide and film projectors

• 	� screens

• 	� extension cords

• 	� projector carts

• 	� microphones

• 	� mixers

• 	� speaker system

• 	� tape recorders

• 	� television monitors

• 	� VCRs

• 	� overhead projectors

• 	� pointers

• 	� flip charts

• 	� blackboards

• 	� technician and operator services

dmariani@marianimarke*ng.com

(561) 512-­‐1440

EVENT CHECKLIST

- Office Expenses

� staff time

� overtime and compensatory time � additional staff (temporaries,

students)

� data processing � phones

� duplicating

� postage for general correspondence

  - supplies (pens, pads, decals)

- committee materials

- hospitality for committee members

- complimentary tickets

- staff travel/accommodations

dmariani@marianimarke*ng.com

(561) 512-­‐1440