## A. Detailed Project Work Plan
Up-Scaling Basic Sanitation for the Urban Poor (UBSUP) |  |  |  | SafiSan Project |  |  |  | WSP: | NAWASSCO (example)
Detailed Project Work Plan |  |  |  | sheet A
[5 empty] | Prepared by: |  |  |  |  | Date:
Activity | CARD |  | Category (3) |  |  | Status (1) |  |  | Month>>
Category | No. | Activity |  | Output | Tool(s)? |  | Deadline | Person(s) responsible | Team Week (no.)>>
Preparatory activities | 1 (4) | WSP appoints staff members responsible for onsite sanitation & for SafiSan programme | A | Responsible unit or person(s) | Yes |  | June 20
| 2a | Project Task Team (PTT) establishment & kick-off meeting (discussion of ToR) | A | PTT is formed and understands its roles, etc. | Yes
| 2b | Preparation of the detailed Project Work Plan | A | Detailed Project Work Plan
| 3 | Preparation of the SafiSan office/desks within the office of the WSPs | A | Functioning unit & computer (+software) | Yes
| 4 | Awareness creation (regarding the project) at WSP level (meeting, posters, etc.) | B | All WSP staff are fully aware of SafiSan | Yes
| 5 | Training/induction of relevant WSP staff on the SafiSan software & toolkit | B | All relevant staff are trained | Yes
| 6 | Capacity development activities (mainly at WSP level) provided by the Field Monitors | B | Capacity is built | Yes
| 7a | Assessing the required number of Social Animators | A | No. of SAs is adapted to the tasks | Yes
| 7b | Recruitment of the Social Animators (based on area population data & habitation patterns) | A | Team of qualified Social Animators
| 8a | Training of the Social Animators | B | Team of trained Social Animators | Yes
| 8b | Meeting of project implementers (PTT, SAs, Artisans & Emptiers) | B | Improved coordination and communication
Demand assessment | 9 | Demand assessment in the SafiSan Project PHASE 1 project area (zone) using VST (5) | C | Demand assessment report using template | Yes
| 10 | Confirmation of SafiSan Project PHASE 1 project area(s) | C/A | Decision approved by WSP management | Yes
| 11 | Construction of the SafiSan demonstration toilets | F | According to the criteria (see Toolkit) | Yes
| 12a | Preparation of area(s) assessments for PHASE 2 (using the VST) | C/A | List of potential areas | Yes
| 12b | Data collection for PHASE 2 project areas | D | Reliable data available on potential project areas
| 12c | Confirmation of the PHASE 2 SafiSan Project area(s) | A | PHASE 2 project areas are known
| 13 | Assessing the need for and (if yes) the required number and capacity of DTFs | C | Demand assessment report using the template
| 14 | Identification & securing of suitable & accessible sites for drying beds/DEWATS (DTFs) | D | Demand assessment report using the template | Yes
| 15 | Data collection and transfer to the Virtual Sanitation Tool (VST) | D | The VST has the most recent data | Yes
Community-level (2) | 16 | Design of the community awareness > mobilisation > social marketing project component | A | The Social Marketing Programme (harmonised) | Yes
(area level) | 17 | Preparations for the community awareness & mobilisation programme | A | Lists of activities, persons, tools, etc. | Yes
| 18 | Identification, registration and training of the local artisans | D | List with artisans (+ details) | Yes
| 19 | Identification, registration (database), training and licensing of the manual emptiers | D | List with manual emptiers (+ details) | Yes
| 20 | Identification and training of DTF operators | D/F | Procedure based on criteria | Yes
| 21 | Implementation of the short school WASH programme | E | Procedure based on criteria | Yes
Implementation | 22 | Checklist for assessing the completion of preparatory and other project activities | B | All activities are well implemented | Yes
| 23 | Start of the community awareness and mobilisation component (barazas, etc.) | E1/E2 | Trained & licensed manual emptiers | Yes
| 24 | Start of the social marketing component (e.g. household & plot visits) | E3 | School children are sensitised | Yes
| 25 | Data collection & transfer by Social Animators | D | Database is kept up-to-date | Yes
| 26 | Registration of customers | D | Improved procedures (if necessary) | Yes
| 27 | How to bring artisans and customers together? | A/B | Community & artisans aware of SafiSan procedures | Yes
| 1): | N = Not yet started; D = Draft ready; O = On-going; C = Complete; E = Delayed
| 2) | Each community awareness & mobilisation activity such as the SafiSan Mini Fairs and the SafiSan Baraza Shows has its own programme
| 3): | A = Design & planning; B = Information & training; C = Demand assessment; D = Data collection; E1 = Awareness creation; E2 = Community mobilisation; E3 = Social marketing; F = Technical; G = Disbursement request; H = Reporting
| 4): | The Activity CARDS are included in the Toolkit
| 5): | VST = Virtual Sanitation Tool

## B. Detailed Project Work Plan
Up-Scaling Basic Sanitation for the Urban Poor (UBSUP) |  |  |  | SafiSan Project |  |  |  | WSP >>
Detailed Project Work Plan |  |  |  | sheetB
[5 empty] | Prepared by: |  |  |  | Date:
Activity | CARD |  | Category (3) |  |  | Status (1) |  |  | Month >>
Category | No.(4) | Activity |  | Output | Tool? |  | Deadline | Person responsible | Team Week (no.) >>
Implementation | 28 | Construction (or assembly) of SafiSan toilets and of the DTF(s) | E3/F | Well sited and constructed toilets | Yes |  | June 19
Coordination | 29 | Project Task Team meetings (when required) | A/B | Proper organisation & coordination | Yes
Disbursements | 30 | Preparation of disbursement requests (when required) | G | Timely submission of disb. request | Yes
| 31 | Signing of memorandum of understanding (MoU) for DTF(s) with relevant authorities | T | Signed MoU | Yes
| 32 | (final) Inspections, rectifications & commissioning & data collection on SafiSan toilets | T/D | All toilets are good & of good quality | Yes
Data collection | 33 | Transfer of data to the SafiSan Database (as required)(on WSP-SafiSan computer) | D | Data entered in SafiSan computer | Yes
Implementation | 34 | Payment of subsidies (on-going/as required) | G | Subsidies paid on time!! (on-going) | Yes
| 35 | Training of the operators of decentralised treatment facility (-ies) | B | Trained DTF operators | Yes
| 36 | Community sensitisation on the decentralised treatment facility (-ies | E | Community is aware of value chain & DTF | Yes
Data collection | 37 | Transfer of data to the WSTF (UPC-IS & MajiData) at regular intervals | D | Data is transferred | Yes
| 38 | Updating of the UPC-IS & MajiData (WSTF level) and feedback to WSP & Field monitors | D | MajiData & UPC-IS are updated | Yes
Operation & monitoring | 39 | Monitoring the use and maintenance of the SafiSan (UDDT) toilets | I | SafiSan toilets monitored (on-going) | Yes
| 40 | Sludge management (1): monitoring emptying, transport & waste disposal | I | Monitored value chain | Yes
| 41 | Sludge management (2): monitoring DTF operation | I | Monitored value chain | Yes
| 42 | Regular reporting and providing feedback (used to improve SafiSan concept & UPC) (2) | H | Reports handed in on time (on-going) | Yes
Preparatory works | 43 | Preparation of Phase 2 of the SafiSan project | A | Detailed Work Plan | Yes
Data collection | 44 | Updating the SafiSan project layer in MajiData | D | Uploading of MajiData projects layer | Yes
(5) >> | 45
46
47
48
49
50
| 1): | N = Not yet started; D = Draft ready; O = On-going; C = Complete; E = delayed
| 2): | Testing of the entire set of SafiSan procedures (toilet registration, construction, etc.)
| 3): | A = Design & planning; B = Information & training; C = Demand assessment; D = Data collection; E1 = Awareness creation; E2 = Community mobilisation; E3 = Social marketing; F = Technical; G = Disbursement request; H = Reporting; I = Operations monitoring
| 4): | The Activity CARDS are included in the Toolkit
| 5): | If deemed necessary, new (additional) activities can be added
Notes & remarks: