PROJECT SCOPE DOCUMENT

| DATE CREATED: | November 2006 | VERSION NUMBER: | 1 |
| --- | --- | --- | --- |
| AUTHOR OF DOCUMENT: | Rachel Sharp, Project Planning Officer |
| PROJECT DETAILS |
| Project Description | Revealing the ‘accessible remoteness’ of the woodlands, sea lochs, mountains and culture of the UK's first Forest Park and Scotland's first National Park. |
| Project Title | Argyll Forest Park Landscape Partnership Scheme |
| Location | Argyll Forest Park (provisional boundaries agreed by Steering Group): The area covered by the ‘Argyll Forest Park Landscape Partnership’ sits within the Argyll & Bute Council area of Loch Lomond & the Trossachs National Park. The Landscape Partnership boundary to the northeast extends to the river Loin at Arrochar, the village of Strachur in West Cowal and Sandbank at the south-eastern boundary of the National Park. |
| REASONS FOR PROJECT: |
| Vision: A sustainable and healthy environment, economy and community. Strong, active communities, involved and interested in their landscape and its heritage. By promoting the accessible remoteness and the magical, friendly, mysterious image of the Forest Park, people will be attracted and businesses retained. The skills and jobs will be here to sustain, conserve and enhance the special character of the area with facilities in place for people to discover, understand and enjoy their surroundings and therefore be committed to its future. The AFPLP Scheme will: - Realise the communities plans to work as equal partners in the conservation and future development of the area. This initiative will build on the commitment and success of the community network led initiative to improve the physical environment of the area increasing its capacity to collectively improve access to and enjoyment of local heritage in a sensitive way that will also have a range of social and economic benefits. - Raise awareness of and improve access to undiscovered Cowal, revealing the hidden layers of landscape while safeguarding the magical qualities of the area, - Engage effectively with visitors, communities and interest groups to conserve those qualities. - Revive the traditional skills and events needed to safeguard the character of this highly valued landscape. The Planning Phase (Nov 06-Oct 07) is required to enable: - Research and Assessment: to examine and assess the information currently and soon to be available, making links and extracting relevant information and filling in knowledge gaps through partnership working and commissioning specialist input where required. - Partnership Development: Enhance and build upon existing ‘bottom up’ partnership working including: - Community and interest group workshops and surveys to contribute to process - Develop and formalise Partnership Agreement - Landscape Partnership Strategy: Assessment of landscape heritage of the area and identification of the Scheme’s priorities, vision, aims and broad themes. Views on this vision / themes |

Customer Message/Benefits

Identify 'wow factor' / USPs for area – community workshops… Discover the ‘accessible remoteness’ of the magical, friendly, mysterious woodlands, sea lochs, mountains and culture of Argyll Forest Park. Economy - healthy business - jobs - skills - promotion of image / attractiveness of area Social / Community - strengthening communities - social inclusion - local decision-making Environment - conservation and enhancement of natural and cultural heritage - use of natural resources - understanding, enjoyment and access

PROJECT DELIVERABLES

The following will be delivered in the scope of the project (Planning Phase – Scheme deliverables not yet known)

- Project Plan (incorporating timeplan, communication plan, risk register, project scope, financial monitoring) - Partnership and match funding agreements - Whole Community Environment Plans - Landscape Character Study - Audience Development Plan - Training Plan - Access Plan - Landscape Partnership Strategy - Programme of projects - Evaluation and monitoring criteria

| SECTION SPECIFIC TASKS |
| --- |
| Section | Works | Commence | Complete |
| Project Planning and Monitoring | Produce an agreed Project Plan (including Scope, Timeplan, Risk Register, Communication Plan, Financial Monitoring) | Start Nov 06 | End Dec 06 |
| Research and Assessment | General research to inform Project Plan, Theme-based research (landscape, biodiversity, cultural and built heritage) and specialist additional research required in order to provide a comprehensive and accurate assessment of the landscape heritage. | Start Nov 06 | End Mar 07 |
| Partnership Development | Developing the commitment of partners to the project, including securing match funding. | Start Nov 06 | End Jun 07 |
| Whole Community Environment Plans | Development of environmental inventory project suggestions by communities through public workshops. | Start Jan 07 | End Mar 07 |
| Landscape Partnership Strategy | Development of detailed vision, aims, objectives and action plan based on data gathered. Production of Landscape Character Study, Conservation Management Plan, Access Plan, Training Plan, Audience Development Plan, Implementation Plan. | Mid Feb 07 | End Aug 07 |
| Application Form | Completion of Stage 1 application form | Start Feb 07 | Mid Sep 07 |

| Key Milestone: | Date: |
| --- | --- |
| Produce agreed Project Plan | 14 Dec 06 |
| Complete analysis of available data | 22 Dec 06 |
| Receive quotes for specialist research | 31 Jan 07 |
| Agree process and format for Whole Community Env Plan | 1 Feb 07 |
| Complete Landscape Partnership Strategy | 31 August 07 |
| Complete and send application form | 14 September 07 |

SCOPE EXCLUSIONS

The following scope items are specifically excluded from the project

The Cowal Marine Access Strategy and Clyde Coastal Strategy are being developed within a similar timeframe to AFPLP Scheme. While there are clear links to these, the AFPLP Scheme will not include direct implementation of the outcomes of these Strategies. Existing projects will not be implemented as part of the AFPLP Scheme. Projects which have physically started will be classed as ‘existing’.

| APPROVED BUDGET | Total £84,100 (including HLF and Partner contributions) |
| --- | --- |

PROJECT CONSTRAINTS:

Available volunteer time (other commitments) Available Partner Officer’s time Deadline for submission to HLF Other Partner’s funding application submission deadlines Delays in funding approval Restricted time available leading to lack of choice in timings of events and workshops. E.g. Winter, affecting attendance / involvement Funding available for planning phase e.g. commissioning additional / specialist research Any other constraints?

PROJECT SUCCESS CRITERIA & CRITICAL SUCCESS FACTORS

AFPLP Scheme: - Increased awareness of the AFPLP Scheme. - Visitor numbers to heritage sites will have increased. (Should we say by how much? How can we measure this?) - Enhancements will be valued, appreciated and well-used by the public visitors and residents. (How will we measure this?) - Information and promotion within and outside of the area will have been enhanced. (Can we give an indication of physical works? E.g. new signposts, waymarkers, interpretation panels, leaflets, online promotion…) - Long-term programme for skills development - Creation of local jobs relating to the conservation / enhancement of the special character of the area - Enhanced responsible access to the landscape and heritage - Scheme has a similar lever of impact across each of four priorities others?…how to measure? Planning Phase: - Approval of Stage 1 funding - A strong, committed and extensive partnership incorporating all individuals and organisations relevant to the Scheme. - Raised awareness of the AFPLP Scheme (how will we measure this?) - Achieved a clear, accurate and comprehensive understanding of the AFPLP area’s landscape and heritage (measure through views of experts / partners) - Achieved a clear understanding of the current and potential audience for the project - Considered how the audience currently access the landscape and heritage of the area and how this could be enhanced. - Produced a plan for how we will enhance traditional skills and skills that can help sustain the future of the area - Identified baseline data on critical success factors, for comparison with data later in Scheme’s development

| STAKEHOLDERS |
| --- |
| Stakeholders Position: | Individual/Group/Organisation Name: |
| Partner Representative | Sue Minns, Community Partnership Board Member Benmore and Kilmun Community Development Trust |
| Partner Representative | Iain MacInnes, Convenor Community Partnership Lochgoil Community Trust |
| Partner Representative | Malcolm Bartley, Ardentinny Community Trust |
| Partner Representative | John Massey, Sandbank Community Trust |
| Partner Representative | Joan MacLean Davidson, Arrochar Community Trust |
| Partner Representative | Jim Sim, Lochgoil Community Trust |
| Partner Representative Local Elected Member | Cllr Douglas Currie, Strachur Development Company |
| Local Elected Member | Cllr Bruce Marshall |
| Partner Representative | Russel Bruce, National Park Board Member |
| Partner Representative | Dorothy Bruce, CowalFest |
| Partner Representative | Stuart Chalmers, Jessie Crowe, Forestry Commission Scotland |
| Partner Representative | Liz Pryor, Scottish Natural Heritage |
| Partner Representatives | Loch Lomond and the Trossachs National Park Authority Hannah Dinnen, Ceci Alderton, Marion McCahon |
| Potential Partner | Argyll and Bute Council |
| Potential Partner | Argyll and Islands Enterprise |
| Potential Partner | VisitScotland |
| Potential (Sub)Partner | Historic Scotland |
| Potential (Sub)Partner | RSBP |
| Potential (Sub)Partner | Scottish Wildlife Trust |
| Any others? |  |

Reporting / Management Structure

# Comments

Page: 1
We may need to have these before that stage in order to progress with the rest of the planning phase (training plans, aud dev, access, potential projects etc)

Page: 3
Are we to think about the whole area in general? Or should we be focussing on particular sites? (Guidance suggests latter, which will be difficult for us as we don’t know them yet)