VDOT Dashboard 4.0 – Projects User Guide

DRAFT

March 2018

Table of Contents

INTRODUCTION	1

About this Guide	1

Purpose of the Guide	1

Audience for the Guide	1

About Dashboard	1

VDOT Dashboard	1

Dashboard 4.0	2

Navigating in Dashboard 4.0	3

Usage Agreement	3

Selecting Project Type	4

Project Detail	4

DASHBOARD 4.0	METRICS	7

Overview	7

Projects	7

Development	7

Delivery	7

Performance Measures	7

On-Time	8

On-Budget	8

Status	8

On-Time	9

On-Budget	9

Business Rules	10

Development On-Time	10

Development On-Budget	14

Delivery On-Time	14

Delivery On-Budget	15

DASHBOARD COMPONENTS	16

Overview	16

Visualization	16

Dashboard Elements	16

Dashboard Functionality	17

Project Overview	17

Project Overview – Elements	17

Project Overview – Functionality	18

Project Details	18

Project Details – Elements	18

Program Details – Functionality	19

DASHBOARD DATA SOURCES	20

Overview	20

Data Sources	20

Cardinal	21

VDOT Dashboard 4.0 User Guide

Data Warehouse	21

iSYP	21

PCES	21

PWA	22

SharePoint	22

SiteManager	22

Virginia Roads	22

TECHNICAL APPENDIX	23

TECHNICAL BUSINESS RULES	24

Development On-Time	24

Detailed Logic	24

Explanations	26

Development On-Budget	30

Detailed Logic	30

Explanations	31

Delivery On-Time	32

Detailed Logic	32

Explanations	35

Delivery On-Budget	36

Detailed Logic	36

Explanations	38

Project Baselines	39

Detailed Logic	39

DATA MAPPING	43

Development On-Time	43

Design/Build Projects	43

DRPT Projects	44

Data Field Cross Reference	44

VDOT Dashboard 4.0 User Guide

Table of Figures & Tables

Figure 1: Current View of Dashboard 3	2

Figure 2: Design for New Dial in Dashboard 4.0	2

Figure 3: Usage Agreement	3

Figure 4: Project Performance Dashboard	4

Figure 5: Project Detail Sub-Screen	4

Figure 6: Performance Dial	5

Figure 7: Filtering Using Drop Down Display	5

Figure 8: Filtering for Project Details	5

Figure 9: Single Project Detail	6

Figure 10: On-Time Status	9

Figure 11: Dashboard 4.0 Project Dial Home Page	16

Figure 12: Dashboard 4.0 Projects Overview	17

Figure 13: Filtered view of projects with filtering criteria	18

Figure 14: Project Details	18

Figure 15: Data Flow Diagram	20

Table 1: Development On-Time Rules	11

Table 2: Development On-Time Example #1	12

Table 3: Development On-Time Example #2	13

Table 4: Development On-Budget Rules	14

Table 5: Delivery On-Time Rules	15

Table 6: Delivery On-Budget Rules	15

Table 7: Project Development On-Time Status Explanation	28

Table 8: Project Development On-Time Priority Levels	29

Table 9: Development On-Budget Status Explanation	31

Table 10: Delivery On-Time Cross Reference	34

Table 11: Delivery On-Time Status Explanation	36

Table 12: Delivery On-Budget Logic	37

Table 13: Delivery On-Time Status Explination	38

Table 14: Design/Build Activity Crosswalk	43

Table 15: DRPT Activity Crosswalk	44

VDOT Dashboard 4.0 User Guide

Introduction

About this Guide

Purpose of the Guide

This guide is designed to provide an introduction and explanation of the Virginia Department of Transportation Dashboard 4.0 (the Dashboard). The primary focus of the guide is on the navigation, features and business rules that support the performance metrics reported on the Dashboard, the calculation methodologies and the data sources.

Audience for the Guide

This guide is intended to help Virginia’s citizens and transportation professionals better understand the Dashboard navigation, functionality, guiding principles, business rules for on-time and on-budget performance measures and project data inputs from source systems that support and inform the results reported on the Dashboard.

Throughout this guide, key points and references are highlighted in the sidebar.

About Dashboard

VDOT Dashboard 3.0

The VDOT Dashboard 3.0 provides a variety of metrics on transportation performance, safety, condition, finances, management, citizen surveys, and

projects. Currently in its third iteration, the Dashboard provides a single, integrated reporting platform for key performance indicators from across the agency.

VDOT Dashboard 4.0 User Guide

More information on Dashboard 3 can be found here.

1

Figure 1: Current View of Dashboard 3

Dashboard 4.0

The fourth iteration of the Dashboard, referred to as Dashboard 4.0, is under development and will be launched one dial at a time beginning in fiscal year 2019. Projects will be the first new dial displayed and the rules and measures driving performance are described in the following sections of this guide.

Figure 2: Design for New Dial in Dashboard 4.0

| VDOT Dashboard 4.0 User Guide | 2 |
| --- | --- |

Navigating in Dashboard 4.0

Usage Agreement

Dashboard 4.0 is initially being released as a prototype. When first opening the link, a usage agreement is displayed to inform the user that the information shared is currently under draft and is subject to change.

Click to the right of the orange button (slide not enabled) then click “Enter” to open Dashboard 4.0.

The usage agreement will be removed when Dashboard 4.0 goes live to the public.

Click

Figure 3: Usage Agreement

| VDOT Dashboard 4.0 User Guide | 3 |
| --- | --- |

Selecting Project Type

Project performance measures are displayed in four dials showing On-Time and On-Budget for Project Development and Project Delivery. The default view shows performance for all projects. Filter for All Projects, VDOT Managed, or Non-VDOT Managed by clicking on the option in the bar above the dials.

Figure 4: Project Performance Dashboard

Project Detail

Detailed information on each project is available by clicking on the orange button for “Project Development” or “Project Delivery”. The page that opens allows for the filtering of projects on a variety of details.

Figure 5: Project Detail Sub-Screen

Provide feedback to the Dashboard 4 project team by clicking on the mail icon at the bottom left of the screen.

To return to the main page, simply click “Project Home” in the top left corner.

| VDOT Dashboard 4.0 User Guide | 4 |
| --- | --- |

Each performance dial displays active projects by default. The chart next to the dial is interactive. Clicking on the chart headers will reset the dial to the selected category to show active, completed, or total projects in the graphic. At the bottom of the dial, the target for the measure is defined.

Figure 6: Performance Dial

The gray segment below the dials provide additional filter options for fiscal year, UPC, District, Residency, City/County, Road System, Accomplishment, Administered By, Scope of Work, Description, Project Status, State of Good Repair, and Smart Scale. The dials will recalibrate with each filter choice.

Figure 7: Filtering Using Drop Down Display

Project detail can be accessed through drilldowns. To access this information, select a single cell in the project row and right-click. From the pop-up menu hover over “Drillthrough” then click on “Development Detail”.

Figure 8: Filtering for Project Details

Dashboard 4.0 functions best in Google Chrome. Some browsers may not display all graphics.

Right-clicking on the project specific row is the only way to access additional detail

| VDOT Dashboard 4.0 User Guide | 5 |
| --- | --- |

The project detail screen provides general information on the project including contact details for the project manager. Task, budget, and mapping details when available are also displayed. The envelope icon in the top right corner will allow the user to provide feedback to the Dashboard 4.0 project team.

Figure 9: Single Project Detail

| VDOT Dashboard 4.0 User Guide | 6 |
| --- | --- |

Dashboard 4.0 Metrics

Overview

This chapter describes the metrics that are used for Projects on the Dashboard. Projects are measured during each phase (Development and Delivery), for their respective performance measures (On-Time and On-Budget).

Projects

Development

Project Development refers to the activities performed during the planning, design, and preparation for advertisement for transportation projects.

Delivery

Project Delivery refers to the activities performed after the award of a project, during construction or delivery of products or services to complete the transportation project.

Most projects typically include both a Development and Delivery phase. However, some projects may only include one phase depending on the nature of the project.

Performance Measures

Project phases of Development and Delivery are measured relative to their approved activity schedules and budgets for on-time and on-budget performance. Therefore, there are four measures: Development On-Time, Development On-Budget, Delivery On-Time, and Delivery On-Budget. Each phase has defined measures, which are described below.

VDOT Dashboard 4.0 User Guide

The four performance measures are:

- Development On-Time

- Development On-Budget

- Delivery On-Time

- Delivery On-Budget

7

On-Time

Development

- Measures the performance of meeting project activities from the time it is approved by the CTB until the Delivery phase begins when the contract is awarded.

- The initial project kickoff activities (Local Agreement, Start Development, and Determine Requirements) are scheduled and fixed (or baselined) upon CTB funding approval.

- The remaining schedule activities become baselined after the project’s full scope has been finalized and approved for design. Delivery

- Measures the performance of completing project milestones from the time the contract is awarded through contract completion.

- Schedules become baselined at the time of the contract award, when the contractor has committed to a specific schedule for completion of the project.

On-Budget

Development

- Compares the CTB approved budget to the current total project estimate.

- Project budgets are fixed when the project is approved for funding by the CTB.

Delivery

- Compares the contract award amount to the current total project estimate.

- Total project budgets are fixed when the project is approved for funding by the CTB.

Status

A status color indicator is calculated for each applicable Project Development Activity and Project Delivery Milestone (On-Time), and the corresponding budget phases (On-Budget). For each project, an overall status is calculated based on available data for each applicable performance measure. The status color indicators are defined below.

| VDOT Dashboard 4.0 User Guide | 8 |
| --- | --- |

On-Time

The on-time metrics have been created to encourage the early-start and early-finish of Project Development Activities and Project Delivery Milestones. This results in projects turning yellow when a critical activity or milestone is approaching to encourage early finish and bring a heightened attention to the schedule. It does not mean that a project is late.

Figure 10: On-Time Status

- Green (G): Good – Activity or Milestone is ahead of schedule, or completed on-time

- Yellow (Y): Heightened Attention – Activity or Milestone planned finish date is approaching

- Red (R): Activity or Milestone is late – Action is required to restore the project to a Green On-Time status

For the Dashboard, a ‘baseline date’ is defined as the date at which the project schedule and budget are established.

On-Budget

The determination of the on-budget status indicator varies by phase, but projects are encouraged to be within 10% of the approved budget or contract award amount. For Project Development, the total project estimate is used because during this phase, engineers and procurement representatives always consider the entire cost of the project through Delivery. In the Project Delivery phase, the performance is measured against the actual contract award amount.

- Green (G): Good – Estimated or actual cost is on or under budget

- Yellow (Y): Heightened Attention – Estimated or actual cost is over budget but does not exceed contingencies

- Red (R): Over Budget – Estimated or actual cost is over budget and exceeds contingencies

| VDOT Dashboard 4.0 User Guide | 9 |
| --- | --- |

Business Rules

Using the defined performance measures as a guide, the status for each project is governed by a set of business rules, which are described below.

Development On-Time

A project is considered On Time (Green) until the next scheduled activity gets within a certain number of days of its planned finish. . At that time the project will be reports as “Yellow” on the Dashboard. If the activity is completed on or before the Planned Finish date, it will turn back to Green. If an activity is 1 (one) day late the project will show red. A project will also show red if critical data is missing.

If an activity completes in the red status (i.e. exceeds the baseline), the project remains in that status until another activity completes on time. Please note in the table below that the Activity names in parentheses reference the name in VDOT’s data systems.

- Target: 70% of projects are awarded by the Planned Finish date

- Baseline Schedule: Of the activities listed in the table below, the scheduled completion dates for Local Agreement, Start Development, and Determine Requirements are locked (or baselined) when the CTB approves the project. Scheduled completion dates for all other activities are baselined with a Planned Finish date when the Determine Requirements activity is completed.

- R-Y-G Status: Project status is based on completing the activities in the table below according to the project’s baseline schedule.

VDOT Dashboard 4.0 User Guide

Project Development On-Time target is 70% of projects to be awarded by the baseline end date

10

| Activity |  | Activity | Early Finish |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Code |  |  |  |  |

Late

Finish

Local Agreement

Start Development

(Authorize PE)

Determine Requirements

(Scope Project)

Engage Public (Approve Willingness, Adopt Location/Design)

Start Purchasing Right-of-Way (Authorize R/W & UT Funds)

Utility Relocation

Complete Purchasing Right-of-Way (Acquire Right-of-Way)

Obtain Permits

Solicit Bids (Advertise

Project)

Start Delivery (Award

Contract)

10

12

22

47, 49

52

67U

69

70

80

84

| > 30 days | ≤ 30 days |  |
| --- | --- | --- |
| early | early |  |
| > 30 days | ≤ 30 days |  |
| early | early |  |
| > 30 days | ≤ 30 days |  |
| early | early |  |
| > 30 days | ≤ 30 days |  |
| early | early |  |
| > 30 days | ≤ 30 days |  |
| early | early |  |
| > 30 days | ≤ 30 days |  |
| early | early |  |
| > 60 days | ≤ 60 days |  |
| early | early |  |
| > 60 days | ≤ 60 days |  |
| early | early |  |
| > 60 days | ≤ 60 days |  |
| early | early |  |
| > 30 days | ≤ 30 days |  |
| early | early |  |

- 0 days late

- 0 days late

- 0 days late

- 0 days late

- 0 days

Baselinelate Finish

| Date | > 0 days |
| --- | --- |
|  | late |

- 0 days late

- 0 days late

- 0 days late

- 0 days late

Table 1: Development On-Time Rules

VDOT Dashboard 4.0 User Guide

11

Examples

- Example #1: As of 12/8/2016, the on-time status of the project below is green because the Scope Project activity completed on time. It will remain as such if the next scheduled activity - Authorize Right of Way and Utility Funds, planned to end on 3/31/2017 - completes 30 days early. If it completes exactly on time, a temporary yellow project status (the leading indicator) will trigger 30 days before 3/31/2017, and the status will change back to green on 4/1/2017.

|  | Activity |  |  |  | Activity |  |  |  | Baseline |  |  |  | Actual End |  |  |  | Status |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Code |  |  |  | End Date |  |  |  | Date |  |  |  |  |  |
|  | Start Development (Authorize |  | 12 |  |  | 8/1/2016 |  |  | 7/28/2016 |  |  |  | Green |  |
|  | Preliminary Engineering) |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Determine Requirements (Scope |  | 22 |  |  | 12/1/2016 |  |  | 12/1/2016 |  |  |  | Green |  |
|  | Project) |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Start Purchasing Right-of-Way |  | 52 |  |  | 3/31/2017 |  |  |  |  |  |  |  | Green |  |
|  | (Authorize R/W & UT Funds) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Complete Purchasing Right-of-Way |  | 69 |  |  | 3/31/2018 |  |  |  |  |  |  |  | Green |  |
|  | (Acquire Right-of-Way) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Solicit Bids (Advertise Project/Begin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | State Forces/Hired Equipment |  | 80 |  |  | 3/30/2018 |  |  |  |  |  |  |  | Green |  |
|  | Construction) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Start Delivery (Award Contract) |  | 84 |  |  | 5/15/2018 |  |  |  |  |  |  |  | Green |  |

Table 2: Development On-Time Example #1

| VDOT Dashboard 4.0 User Guide | 12 |
| --- | --- |

- Example #2: As of 12/8/2016, the on-time status of the project below is red because the Scope Project activity is incomplete, and it is the lowest activity status. Scope Project activity was scheduled to finish on 8/30/2016, and if scoping completes while the next scheduled activity ends on time - Adopt Location/Design, baselined to finish on 12/28/2016 - the project status will recover to green.

Activity

Start Development (Authorize

Preliminary Engineering)

Determine Requirements (Scope

Project)

Engage Public (Adopt

Location/Design)

Start Purchasing Right-of-Way (Authorize R/W & UT Funds)

Complete Purchasing Right-of-Way

(Acquire Right-of-Way)

Obtain Permits

Solicit Bids (Advertise Project/Begin State Forces/Hired Equipment Construction)

Start Delivery (Award Contract)

| Activity | Baseline End | Actual | Status |
| --- | --- | --- | --- |
| Code | Date | End Date |  |
| 12 | 11/14/2016 | 8/24/2016 | Green |
| 22 | 8/30/2016 |  | Red |
| 49 | 12/28/2016 |  | Yellow |
| 52 | 5/1/2017 |  | Green |

| 69 | 11/21/2017 | Green |
| --- | --- | --- |
| 70 | 4/10/2018 | Green |

| 80 | 4/10/2018 | Green |
| --- | --- | --- |
| 84 | 6/13/2018 | Green |

Table 3: Development On-Time Example #2

| VDOT Dashboard 4.0 User Guide | 13 |
| --- | --- |

Development On-Budget

The Project Development On-Budget business rules classify each project based on the approved budget and the current project estimate amount.

- Target: 74% of projects have estimates within the approved budget for the project.

- R-Y-G Status: Total project cost performance is measured by comparing the current project estimate to the budget approved by the Commonwealth Transportation Board, as illustrated in the table below. Projects with an estimate that are over one year old, or are missing, will result in a status of yellow.

Project Development On-Budget target is 74% of projects have estimates within the budget.

|  | Approved Budget |  |  |  |  | Current Estimate |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | < $5 million |  | ≤ 0 |  |  | > 0 to < 20% |  | ≥ 20% |
|  | $5 million to $10 million |  | ≤ 0 |  |  | > 0 to > $1M |  | ≥ $1M |
|  | > $10 million |  | ≤ 0 |  |  | > 0 to < 10% or < $5M* |  | ≥ 10% or ≥ $5M* |
|  |  |  |  | * Whichever is less |  |  |

Table 4: Development On-Budget Rules

Delivery On-Time

In the Project Delivery phase, projects may have interim milestones established between the dates of contract award and contract completion. Each of the interim milestones will have an On-Time status calculated based on the criteria below.

- Target: 77% of projects finish on or before the original completion date.

- R-Y-G Status: Project status is based on completing project specific milestones according to the project’s baseline schedule. Milestones include “Start Delivery”, “Complete Delivery”, and other interim milestones specific to the project. The interim milestones include any contractual dates or major phases within the project. The thresholds set below are designed to encourage early start / early finish and mirror the Project Development On-Time rules stated previously in this document.

Project Delivery On-Time target is 77% of projects finish by the original completion date.

| VDOT Dashboard 4.0 User Guide | 14 |
| --- | --- |

Milestones

Project Specific Interim Milestones

Complete Delivery

| Early Finish |  |  |  | Late Finish |
| --- | --- | --- | --- | --- |
| > 14 days |  | ≤ 14 days |  | Baseline |  | ≤ 7 days |  | > 7 days |
|  |  |  |  | End Date |  |  |  |  |
| > 0 days |  |  |  | > 0 days |

Table 5: Delivery On-Time Rules

Delivery On-Budget

In the Project Delivery phase, projects may have interim milestones established between the estimated and actual cost of the contract. The On-Budget status is calculated based on the criteria below.

- Target: 82% of projects finish within 110% of the award amount.

- R-Y-G Status: Delivery project cost performance is measured by comparing the current project estimate and actual cost to the contract award amount.

Project Delivery On-Budget target is 82% of projects finish within 110% of the contract

Status

Projects have not been executed; no status

Active

Completed

Neither the current contract amount, nor the cost of work to date, exceed the award amount by more than 3%

Un-audited final cost is within 110% of award amount

Either the current contract amount, or the

cost of work to date, exceeds the contract award amount by 3% to 10%

Cost of work to date, or

the current contact amount, exceed the original award amount by 3% to 10%

Either the current contract

amount, or the cost of work to date, exceeds the contract award amount by more than 10%

Un-audited final cost is not known (after acceptance but before the 35-day period is closed); Either the cost of work to date, or the current contract amount, exceeds 110% of the award amount

Table 6: Delivery On-Budget Rules

| VDOT Dashboard 4.0 User Guide | 15 |
| --- | --- |

Dashboard Components

Overview

This chapter describes the components that comprise Dashboard 4.0. These include Visualizations, the Projects Overview, and Projects Detail sections.

Visualization

Dashboard Elements

The Projects home page of Dashboard 4.0 contains four gauges, each of which depicts a particular project metric: Project Development (On-Time and On-Budget) and Project Delivery (On-Time and On-Budget). The gauges depict the percent of projects that were classified as green (“good”) and can be filtered to view VDOT-Managed and Locally Managed projects separately.

The four project performance measures are visualized on the Projects home page of Dashboard 4.0.

Figure 11: Dashboard 4.0 Project Dial Home Page

| VDOT Dashboard 4.0 User Guide | 16 |
| --- | --- |

Dashboard Functionality

The four charts are both animated and interactive. They can be updated whenever new data is added to the system to reflect any changes in the overall statistics. There are links to this User Guide, Analytics, and a link to provide feedback to the Dashboard 4.0 project team.

Project Overview

Project Overview – Elements

This portion of the website is accessed by clicking the orange “Project Development” or “Project Delivery” buttons below the dials of the Dashboard’s home page. The Program Overview takes the two metrics displayed (On-Time and On-Budget) – and allows users to see more detailed breakdowns of the projects. The table lists the exact numbers of projects that are classified as Green, Yellow, and Red.

The Project Overview allows the user to see both general On-Time and On-Budget information as well as the list of related projects

Figure 12: Dashboard 4.0 Projects Overview

| VDOT Dashboard 4.0 User Guide | 17 |
| --- | --- |

Project Overview – Functionality

The dials and table are both animated and interactive. There are two ways to filter the data displayed. First you can click on any cell in the row by status. For example, by clicking on the red icon for “Status On-Time”, the dial goes blank (no green projects) and the table list only late projects. The second way to filter is to use the drop down options in the gray section to select a subset of projects.

Figure 13: Filtered view of projects with filtering criteria

Project Details

Project Details – Elements

This portion of the Dashboard is accessed by right-clicking on a single project in the project list and selecting the “Drillthrough” option. This brings the user to a single page for each project. For each project the general information, project schedule, and budget are shown, and where available the project is mapped.

Figure 14: Project Details

| VDOT Dashboard 4.0 User Guide | 18 |
| --- | --- |

Program Details – Functionality

The general information section provides basic project details as well as the contact information for the project. By clicking on the envelope icon, an email to the project contact will be generated automatically. Project development task are listed in the schedule section. Each task planned start and finish is listed and actual start and finish are populated as the project moves forward. The budget section will list the budget, estimate, and variance of the funding for the project along with the date of the estimate.

Initial mapping of the project, where data is available, is zoomed out to a statewide view. The user can zoom in by clicking in the map to get down to a more precise location.

| VDOT Dashboard 4.0 User Guide | 19 |
| --- | --- |

Dashboard Data Sources

Overview

This chapter identifies and defines the data sources used in the Dashboard. A brief overview of each system is provided. These include the iSYP suite, PWA, PCES, Cardinal, Site Manager, SharePoint, Virginia Roads, and the Data Warehouse. The diagram below provides an illustration of the data flow from the various data sources into the Smart Scale Dashboard. Information about projects is entered into these systems by local governments, DRPT, and VDOT.

Local governments, DRPT, and VDOT enter transportation project information into a variety of systems. These systems are used as sources of data. The data is compiled within a Data Warehouse and presented through the Dashboard web site.

Figure 15: Data Flow Diagram

Data Sources

| VDOT Dashboard 4.0 User Guide | 20 |
| --- | --- |

Cardinal

Cardinal is a statewide application that serves as the source system of financial data. The ‘actual cost’ incurred for a given project is obtained from Cardinal data for the Dashboard.

Data Warehouse

VDOT’s Data Warehouse was designed to provide analysis and reporting on data from disparate information technology systems utilized within VDOT. The VDOT data warehouse also serves as a repository for data from transactional and / or archived systems. Data from transactional systems are updated regularly into the Data Warehouse from the source systems — users do not directly update data in the Data Warehouse. The respective source systems provide the data to the Data Warehouse that was created or modified within the past business day. The Dashboard utilizes the Data Warehouse for all of its transportation project data needs.

iSYP

The Integrated Six Year Program (iSYP) suite of applications provides a set of tools for managing projects and developing multi-year, resource constrained improvement programs. The iSYP suite consists of an integrated set of applications, including the following modules: Schedule, Project Pool, Funding, Six-Year Program, Estimates, Construction Expenditures, Each module shares data with other modules, and helps to track transportation projects from their candidacy stage through completion of construction. Other systems leverage data from iSYP for specific purposes. The majority of the data displayed and used for calculations of status in the Dashboard is sourced from iSYP.

PCES

The Project Cost Estimating System (PCES) is a parametric cost estimation tool, used to establish initial project budgets during project scoping. PCES provides a consistent method for generating estimates across the agency. In addition to providing a standard parametric cost analysis capability, PCES serves as the central repository for construction estimates. PCES contains budgets and estimates for every project with a UPC. Multiple estimates are stored as the project progresses from scoping through the design and construction phases. Basic project information and estimate approval information from the Project Pool are made available for viewing in PCES. Estimates from PCES can be viewed in the Project Pool and the live SYP.

| VDOT Dashboard 4.0 User Guide | 21 |
| --- | --- |

PWA

The Project Web Application (PWA) serves as the new source system of entry and record for transportation projects during the Project Development phase. Project Development schedules serve as the foundation for Programming Schedules. This system leverages Microsoft Project Server to maintain the schedule and related information for a given project based on defined development activities. The Dashboard utilizes the schedule data (i.e., planned and actual dates for the tracked milestones) from PWA to calculate the on-time status for the Project Development phase.

SharePoint

VDOT leverages Microsoft SharePoint as an enterprise tool for a variety of purposes and needs. The Dashboard utilizes SharePoint as a mechanism with which contract data for local government administered projects is input by VDOT Project Coordinators, or other designated staff. The data entered into SharePoint feeds into VDOT’s Data Warehouse. This data is used to determine the on-time and on-budget status for these projects in the Delivery phase.

SiteManager

SiteManager is a comprehensive construction management software product that maintains information relevant to the VDOT awarded contracts. The system captures data for each contract from contract award through contract completion and acceptance. The Dashboard leverages documentation for the Project Delivery phase from SiteManager.

Virginia Roads

The Dashboard utilizes the transportation project location data that is available from Virginia Roads for display within the Dashboard.

| VDOT Dashboard 4.0 User Guide | 22 |
| --- | --- |

Technical

Appendix

| VDOT Dashboard 4.0 User Guide | 23 |
| --- | --- |

Technical Business Rules

The detail and logic for the business rules applied to each of the four performance measures are described below. The details are technical in nature and describe the various data conditions that are encountered with transportation project data. In addition, the business rules for project baselines are provided.

Development On-Time

The technical details for the business rules that govern the Development On-Time performance measure are provided below. The business rules assume an understanding of how this data is maintained and managed in the representative source systems and the Data Warehouse.

Detailed Logic

Project Development On-Time business rules contain rules for Critical, Open, and Closed Activities. In addition, general rules and priorities are established for the business logic.

- The following general rules override 'closed' and/or 'open' Activity business rules.

1.1. The following business rules are applicable to Activity 47 and Activity

- One activity, or the other activity, or both activities may be populated.

1.1.1. IF Activity 47 is NULL AND Activity 49 is NOT NULL, THEN Activity

49 is shown.

1.1.2. IF Activity 49 is NULL AND Activity 47 is NOT NULL, THEN Activity

47 is shown.

1.1.3. IF Activity 47 AND Activity 49 are NULL, THEN Activity 49 is shown.

1.1.4. IF Activity 47 AND Activity 49 is NOT NULL, THEN Activity 49 is shown.

| VDOT Dashboard 4.0 User Guide | 24 |
| --- | --- |

1.2. The following business rules are applicable to Activity 70

1.2.1. The Latest Start Date may be NULL or NOT NULL

1.2.2. The Latest End Date may be NULL or NOT NULL

1.2.3. If Latest Start Date = Latest End Date, THEN status data IS NOT shown /// If the Latest_Start_Date and Latest_End_Date are the same date, (indicating a Latest duration of 0 days) the activity will be excluded from the activity and project level on-time assessments.

1.2.4. If Latest Start Date != Latest End Date, THEN status data IS shown

  - If at any time the Latest_Start_Date and Latest_End_Date are updated and the dates are different (resulting in a duration of > 0 days) then Activity 70 will be included in both the individual activity and project status.

- The following are Critical Activity rules. Critical Activity rules override Closed and/or Open Activity rules.

2.1. IF Baseline End Date is NULL, THEN the Activity Days variance calculation for ('10', '12', '22', '47', '49', '52', '67U', '69', '70', '80', '84') is [TRUNC(SYSDATE) - NVL('actual_end_date', 'latest_end_date')]

- The following are Open Activity rules. Open Activity rules override Closed Activity rules.

3.1. IF Baseline End Date is NOT NULL AND Acutal End Date IS NULL, THEN the Activity Days variance calculation for ('10', '12', '22', '47', '49', '52', '67U', '69', '70', '80', '84') is [TRUNC(SYSDATE) - 'baseline_end_date']

- The following are Closed Activity rules.

4.1. IF Baseline End Date is NOT NULL AND Actual End Date IS NOT NULL, THEN the Activity Days variance calculation for ('10', '12', '22', '47', '49', '52', '67U', '69', '70', '80', '84') is ['actual_end_date' - 'baseline_end_date']

| VDOT Dashboard 4.0 User Guide | 25 |
| --- | --- |

Explanations

For the applicable business rules, an explanation of the reason for the status, as well as how the rules are prioritized are provided in the tables below.

|  |  |  |  | Activity |  | RYG Status ¦ |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Business |  | Activity |  |  |  | Early Warn ¦ |  |  |
|  |  |  |  | Days |  |  |  | Development On-Time Status Explanation |
| Rule |  | Code |  |  |  | Critical Flag ¦ |  |  |
|  |  |  |  | Variance |  |  |  |  |
|  |  |  |  |  |  | Priority |  |  |
|  |  | ('10', '12', |  |  |  |  |  |  |
|  |  | '22', '47', |  |  |  |  |  |  |
| 2.1 |  | '49', '52', |  | N/A |  | R¦N¦Y¦1 |  | 'Red on-time status: ' ¦¦ NEW_MILESTONE_DESC ¦¦ ' |
|  |  | '67U', '69', |  |  |  |  |  | milestone baseline missing' |
|  |  | '70', '80', |  |  |  |  |  |  |
|  |  | '84') |  |  |  |  |  |  |
|  |  | ('10', '12', |  |  |  |  |  | 'Green on-time status: ' ¦¦ NEW_MILESTONE_DESC ¦¦ |
|  |  | '22', '47', |  |  |  |  |  |  |
| 3.1 |  |  |  | < -30 |  | G¦N¦N¦8 |  | ' milestone is ' ¦¦ ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' |
|  |  | '49', '52', |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | days ahead of the expected completion date' |
|  |  | '67U') |  |  |  |  |  |  |
|  |  | ('10', '12', |  |  |  |  |  | 'Yellow on-time status: ¦¦ NEW_MILESTONE_DESC ¦¦ ' |
| 3.1 |  | '22', '47', |  | BETWEEN |  | Y¦Y¦N¦4 |  | milestone is ' ¦¦ ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' |
|  |  | '49', '52', |  | -30 AND 0 |  |  |  | days ahead of the expected completion date and there |
|  |  | '67U') |  |  |  |  |  | is a risk of missing this milestone date' |
|  |  | ('10', '12', |  |  |  |  |  | 'Red on-time status: ¦¦ NEW_MILESTONE_DESC ¦¦ ' |
|  |  | '22', '47', |  |  |  |  |  |  |
| 3.1 |  |  |  | > 0 |  | R¦N¦N¦5 |  | milestone is ' ¦¦ ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' |
|  |  | '49', '52', |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | days past the expected completion date' |
|  |  | '67U') |  |  |  |  |  |  |
|  |  | ('10', '12', |  |  |  |  |  | 'Red on-time status: ' ¦¦ NEW_MILESTONE_DESC ¦¦ ' |
|  |  | '22', '47', |  |  |  |  |  |  |
| 3.1 |  |  |  | > 0 |  | R¦N¦N¦2 |  | milestone is ' ¦¦ ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' |
|  |  | '49', '52', |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | days past the expected completion date' |
|  |  | '67U') |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | 'Green on-time status: ' ¦¦ NEW_MILESTONE_DESC ¦¦ |
| 3.1 |  | ('69', '70') |  | < -60 |  | G¦N¦N¦8 |  | ' milestone is ' ¦¦ ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' |
|  |  |  |  |  |  |  |  | days ahead of the expected completion date' |
|  |  |  |  |  |  |  |  | 'Yellow on-time status: ¦¦ NEW_MILESTONE_DESC ¦¦ ' |
| 3.1 |  | ('69', '70') |  | BETWEEN |  | Y¦Y¦N¦4 |  | milestone is ' ¦¦ ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' |
|  |  |  |  | -60 AND 0 |  |  |  | days ahead of the expected completion date and there |
|  |  |  |  |  |  |  |  | is a risk of missing this milestone date' |

| VDOT Dashboard 4.0 User Guide | 26 |
| --- | --- |

|  |  |  |  |  |  |  |  | 'Red on-time status: ¦¦ NEW_MILESTONE_DESC ¦¦ ' |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1 |  | ('69', '70') |  | > 0 |  | R¦N¦N¦5 |  | milestone is ' ¦¦ ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' |
|  |  |  |  |  |  |  |  | days past the expected completion date' |
|  |  |  |  |  |  |  |  | 'Red on-time status: ' ¦¦ NEW_MILESTONE_DESC ¦¦ ' |
| 3.1 |  | ('69', '70') |  | > 0 |  | R¦N¦N¦2 |  | milestone is ' ¦¦ ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' |
|  |  |  |  |  |  |  |  | days past the expected completion date' |
|  |  |  |  |  |  |  |  | 'Green on-time status: ' ¦¦ NEW_MILESTONE_DESC ¦¦ |
| 3.1 |  | '80' |  | < -60 |  | G¦N¦N¦8 |  | ' milestone is ' ¦¦ ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' |
|  |  |  |  |  |  |  |  | days ahead of the expected completion date' |
|  |  |  |  |  |  |  |  | 'Yellow on-time status: ¦¦ NEW_MILESTONE_DESC ¦¦ ' |
| 3.1 |  | '80' |  | BETWEEN |  | Y¦Y¦N¦4 |  | milestone is ' ¦¦ ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' |
|  |  |  |  | -60 AND 0 |  |  |  | days ahead of the expected completion date and there |
|  |  |  |  |  |  |  |  | is a risk of missing this milestone date' |
|  |  |  |  | BETWEEN |  |  |  | 'Red on-time status: ¦¦ NEW_MILESTONE_DESC ¦¦ ' |
| 3.1 |  | '80' |  |  |  | Y¦N¦N¦5 |  | milestone is ' ¦¦ ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' |
|  |  |  |  | 1 AND 15 |  |  |  | days past the expected completion date' |
|  |  |  |  |  |  |  |  | 'Red on-time status: ' ¦¦ NEW_MILESTONE_DESC ¦¦ ' |
| 3.1 |  | '80' |  | > 15 |  | R¦N¦N¦2 |  | milestone is ' ¦¦ ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' |
|  |  |  |  |  |  |  |  | days past the expected completion date' |
|  |  |  |  |  |  |  |  | 'Green on-time status: ' ¦¦ NEW_MILESTONE_DESC ¦¦ |
| 3.1 |  | '84' |  | < -30 |  | G¦N¦N¦8 |  | ' milestone is ' ¦¦ ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' |
|  |  |  |  |  |  |  |  | days ahead of the expected completion date' |
|  |  |  |  |  |  |  |  | 'Yellow on-time status: ¦¦ NEW_MILESTONE_DESC ¦¦ ' |
| 3.1 |  | '84' |  | BETWEEN |  | Y¦Y¦N¦4 |  | milestone is ' ¦¦ ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' |
|  |  |  |  | -30 AND 0 |  |  |  | days ahead of the expected completion date and there |
|  |  |  |  |  |  |  |  | is a risk of missing this milestone date' |
|  |  |  |  |  |  |  |  | 'Red on-time status: ' ¦¦ NEW_MILESTONE_DESC ¦¦ ' |
| 3.1 |  | '84' |  | > 0 |  | R¦N¦N¦2 |  | milestone is ' ¦¦ ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' |
|  |  |  |  |  |  |  |  | days past the expected completion date' |
|  |  | ('10', '12', |  |  |  |  |  |  |
|  |  | '22', '47', |  |  |  |  |  | 'Green on-time status: ' ¦¦ NEW_MILESTONE_DESC ¦¦ |
| 4.1 |  | '49', '52', |  | < 0 |  | G¦N¦N¦7 |  | ' milestone finished ' ¦¦ |
|  |  | '67U', '69', |  |  |  |  |  | ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' days early' |
|  |  | '70') |  |  |  |  |  |  |
| 4.1 |  | ('10', '12', |  | = 0 |  | G¦N¦N¦7 |  | 'Green on-time status: ' ¦¦ NEW_MILESTONE_DESC ¦¦ |
|  |  | '22', '47', |  |  |  |  |  | ' milestone finished on-time' |

| VDOT Dashboard 4.0 User Guide | 27 |
| --- | --- |

'49', '52',

'67U', '69',

'70')

|  |  | ('10', '12', |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | '22', '47', |  |  |  |  |  | 'Red on-time status: ¦¦ NEW_MILESTONE_DESC ¦¦ ' |
| 4.1 |  | '49', '52', |  | > 0 |  | R¦N¦N¦6 |  | milestone finished ' ¦¦ |
|  |  | '67U', '69', |  |  |  |  |  | ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' days late' |
|  |  | '70') |  |  |  |  |  |  |
|  |  | ('10', '12', |  |  |  |  |  |  |
|  |  | '22', '47', |  |  |  |  |  | 'Red on-time status: ' ¦¦ NEW_MILESTONE_DESC ¦¦ ' |
| 4.1 |  | '49', '52', |  | > 0 |  | R¦N¦N¦3 |  | milestone finished ' ¦¦ |
|  |  | '67U', '69', |  |  |  |  |  | ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' days late' |
|  |  | '70') |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | 'Green on-time status: ' ¦¦ NEW_MILESTONE_DESC ¦¦ |
| 4.1 |  | '80' |  | < 0 |  | G¦N¦N¦7 |  | ' milestone finished ' ¦¦ |
|  |  |  |  |  |  |  |  | ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' days early' |
| 4.1 |  | '80' |  | = 0 |  | G¦N¦N¦7 |  | 'Green on-time status: ' ¦¦ NEW_MILESTONE_DESC ¦¦ |
|  |  |  |  |  |  |  |  | ' milestone finished on-time' |
|  |  |  |  |  |  |  |  | 'Red on-time status: ¦¦ NEW_MILESTONE_DESC ¦¦ ' |
| 4.1 |  | '80' |  | > 0 |  | R¦N¦N¦6 |  | milestone finished ' ¦¦ |
|  |  |  |  |  |  |  |  | ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' days late' |
|  |  |  |  |  |  |  |  | 'Red on-time status: ' ¦¦ NEW_MILESTONE_DESC ¦¦ ' |
| 4.1 |  | '80 |  | > 0 |  | R¦N¦N¦3 |  | milestone finished ' ¦¦ |
|  |  |  |  |  |  |  |  | ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' days late' |
|  |  |  |  |  |  |  |  | 'Green on-time status: ' ¦¦ NEW_MILESTONE_DESC ¦¦ |
| 4.1 |  | '84' |  | < 0 |  | G¦N¦N¦7 |  | ' milestone finished ' ¦¦ |
|  |  |  |  |  |  |  |  | ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' days early' |
| 4.1 |  | '84' |  | = 0 |  | G¦N¦N¦7 |  | 'Green on-time status: ' ¦¦ NEW_MILESTONE_DESC ¦¦ |
|  |  |  |  |  |  |  |  | ' milestone finished on-time' |
|  |  |  |  |  |  |  |  | 'Red on-time status: ' ¦¦ NEW_MILESTONE_DESC ¦¦ ' |
| 4.1 |  | '84' |  | > 0 |  | R¦N¦N¦3 |  | milestone finished ' ¦¦ |
|  |  |  |  |  |  |  |  | ABS(ACTIVITY_TIME_VARIANCE)) ¦¦ ' days late' |

Table 7: Project Development On-Time Status Explanation

| VDOT Dashboard 4.0 User Guide | 28 |
| --- | --- |

For Project Development On-Time business rules, the following priority levels are set.

Priority

Level

1

2

3

4

5

6

7

8

Business Rule (at activity

level)

Red - baseline missing

Red - open activity

Red - closed activity

Early Yellow - open activity

Yellow - open activity

Yellow - closed activity

Green - closed activity

Green - open activity

Logic

Status = R and baseline end date is NULL

Status = R and actual end date is NULL

Status = R and actual end date is NOT NULL

Status = Y and actual end date is NULL AND Early Flag = 'Y'

Status = Y and actual end date is NULL AND Early Flag <> 'Y'

Status = Y and actual end date is NOT NULL

Status = G and actual end date is NOT NULL

Status = G and actual end date is NULL

The following notes apply to the priority levels.

- Rules only apply to Activities ('10', '12', '22', '47', '49', '52', '67U', '69', '70', '80', '84')

- Rules for "closed" activities apply to the MAX (activity_code) within the MAX (actual_end_date) per UPC, OR if the activity is a "critical red".

- Rules for "open" activities apply to all open activities.

- The project level status is derived as the MIN (project level priority) from the project's activities meeting the criteria above (#1, #2, #3).

- IF multiple activities match the criteria above, THEN project level status is derived from the activity with the latest actual_end_date (only impacts closed activity).

- IF multiple activities match the criteria above, THEN project level status is derived from the activity with the earliest baseline_end_date.

- IF multiple activities match the criteria above, THEN project level status is derived from the activity with the maximum activity_code.

Table 8: Project Development On-Time Priority Levels

| VDOT Dashboard 4.0 User Guide | 29 |
| --- | --- |

Development On-Budget

The technical details for the business rules that govern the Development On-Budget performance measure are provided below. The business rules assume an understanding of this data is maintained and managed in the representative source systems and the Data Warehouse.

Detailed Logic

The project cost performance is measured by comparing the current project estimate to the budget approved by the Commonwealth Transportation Board. A project will be given the status of the ‘lowest’ value as indicated by the rules below.

- Rules to determine status based on age of estimate

1.1. IF 'Today' > Approved Estimate Date AND Approved Estimate Date is < 365 calendar days, THEN Status = Green.

1.2. ELSE IF 'Today' > Approved Estimate Date AND Approved Estimate Date is >= 365 calendar days, THEN Status = Yellow.

- Rules to determine status based on value of Approved Estimate Total is less than $5 Million. The following variance calculation is used: (CTB Approved Estimate – Current Estimate Total) as %.

2.1. IF variance ≤ 0%, THEN Status = Green

2.2. IF variance > 0% AND < 20%, THEN Status = Yellow

2.3. IF variance >= 20%, THEN Status = Red

- Rules to determine status based on value of Approved Estimate Total is greater than or equal to $5 Million and less than $10 Million. The following variance calculation is used: (CTB Approved Estimate – Current Estimate Total) as $.

3.1. IF variance ≤ $0, THEN Status = Green

3.2. IF variance > $0 AND < $1 Million, THEN Status = Yellow

3.3. IF variance >= $1 Million, THEN Status = Red

- Rules to determine status based on value of Approved Estimate Total is greater than or equal to $10 Million. The following variance calculation is used: (CTB Approved Estimate – Current Estimate Total) as % and $. The lesser of the % and $ value is used to determine the status.

4.1. IF variance ≤ $0, THEN Status = Green /// Since variance is less than 0, a

  - comparison is not required.

4.2. IF variance > 0% AND < 10%, OR IF variance < $5 Million, THEN Status = Yellow

4.3. IF variance >= 10%, OR IF variance >= $5 Million, THEN Status = Red

| VDOT Dashboard 4.0 User Guide | 30 |
| --- | --- |

Explanations

For the applicable business rules, an explanation of the reason for the status is provided in the table below.

Business

Rule

Dev. On-

Budget

Status

Variance

Development On-Budget Status Explanation

|  | 1.1 |  | G |  | < 365 days |  |  | <<add explanation text displayed>> |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1.2 |  | Y |  | >= 365 days |  |  | <<add explanation text displayed>> |  |
|  | 2.1 |  | G |  | ≤ 0% |  |  | <<add explanation text displayed>> |  |
|  | 2.2 |  | Y |  | > 0% AND < 20% |  |  | <<add explanation text displayed>> |  |
|  | 2.3 |  | R |  | >= 20% |  |  | <<add explanation text displayed>> |  |
|  | 3.1 |  | G |  | ≤ $0 |  |  | <<add explanation text displayed>> |  |
|  | 3.2 |  | Y |  | >$0AND<$1M |  |  | <<add explanation text displayed>> |  |
|  | 3.3 |  | R |  | >=$1M |  |  | <<add explanation text displayed>> |  |
|  | 4.1 |  | G |  | ≤ $0 |  |  | <<add explanation text displayed>> |  |
|  | 4.2 |  | Y |  | > 0% AND < 10%, OR < $5 |  |  | <<add explanation text displayed>> |  |
|  |  |  |  |  | M |  |  |  |  |
|  | 4.3 |  | R |  | >= 10%, OR >= $5 M |  |  | <<add explanation text displayed>> |  |
|  |  |  | Table 9: Development On-Budget Status Explanation |  |  |

| VDOT Dashboard 4.0 User Guide | 31 |
| --- | --- |

Delivery On-Time

The technical details for the business rules that govern the Delivery On-Time performance measure are provided below. The business rules assume an understanding of this data is maintained and managed in the representative source systems and the Data Warehouse.

Detailed Logic

- Project Selection:

1.1. Same selection as it is ‘today’ (Fiscal year)

- Prior to completion, all milestones will be flagged for being at risk (Yellow) 14 calendar days prior to an original milestone completion date, and remain yellow until 7 calendar days after. Beyond 7 calendar days, the milestone activity would be red.

2.1. IF Actual Completion = null:

2.1.1. IF Today < (Original Milestone Completion -14 calendar days), THEN Status = Green

2.1.2. IF Today > (Original Milestone Completion -14 calendar days) AND Today < Original Milestone Completion, THEN Status = Yellow (early)

2.1.3. IF Today > Original Milestone Completion AND Today < Original Milestone Completion +7 calendar days), THEN Status = Yellow

2.1.4. IF Today > (Original Milestone Completion +7 calendar days), THEN Status = Red

- Once completed, IF the milestone was completed on or before the “Original Milestone Completion Date”, THEN milestone will be green. IF it was completed within 7 calendar days after the milestone, THEN the status will be yellow. IF it was completed more than 7 calendar days late, THEN the status will be red.

3.1. IF Actual Completion ≠ null:

3.1.1. IF Actual Completion < Original Milestone Completion, THEN Status

- Green. Allows for different explanations when ‘<’ versus ‘=’ for the Original Milestone Completion.

3.1.2. IF Actual Completion > Original Milestone Completion AND Actual Completion < (Original Milestone Completion +7), THEN Status = Yellow

3.1.3. IF Actual Completion > (Original Milestone Completion +7), THEN Status = Red

| VDOT Dashboard 4.0 User Guide | 32 |
| --- | --- |

3.1.4. Overall project score is the score of the most recently completed Milestone

- The “Original Completion Date” is the contractual completion date for delivery established upon contract award, and the “Current Completion Date” is the estimated contract completion.

4.1. IF Construction Contract Accepted Date = null:

4.1.1. IF Today or Current Completion Date < (Original Completion Date - 14 calendar days), THEN Status = Green

4.1.2. IF Today or Current Completion Date > (Original Completion Date - 14 calendar days) AND ‘today’ OR Current Completion Date < Original Completion Date, THEN Status = Yellow (early)

4.1.3. IF Today or Current Completion Date > Original Completion Date AND ‘today’ or Current Completion Date < Original Completion Date +7 calendar days), THEN Status = Yellow

4.1.4. IF Today or Current Completion Date > (Original Completion Date +7 calendar days), THEN Status = Red

4.2. IF Construction Contract Accepted Date ≠ null:

4.2.1. IF Construction Contract Accepted Date < Original Completion Date, THEN Status = Green. Allows for different explanations when ‘<’ versus ‘=’ for the Original Completion Date.

4.2.2. IF Construction Contract Accepted Date > (Original Completion Date), THEN Status = Red

- IF there is missing critical data, THEN Red

5.1. IF Description ≠ null, AND Original Completion Date = null, THEN Status = Red

5.2. IF Today > (Activity 84 Actual Date (this is Contract Execution) + 90), AND Description = null, AND Original Number of Days Allowed >180 days, Status = Yellow

5.3. IF Description ≠ null, AND Original Milestone Completion =null, THEN Status = Red

- Overall Project Score – sets the priority for applying business rules #2 through #5 – the worst case RYG status of the following:

6.1. IF BR #5.1= Red, THEN Red,

6.2. IF BR #5.2 = Red, THEN Red,

6.3. ELSE IF Construction Contract Accepted Date ≠ null, THEN follow BR #4.2

6.4. ELSE IF Construction Contract Accepted Date = null, THEN follow the worst score of:

6.4.1.BR #4.1

| VDOT Dashboard 4.0 User Guide | 33 |
| --- | --- |

6.4.2. BR #3.1 for the milestone with the most recent Actual Completion date

6.4.3. BR #2.1 for the next milestone based on the Original Milestone Completion date

The table below provides a cross reference between the detailed business rules, the schedule, and the status indicator colors.

Business Rule #

Early Finish

On-time

Late Finish

Prior to

Completion (2.1)

Once Milestone Completed (3.1)

Once Contract Accepted (4.2)

Prior to Contract

Accepted (4.1)

|  |  |  |  | Original Milestone |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| < -14 days |  | ≥ -14 days ≤ 0 |  |  |  | > 0 ≤ 7 days |  | > 7 days |
|  |  |  |  | Completion |  |  |  |  |
| ≤ 0 days |  | Original Milestone |  | ≤ 7 days |  | > 7 days |
|  |  | Completion |  |  |  |  |
| ≤ 0 days |  | Original |  | > 0 days |
|  |  | Completion Date |  |  |
| < -14 days |  | ≥ -14 days ≤ 0 |  | Original |  | > 0 ≤ 7 days |  | > 7 days |
|  |  |  |  | Completion Date |  |  |  |  |

* All days are “Calendar Days”

Table 10: Delivery On-Time Cross Reference

| VDOT Dashboard 4.0 User Guide | 34 |
| --- | --- |

Explanations

For the applicable business rules, an explanation of the reason for the status is provided in the table below.

| Business |  | Delivery |  | Days |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | On-Time |  |  |  | Delivery On-Time Status Explanation |
| Rule |  |  |  | Variance |  |  |
|  |  | Status |  |  |  |  |
| 5.1 |  | R |  | - |  | Red on-time status: ' ¦¦ '"' ¦¦ '"' ¦¦ milestone_desc ¦¦ '"' ¦¦ '"' ¦¦ ' |
|  |  |  |  |  |  | milestone missing critical data' |
| 5.2 |  | Y |  | - |  | Yellow on-time status: ' ¦¦ '"' ¦¦ milestone_desc ¦¦ '"' ¦¦ ' milestone |
|  |  |  |  |  |  | missing critical data' |
|  |  |  |  |  |  | Red on-time status: Today or Current Contract Completion date is ' |
| 4.1 |  | R |  | > 7 |  | ¦¦ contract_days_variance ¦¦ ' days later than the Original Contract |
|  |  |  |  |  |  | Completion Date' |
| 4.1 |  | Y |  | BETWEEN |  | Yellow on-time status: Today or Current Contract Completion date is |
|  |  |  |  | 1 and 7 |  | ' ¦¦ contract_days_variance ¦¦ ' days later than the Original |
|  |  |  |  |  |  | Contract Completion Date' |
|  |  |  |  |  |  | Early Yellow on-time status: Today or Current Contract Completion |
| 4.1 |  | Y |  | BETWEEN |  | date is ' ¦¦ contract_days_variance ¦¦ ' days prior to the Original |
|  |  |  |  | -14 and 0 |  | Contract completion date and may be at risk of meeting this Original |
|  |  |  |  |  |  | Contract Completion Date' |
|  |  |  |  |  |  | Green on-time status: Today or Current Contract Completion date is |
| 4.1 |  | G |  | < -14 |  | ' ¦¦ contract_days_variance ¦¦ ' days prior to the Original Contract |
|  |  |  |  |  |  | Completion Date' |
|  |  |  |  |  |  | Red on-time status: Contract Accepted Date is ' ¦¦ |
| 4.2 |  | R |  | > 0 |  | contract_days_variance ¦¦ ' days after the Original Contract |
|  |  |  |  |  |  | Completion Date ' |
|  |  |  |  |  |  | Green on-time status: Contract Accepted Date is ' ¦¦ |
| 4.2 |  | G |  | < 0 |  | contract_days_variance ¦¦ ' days before the Original Contract |
|  |  |  |  |  |  | Completion Date ' |
| 4.2 |  | G |  | 0 |  | Green on-time status: Contract Accepted Date is the same as the |
|  |  |  |  |  |  | Original Contract Completion date' |
|  |  |  |  |  |  | Red on-time status: ' ¦¦ '"' ¦¦ milestone_desc ¦¦ '"' ¦¦ ' completed' |
| 3.1 |  | R |  | > 7 |  | ¦¦ milestone_days_variance ¦¦ ' days past the expected completion |
|  |  |  |  |  |  | date' |

| VDOT Dashboard 4.0 User Guide | 35 |
| --- | --- |

3.1

3.1

3.1

2.1

2.1

2.1

2.1

Y

G

G

R

Y

Y

G

BETWEEN

1 and 7

- 0

0

> 7

BETWEEN

1 and 7

BETWEEN -14 and 0

< -14

Yellow on-time status: ' || '"' || milestone_desc || '"' || ' completed' || milestone_days_variance || ' days past the expected completion date'

Green on-time status: ' || '"' || milestone_desc || '"' || ' completed' || milestone_days_variance || ' days early'

Green on-time status: ' || '"' || milestone_desc || '"' || '

completed on time'

Red on-time status: ' || '"' || milestone_desc || '"' || ' is ' || milestone_days_variance || ' days behind schedule'

Yellow on-time status: ' || '"' || milestone_desc || '"' || ' is ' || milestone_days_variance ||' days behind schedule'

Early Yellow on-time status: ' || '"' || milestone_desc || '"' || ' is '

- milestone_days_variance || ' days ahead of scheduled date and may be at risk of meeting the expected completion date'

Green on-time status: ' || '"' || milestone_desc || '"' || ' is ' || milestone_days_variance || ' days ahead of schedule'

Table 11: Delivery On-Time Status Explanation

Delivery On-Budget

The technical details for the business rules that govern the Delivery On Budget performance measure are provided below. The business rules assume an understanding of this data is maintained and managed in the representative source systems and the Data Warehouse.

Detailed Logic

Contract on-budget metrics are calculated by comparing the Original Contract Award Amount to the Current Contract Amount and Cost of Work to Date.

- Project Selection:

1.1. Exclude Category ‘M’ Projects

- For active contracts and up to 35 days after Acceptance, Original Contract Amount is compared to the Cost of Work To Date and Current Contract Amount.

2.1. IF Today < (Construction Contract Accepted + 35 calendar days) OR Construction Contract Accepted Date = null

| VDOT Dashboard 4.0 User Guide | 36 |
| --- | --- |

2.1.1. IF Cost of Work to Date < (Original Contract Award Amount +3%) AND Current Contract Amount < (Original Contract Award Amount +3%), THEN Status = Green

2.1.2. IF Cost of Work to Date > (Original Contract Award Amount +3%) AND Cost of Work to Date < (Original Contract Award Amount +10%), OR IF Current Contract Amount > (Original Contract Award Amount +3%) AND Current Contract Amount < (Original Contract Award Amount +10%), THEN Status = Yellow

2.1.3. IF Cost of Work to Date > (Original Contract Award Amount +10%) OR Current Contract Amount > (Original Contract Award Amount +10%), THEN Status = Red

- For completed contracts 35 days after Acceptance with un-audited final costs, metrics are calculated with different thresholds eliminating the yellow band:

3.1. IF Construction Contract Accepted Date ≠ null AND Today > (Construction Contract Accepted Date +35 calendar days)

3.1.1. IF Cost of Work To Date < (Original Contract Award Amount +10%) AND Current Contract Amount < (Original Contract Award Amount +10%), THEN Status = Green

3.1.2. IF Cost of Work to Date > (Original Contract Award Amount +10%) OR Current Contract Amount > (Original Contract Award Amount +10%), THEN Status = Red

- IF there is missing critical data, THEN Status = Red

4.1. IF Cost of Work to Date = null, OR Original Contract Award Amount = null, OR Original Completion Date = null, OR Current Contract Amount = null, THEN Status = Red

- Overall Project Score – sets the priority for applying business rules #2 through #4 – the worst case RYG status of the following:

5.1. IF BR #4.1= Red, THEN Red,

5.2. ELSE IF Construction Contract Accepted Date ≠ null AND Today > (Construction Contract Accepted Date +35 calendar days)

5.2.1. Project Score follows BR #3.

5.3. ELSE IF Today < (Construction Contract Accepted + 35 calendar days) OR Construction Contract Accepted Date = null

5.3.1. Project Score follows BR #2

|  | Standard Projects |  | Base Cost |  | Amount Over Original Contract Award Amount |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Active and Completed up to 35 |  |  |  | <3% |  | >3% and <10% |  |  | >10% |  |
|  | days after Acceptance |  | Original Contract |  |  |  |  |  |  |  |  |
|  |  |  | Award Amount |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Completed with Final Voucher |  |  |  | <10% |  | >10% |  |  |

Table 12: Delivery On-Budget Logic

| VDOT Dashboard 4.0 User Guide | 37 |
| --- | --- |

Explanations

For the applicable business rules, an explanation of the reason for the status is provided in the table below.

Business

Rule

Delivery On-Time Status

Budget

Variance

Delivery On-Time Status Explanation

|  |  |  |  |  |  |  |  | Red on-budget status: Missing critical contract data (Cost of |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 4.1 |  | R |  |  |  |  | Work to Date; Original Contract Award Amount; Original |  |
|  |  |  |  |  |  |  |  | Completion Date; Current Contract Amount |  |
|  |  |  |  |  |  |  |  | Completed Projects: Red on-budget status - Contract more than |  |
|  |  |  |  |  |  |  |  | 10% over the Original Contract Award Amount |  |
|  | 3.1.2 |  | R |  |  | > 10% |  |  |  |
|  |  |  |  |  |  |  |  | Red on-budget status: Completed project with contract more |  |
|  |  |  |  |  |  |  |  | than 10% over the Original Contract Award Amount |  |
|  |  |  |  |  |  |  |  | Completed Projects: Green on-budget status- Contract less than |  |
|  |  |  |  |  |  |  |  | or equal to 10% of Original Contract Award Amount |  |
|  | 3.1.1 |  | G |  |  | <= 10% |  |  |  |
|  |  |  |  |  |  |  |  | Green on-budget status: Completed project with contract less |  |
|  |  |  |  |  |  |  |  | than or equal to 10% of Original Contract Award Amount |  |
|  |  |  |  |  |  |  |  | Active Projects: Red on-budget status - Contract more than 10% |  |
|  |  |  |  |  |  |  |  | of the Original Contract Award Amount |  |
|  | 2.1.3 |  | R |  |  | > 10% |  |  |  |
|  |  |  |  |  |  |  |  | Red on-budget status: Active project with contract more than |  |
|  |  |  |  |  |  |  |  | 10% of the Original Contract Award Amount |  |
|  |  |  |  |  |  |  |  | Active Projects: Yellow on-budget status - Contract over more |  |
|  |  |  |  |  |  |  |  | than 3% and less than or equal to 10% of the Original Contract |  |
|  |  |  |  |  |  | >3%<= |  | Award Amount |  |
|  | 2.1.2 |  | Y |  |  |  |  |  |  |
|  |  |  |  |  |  | 10% |  |  |  |
|  |  |  |  |  |  |  |  | Yellow on-budget status: Active project with contract over more |  |
|  |  |  |  |  |  |  |  | than 3% and less than or equal to 10% of the Original Contract |  |
|  |  |  |  |  |  |  |  | Award Amount |  |
|  |  |  |  |  |  |  |  | Active Projects: Green on-budget status - Contract less than or |  |
|  |  |  |  |  |  |  |  | equal to 3% of the Original Contract Award Amount |  |
|  | 2.1.1 |  | G |  |  | <= 3% |  |  |  |
|  |  |  |  |  |  |  |  | Green on-budget status: Active project with contract less than or |  |
|  |  |  |  |  |  |  |  | equal to 3% of the Original Contract Award Amount |  |
|  |  |  |  | Table 13: Delivery On-Time Status Explanations |  |

| VDOT Dashboard 4.0 User Guide | 38 |
| --- | --- |

Project Baselines

For the projects in the representative Fiscal Year the activity schedule and project budget data are baselined on specific criteria based upon date fields that are used to maintain and manage the data in the representative source systems and/or the Data Warehouse. The information provided is technical and assumes an understanding of project data.

Detailed Logic

/// This rule locks the scheduled dates for ‘Activity Codes’ 10, 12, 22 for Smart

Scale 2017 and 2018 projects as of a specific date. This rule also locks UPC’s that are exceptions to the rule.

- IF Smart Scale Cohort < 2019, THEN for Activity Codes (10, 12, 22)…

- SET ‘Baseline Begin Date’ = ‘Latest Begin Date’ AND SET ‘Baseline End Date’ = ‘Latest End Date’ AND SET the ‘Date’ as…

  - CASE IF Smart Scale Cohort FY2017, THEN ‘Date’ is 01/20/2017 ///

Administrative date for FY2017

  - CASE IF Smart Scale Cohort FY2018, THEN ‘Date’ is 07/26/2017 ///

Administrative date for FY2018

  - CASE IF UPC is an ‘exception’, THEN SET ‘Date’ as…

    - 104957, 7/26/2017 /// specific Smart Scale project exception

    - 111753, 7/26/2017 /// specific Smart Scale project exception

    - 111883, 7/26/2017 /// DRPT Smart Scale project exception

    - 111881, 7/26/2017 /// DRPT Smart Scale project exception

    - 110806, 7/26/2017 /// DRPT Smart Scale project exception

    - 111886, 7/26/2017 /// DRPT Smart Scale project exception

    - 111882, 7/26/2017 /// DRPT Smart Scale project exception

    - 111885, 7/26/2017 /// DRPT Smart Scale project exception

    - 111884, 7/26/2017 /// DRPT Smart Scale project exception

    - 109942, 7/26/2017 /// DRPT Smart Scale project exception

    - 111654, 7/26/2017 /// DRPT Smart Scale project exception

    - 111672, 7/26/2017 /// DRPT Smart Scale project exception

    - 109289, 7/26/2017 /// DRPT Smart Scale project exception

    - 109541, 7/26/2017 /// DRPT Smart Scale project exception

    - 109749, 7/26/2017 /// DRPT Smart Scale project exception

    - 111656, 7/26/2017 /// DRPT Smart Scale project exception

    - 111660, 7/26/2017 /// DRPT Smart Scale project exception

| VDOT Dashboard 4.0 User Guide | 39 |
| --- | --- |

    - 110542, 7/26/2017 /// DRPT Smart Scale project exception

    - 111662, 7/26/2017 /// DRPT Smart Scale project exception

    - 109800, 7/26/2017 /// DRPT Smart Scale project exception

    - 111879, 7/26/2017 /// DRPT Smart Scale project exception

    - 111653, 7/26/2017 /// DRPT Smart Scale project exception

    - 111880, 7/26/2017 /// DRPT Smart Scale project exception

    - 111658, 7/26/2017 /// DRPT Smart Scale project exception

    - 109801, 7/26/2017 /// DRPT Smart Scale project exception

    - 99712, 7/26/2017 /// DRPT Smart Scale project exception

  - This rule applies to Smart Scale Projects NOT in 2017 or 2018 that may still reside in iPM

- ELSE IF Smart Scale Cohort > 2019 OR Smart Scale Cohort IS NULL) AND

IN_PWA <> 1, THEN for Activity Codes (10, 12, 22)…

  - This rule sets the date as the ‘system date’. This date may be formally established (e.g., 9/1)

SET ‘Date’ as ‘SYS DATE’

  - This rule applies to Smart Scale Projects that are ‘in’ PWA for post Activity

22 activities.

- ELSE IF Smart Scale Cohort < 2019 AND IN_PWA = 1, THEN for Activity Codes (47, 49, 52, 67U, 69, 70, 80, 84)…

        - This rule sets the date logic only

      - SET ‘Baseline Begin Date’ = ‘Latest Begin Date’ AND SET ‘Baseline End Date’ = ‘Latest End Date’

  - This rule applies to Smart Scale Projects that are ‘in’ PWA for post Activity

22 activities.

- ELSE IF Smart Scale Cohort < 2019 AND IN_PWA <> 1, THEN for Activity Codes (47, 49, 52, 67U, 69, 70, 80, 84)…

        - This rule allows the scheduled dates for post-Activity 22 Codes scheduled dates to fluctuate if the ‘Actual End Date’ for ‘Activity Code’ (22) is not populated

      - WHERE ‘DW Effective End Date’ IS NULL and Activity Code (22) ‘Actual End Date’ IS NULL,

SET ‘Baseline Begin Date’ = ‘Latest Begin Date’ AND SET ‘Baseline End Date’ = ‘Latest End Date’

| VDOT Dashboard 4.0 User Guide | 40 |
| --- | --- |

      - This uses the date that the ‘Actual Date’ was entered into the system to lock the scheduled dates for post-Activity 22 scheduled dates. For this rule, ONLY the ‘date’ and NOT the ‘time’ for ‘Last Modified Date’ is used in the ‘less than or equal to’ comparison. In this way, the comparison will catch transactions that occur on the same day, whereas including the ‘time’ would exclude transactions that are separated by seconds, which is not desired. A review of the timestamp data revealed that editors do edit multiple data values within the same editing session where the edit to Activity 22 is not the last edit made when looking at the time (HH:MM:SS).

    - WHERE ‘DW Effective End Date’ IS NULL and Activity Code (22) ‘Actual End Date’ IS NOT NULL, exclude the activity without a record with NULL ‘DW Effective End Date’, THEN SET ‘Baseline Begin Date’ = ‘Latest Begin Date’ AND SET ‘Baseline End Date’ = ‘Latest End Date’ WHERE ‘Last Modified Date’ <= ‘Last Modified Date’ of the ‘Actual End Date’ for Activity (22). SELECT the record with the MAX ‘Last Modified Date’. IF there are multiple records of an activity that share the same ‘Last Modified Date’, SELECT the one with MAX ‘DW Effective Begin Date’.

  - This rule applies to future Smart Scale Projects that are ‘in’ PWA for post Activity 22 activities.

- ELSE IF (Smart Scale Cohort > 2019 OR Smart Scale Cohort IS NULL) AND

IN_PWA = 1, THEN for Activity Codes (10, 12, 22, 47, 49, 52, 67U, 69, 70, 80,

84)…

      - This rule sets the date logic only

    - SET ‘Baseline Begin Date’ = ‘Latest Begin Date’ AND SET ‘Baseline End Date’ = ‘Latest End Date’

  - This rule applies to future Smart Scale Projects that are NOT ‘in’ PWA for post Activity 22 activities.

- ELSE IF (Smart Scale Cohort > 2019 OR Smart Scale Cohort IS NULL) AND IN_PWA <> 1, THEN for Activity Codes (47, 49, 52, 67U, 69, 70, 80, 84)…

      - This rule allows the scheduled dates for post-Activity 22

Codes scheduled dates to fluctuate if the ‘Actual End Date’ for ‘Activity Code’ (22) is not populated

| VDOT Dashboard 4.0 User Guide | 41 |
| --- | --- |

- WHERE ‘DW Effective End Date’ IS NULL and Activity Code

(22) ‘Actual End Date’ IS NULL,

SET ‘Baseline Begin Date’ = ‘Latest Begin Date’ AND SET

‘Baseline End Date’ = ‘Latest End Date’

/// This uses the date that the ‘Actual Date’ was entered into the system to lock the scheduled dates for post-Activity 22 scheduled dates. For this rule, ONLY the ‘date’ and NOT the ‘time’ for ‘Last Modified Date’ is used in the ‘less than or equal to’ comparison. In this way, the comparison will catch transactions that occur on the same day, whereas including the ‘time’ would exclude transactions that are separated by seconds, which is not desired. A review of the timestamp data revealed that editors do edit multiple data values within the same editing session where the edit to Activity 22 is not the last edit made when looking at the time (HH:MM:SS).

- WHERE ‘DW Effective End Date’ IS NULL and Activity Code (22) ‘Actual End Date’ IS NOT NULL, exclude the activity without a record with NULL ‘DW Effective End Date’, THEN SET ‘Baseline Begin Date’ = ‘Latest Begin Date’ AND SET ‘Baseline End Date’ = ‘Latest End Date’ WHERE ‘Last Modified Date’ <= ‘Last Modified Date’ of the ‘Actual End Date’ for Activity (22). SELECT the record with the MAX ‘Last Modified Date’. IF there are multiple records of an activity that share the same ‘Last Modified Date’, SELECT the one with MAX ‘DW Effective Begin Date’.

| VDOT Dashboard 4.0 User Guide | 42 |
| --- | --- |

Data Mapping

The details for data mapping applied to Design/Built Projects and DRPT Projects are described below. The details are technical in nature and describe the crosswalk of data between the VDOT defined activity codes and the tracking sheet activities.

Development On-Time

The technical details for the activity crosswalk for Design/Build Projects and DRPT Projects are detailed below. The business rules assume an understanding of this data that is maintained and managed in the representative source systems and the Data Warehouse.

Design/Build Projects

A crosswalk of the design/build activity code to the tracking sheet activity is provided in the table below.

| Design/Build |  | Description |  | Tracking Sheet |  |
| --- | --- | --- | --- | --- | --- |
| Activity Code |  |  |  | Activity |  |
| 347 |  | Escrow Submission |  | 47 |  |
| 352 |  | Design Build RW and CN fund verification |  | 52 |  |
| 380 |  | Concurrence letter for RFP release |  | 80 |  |
| 384 |  | CTB approval/Award |  | 84 |  |
|  |  | Table 14: Design/Build Activity Crosswalk |  |  |  |

| VDOT Dashboard 4.0 User Guide | 43 |
| --- | --- |

DRPT Projects

A crosswalk of the DRPT activity code to the Dashboard 4.0 tracking activity is provided in the table below.

| DRPT Activity Code |  | Description |  | Dashboard 4.0 Tracking Activity |  |
| --- | --- | --- | --- | --- | --- |
| 110 |  | Grant Award |  | 10 |  |
| 112 |  | Authorize DRPT Funds |  | 12 |  |
| 122 |  | Scope DRPT Project |  | 22 |  |
| 180 |  | RFP /Advertisement |  | 80 |  |
|  |  | Table 15: DRPT Activity Crosswalk |  |  |  |

Data Field Cross Reference

The table below provides a data field cross reference mapping from what is displayed on the dashboard user interface, through the intermediary data objects (tables, views, materialized views), and into VDOT’s Data Warehouse. The data in the Data Warehouse that is depicted on the Dashboard is refreshed from the various source systems of record on a nightly basis. Business logic is then applied to the data in the intermediary data objects. The intermediary data objects are extracted into CSV files. The CSV files are the source of data for the Dashboard 4 application. Not all data fields are depicted in the user interface.

| VDOT Dashboard 4.0 User Guide | 44 |
| --- | --- |

|  | VDOT |  |  |  |  |  | VDOT |  |  | Dashboard |  |  | DashboardM |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CSV |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DashboardMart |  |  |  |  |
|  |  |  |  | VDOT CSV File |  |  | DasboardMar |  |  | Mart View |  |  | art Data |  |  |  |  |  | Datawarehouse Source Data Object |  |
|  | Field |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Field Name |  |  |  |  |
|  |  |  |  |  |  |  | t View |  |  | Field Name |  |  | Object |  |  |  |  |  |  |  |
|  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | CONTR | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | CONTRACT |  | MV_CONTRA |  |  |  |  | ODS.CONTRACT_MILESTONE, ODS.LAD_CONTRACT_MILESTONES, |
|  |  |  |  | CNTRCT_MLS |  |  |  | CT_MILESTON |  | CONTRACT_ID |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | ACT_ID | elivery_Milestone |  |  |  | _ID |  |  |  |  |  |  |
|  |  |  |  | TN |  |  |  | ES |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM |
|  | MLSTN_ | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | MLSTN_CO |  | MV_CONTRA |  | MILESTONE_CO |  | ODS.CONTRACT_MILESTONE, ODS.LAD_CONTRACT_MILESTONES, |
|  |  |  |  | CNTRCT_MLS |  |  |  | CT_MILESTON |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | CODE | elivery_Milestone |  |  |  | DE |  |  |  | DE |  |  |
|  |  |  |  | TN |  |  |  | ES |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM |
|  | MLSTN_ | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | MLSTN_DE |  | MV_CONTRA |  | MILESTONE_DE |  | ODS.CONTRACT_MILESTONE, ODS.LAD_CONTRACT_MILESTONES, |
|  |  |  |  | CNTRCT_MLS |  |  |  | CT_MILESTON |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | DESC | elivery_Milestone |  |  |  | SC |  |  |  | SC |  |  |
|  |  |  |  | TN |  |  |  | ES |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM |
|  | ORIG_S |  |  |  |  | V_PRJ_DLVR_ |  | ORIG_SPCF |  | MV_CONTRA |  |  |  |  | ODS.CONTRACT_MILESTONE, ODS.LAD_CONTRACT_MILESTONES, |
|  | PCFD_C | Dashboard_Project_D |  |  |  |  |  |  |  | ORIG_SPCFD_C |  |  |
|  |  |  |  | CNTRCT_MLS |  | D_CMPLTN |  | CT_MILESTON |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | MPLTN | elivery_Milestone |  |  |  |  |  |  |  | MPLTN_DT |  |  |
|  |  |  |  | TN |  | _DT |  | ES |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM |
|  | _DT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ACTUAL |  |  |  |  | V_PRJ_DLVR_ |  | ACTUAL_SP |  | MV_CONTRA |  |  |  |  | ODS.CONTRACT_MILESTONE, ODS.LAD_CONTRACT_MILESTONES, |
|  | _SPCFD | Dashboard_Project_D |  |  |  |  |  |  |  | ACTUAL_SPCFD |  |  |
|  |  |  |  | CNTRCT_MLS |  | CFD_CMPL |  | CT_MILESTON |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | _CMPLT | elivery_Milestone |  |  |  |  |  |  |  | _CMPLTN_DT |  |  |
|  |  |  |  | TN |  | TN_DT |  | ES |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM |
|  | N_DT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ORIG_N |  |  |  |  | V_PRJ_DLVR_ |  | ORIG_NBR |  | MV_CONTRA |  |  |  |  | ODS.CONTRACT_MILESTONE, ODS.LAD_CONTRACT_MILESTONES, |
|  | BR_DAY | Dashboard_Project_D |  |  |  |  |  |  |  | ORIG_NBR_DAY |  |  |
|  |  |  |  | CNTRCT_MLS |  | _DAYS_ALL |  | CT_MILESTON |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | S_ALLO | elivery_Milestone |  |  |  |  |  |  |  | S_ALLOWED |  |  |
|  |  |  |  | TN |  | OWED |  | ES |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM |
|  | WED |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | LATEST |  |  |  |  | V_PRJ_DLVR_ |  | LATEST_CL |  | MV_CONTRA |  |  |  |  | ODS.CONTRACT_MILESTONE, ODS.LAD_CONTRACT_MILESTONES, |
|  | _CLOSE | Dashboard_Project_D |  |  |  |  |  |  |  | LATEST_CLOSED |  |  |
|  |  |  |  | CNTRCT_MLS |  | OSED_MLS |  | CT_MILESTON |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | D_MLST | elivery_Milestone |  |  |  |  |  |  |  | _MILESTONE |  |  |
|  |  |  |  | TN |  | TN |  | ES |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM |
|  | N |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | DEL_OT | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | DEL_OT_V |  | MV_CONTRA |  | DELIVERY_ON_T |  | ODS.CONTRACT_MILESTONE, ODS.LAD_CONTRACT_MILESTONES, |
|  | _VARIA |  |  | CNTRCT_MLS |  |  |  | CT_MILESTON |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  |  | elivery_Milestone |  |  |  | ARIANCE |  |  |  | IME_VARIANCE |  |  |
|  | NCE |  |  | TN |  |  |  | ES |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM |
|  | DEL_OT | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | DEL_OT_ST |  | MV_CONTRA |  | DELIVERY_ON_T |  | ODS.CONTRACT_MILESTONE, ODS.LAD_CONTRACT_MILESTONES, |
|  | _STATU |  |  | CNTRCT_MLS |  |  |  | CT_MILESTON |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  |  | elivery_Milestone |  |  |  | ATUS |  |  |  | IME_STATUS |  |  |
|  | S |  |  | TN |  |  |  | ES |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM |
|  | DEL_OT | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | DEL_OT_EX |  | MV_CONTRA |  | DELIVERY_ON_T |  | ODS.CONTRACT_MILESTONE, ODS.LAD_CONTRACT_MILESTONES, |
|  | _EXPLA |  |  | CNTRCT_MLS |  |  |  | CT_MILESTON |  | IME_EXPLANATI |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  |  | elivery_Milestone |  |  |  | PLANATION |  |  |  |  |  |  |
|  | NATION |  |  | TN |  |  |  | ES |  | ON |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM |
|  | DEL_OT | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | DEL_OT_EA |  | MV_CONTRA |  | DELIVERY_ON_T |  | ODS.CONTRACT_MILESTONE, ODS.LAD_CONTRACT_MILESTONES, |
|  | _EARLY |  |  | CNTRCT_MLS |  |  |  | CT_MILESTON |  | IME_EARLY_WA |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  |  | elivery_Milestone |  |  |  | RLY_WARN |  |  |  |  |  |  |
|  | _WARN |  |  | TN |  |  |  | ES |  | RN |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM |
|  | DEL_OT | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | DEL_OT_CR |  | MV_CONTRA |  | DELIVERY_ON_T |  | ODS.CONTRACT_MILESTONE, ODS.LAD_CONTRACT_MILESTONES, |
|  | _CRIT_F |  |  | CNTRCT_MLS |  |  |  | CT_MILESTON |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  |  | elivery_Milestone |  |  |  | IT_FLG |  |  |  | IME_CRIT_FLG |  |  |
|  | LG |  |  | TN |  |  |  | ES |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM |

| VDOT Dashboard 4.0 User Guide | 0 |
| --- | --- |

|  | VDOT |  |  |  |  |  | VDOT |  |  | Dashboard |  |  | DashboardM |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CSV |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DashboardMart |  |  |  |  |
|  |  |  |  | VDOT CSV File |  |  | DasboardMar |  |  | Mart View |  |  | art Data |  |  |  |  |  | Datawarehouse Source Data Object |  |
|  | Field |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Field Name |  |  |  |  |
|  |  |  |  |  |  |  | t View |  |  | Field Name |  |  | Object |  |  |  |  |  |  |  |
|  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | DEL_OT | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | DEL_OT_PR |  | MV_CONTRA |  | DELIVERY_ON_T |  | ODS.CONTRACT_MILESTONE, ODS.LAD_CONTRACT_MILESTONES, |
|  | _PRJ_P |  |  | CNTRCT_MLS |  |  |  | CT_MILESTON |  | IME_PRJ_PRIORI |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  |  | elivery_Milestone |  |  |  | J_PRIORITY |  |  |  |  |  |  |
|  | RIORITY |  |  | TN |  |  |  | ES |  | TY |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM |
|  |  |  | Dashboard_Project_D |  | V_PRJ_DLVR_ |  |  |  |  | MV_CONTRA |  |  |  |  | ODS.CONTRACT_MILESTONE, ODS.LAD_CONTRACT_MILESTONES, |
|  | SOURCE |  |  | CNTRCT_MLS |  | SOURCE |  | CT_MILESTON |  | SOURCE |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  |  | elivery_Milestone |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | TN |  |  |  |  | ES |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM |
|  | CONTR | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | CONTRACT |  | MV_CONTRA |  |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  |  |  |  |  |  |  |  |  |  | CONTRACT_ID |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  | ACT_ID | elivery |  | CNTRCT |  | _ID |  | CTS |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | VENDO | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | VENDOR_N | MV_CONTRA |  | VENDOR_NUMB |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  |  |  |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  | R_NBR | elivery |  | CNTRCT |  | BR |  | CTS |  | ER |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | VENDO | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | VENDOR_N |  | MV_CONTRA |  |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | R_NAM |  |  |  |  |  |  |  |  | VENDOR_NAME |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | AME |  | CTS |  |  |  |  |
|  | E |  |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | CN_CNT | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | CN_CNTRC |  | MV_CONTRA |  | CN_CONTRACT_ |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | RCT_TY |  |  |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | T_TYPE |  | CTS |  | TYPE |  |  |
|  | PE |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | CN_CNT |  |  |  |  |  |  |  | CN_CNTRC |  |  |  |  |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | RCT_TY | Dashboard_Project_D |  | V_PRJ_DLVR_ |  |  |  | MV_CONTRA |  | CN_CONTRACT_ |  |  |
|  |  |  |  |  |  | T_TYPE_DE |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  | PE_DES | elivery |  | CNTRCT |  |  |  | CTS |  | TYPE_DESC |  |  |
|  |  |  |  |  |  | SC |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | C |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | CN_CNT | Dashboard_Project_D | V_PRJ_DLVR_ |  | CN_CNTRC |  | MV_CONTRA |  | CN_CONTRACT_ |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | RCT_TY |  |  |  | T_TYPE_AG |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  |  |  | CTS |  | TYPE_AGG |  |  |
|  | PE_AGG |  |  |  |  | G |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | CS_ORI |  |  |  |  |  |  |  | CS_ORIG_S |  |  |  |  |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | G_SPCF | Dashboard_Project_D | V_PRJ_DLVR_ |  |  |  | MV_CONTRA |  | CS_ORGI_SPCFD |  |  |
|  |  |  |  |  | PCFD_CMP |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  | D_CMP | elivery |  | CNTRCT |  |  |  | CTS |  | _CMPLTN_DT |  |  |
|  |  |  |  |  |  | LTN_DT |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | LTN_DT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | CN_DAT | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | CN_DATE_ |  | MV_CONTRA |  | CN_DATE_OF_D |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | E_OF_D |  |  |  |  | OF_DEFAU |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  |  |  | CTS |  | EFAULT |  |  |
|  | EFAULT |  |  |  |  | LT |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | CN_CNT | Dashboard_Project_D | V_PRJ_DLVR_ |  | CN_CNTRC |  | MV_CONTRA |  | CN_CONTRACT_ |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | RCT_EX |  |  |  | T_EXCTN_D |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  |  |  | CTS |  | EXCTN_DT |  |  |
|  | CTN_DT |  |  |  |  | T |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | CNTRCT | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | CNTRCTR_ |  | MV_CONTRA |  | CONTRACTOR_D |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | R_DFLT |  |  |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | DFLT_DT |  | CTS |  | EFAULT_DATE |  |  |
|  | _DT |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | TYPE_O | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | TYPE_OF_ |  | MV_CONTRA |  |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | F_WOR |  |  |  |  |  |  |  |  | TYPE_OF_WORK |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | WORK |  | CTS |  |  |  |  |
|  | K |  |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |

| VDOT Dashboard 4.0 User Guide | 1 |
| --- | --- |

|  | VDOT |  |  |  |  |  | VDOT |  |  | Dashboard |  |  | DashboardM |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CSV |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DashboardMart |  |  |  |  |
|  |  |  |  | VDOT CSV File |  |  | DasboardMar |  |  | Mart View |  |  | art Data |  |  |  |  |  | Datawarehouse Source Data Object |  |
|  | Field |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Field Name |  |  |  |  |
|  |  |  |  |  |  |  | t View |  |  | Field Name |  |  | Object |  |  |  |  |  |  |  |
|  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | TYPE_O | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | TYPE_OF_ |  | MV_CONTRA |  | TYPE_OF_WORK |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | F_WOR |  |  |  |  | WORK_DES |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  |  |  | CTS |  | _DESC |  |  |
|  | K_DESC |  |  |  |  | C |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | TYPE_O | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | TYPE_OF_ |  | MV_CONTRA |  | TYPE_OF_WORK |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | F_WOR |  |  |  |  | WORK_AG |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  |  |  | CTS |  | _AGG |  |  |
|  | K_AGG |  |  |  |  | G |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | CN_STA | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | CN_STATE_ |  | MV_CONTRA |  | CN_STATE_PROJ |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | TE_PRO |  |  |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | PROJ_NBR |  | CTS |  | _NBR |  |  |
|  | J_NBR |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | CN_DES | Dashboard_Project_D |  | V_PRJ_DLVR_ |  |  |  |  | MV_CONTRA |  | CN_DESCRIPTIO |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  |  |  |  |  |  | CN_DESC |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  | C | elivery |  | CNTRCT |  |  |  | CTS |  | N |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | PRJ_NA | Dashboard_Project_D |  | V_PRJ_DLVR_ |  |  |  |  | MV_CONTRA |  |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  |  |  |  |  |  | PRJ_NAME |  |  |  | PROJECT_NAME |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  | ME | elivery |  | CNTRCT |  |  |  | CTS |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | ROAD_S | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | ROAD_SYST |  | MV_CONTRA |  |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  |  |  |  |  |  |  |  |  |  | ROAD_SYSTEM |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  | YSTEM | elivery |  | CNTRCT |  | EM |  | CTS |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | DISTRIC | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | DISTRICT_C |  | MV_CONTRA |  |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  |  |  |  |  |  |  |  |  |  | DISTRICT_CODE |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  | T_CODE | elivery |  | CNTRCT |  | ODE |  | CTS |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | CN_DIS | Dashboard_Project_D | V_PRJ_DLVR_ | CN_DISTRI |  | MV_CONTRA |  | CN_DISTRICT_N |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | TRICT_ |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | CT_NAME |  | CTS |  | AME |  |  |
|  | NAME |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | CONTA | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | CONTACT_ |  | MV_CONTRA |  | CONTACT_NAM |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | CT_NA |  |  |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | NAME |  | CTS |  | E |  |  |
|  | ME |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | CONTA | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | CONTACT_ |  | MV_CONTRA |  | CONTACT_PHO |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | CT_PHO |  |  |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | PHONE |  | CTS |  | NE |  |  |
|  | NE |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | CN_CR |  |  |  |  |  |  |  | CN_CRNT_ |  |  |  |  |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | NT_CNT | Dashboard_Project_D |  | V_PRJ_DLVR_ |  |  |  | MV_CONTRA |  | CN_CRNT_CONT |  |  |
|  |  |  |  |  |  | CNTRCT_A |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  | RCT_A | elivery |  | CNTRCT |  |  |  | CTS |  | RACT_AMT |  |  |
|  |  |  |  |  |  | MT |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | MT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | CN_AW |  |  |  |  |  |  |  | CN_AWRD |  |  |  |  |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | RD_CNT | Dashboard_Project_D |  | V_PRJ_DLVR_ |  |  |  | MV_CONTRA |  | CN_AWRD_CON |  |  |
|  |  |  |  |  |  | _CNTRCT_ |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  | RCT_A | elivery |  | CNTRCT |  |  |  | CTS |  | TRACT_AMT |  |  |
|  |  |  |  |  |  | AMT |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | MT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | CN_COS |  |  |  |  |  |  |  | CN_COST_ |  |  |  |  |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | T_OF_ | Dashboard_Project_D |  | V_PRJ_DLVR_ |  |  |  | MV_CONTRA |  | CN_COST_OF_ |  |  |
|  |  |  |  |  |  | OF_WORK_ |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  | WORK_ | elivery |  | CNTRCT |  |  |  | CTS |  | WORK_TO_DT |  |  |
|  |  |  |  |  |  | TO_DT |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | TO_DT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| VDOT Dashboard 4.0 User Guide |  |  |  |  |  |  |  |  |  | 2 |  |

|  | VDOT |  |  |  |  |  | VDOT |  |  | Dashboard |  |  | DashboardM |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CSV |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DashboardMart |  |  |  |  |
|  |  |  |  | VDOT CSV File |  |  | DasboardMar |  |  | Mart View |  |  | art Data |  |  |  |  |  | Datawarehouse Source Data Object |  |
|  | Field |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Field Name |  |  |  |  |
|  |  |  |  |  |  |  | t View |  |  | Field Name |  |  | Object |  |  |  |  |  |  |  |
|  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | CN_EST | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | CN_EST_C |  | MV_CONTRA |  | CN_ESTIMATED |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | _CMPLT |  |  |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | MPLTN_DT |  | CTS |  | _CMPLTN_DT |  |  |
|  | N_DT |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | CS_CUR |  |  |  |  |  |  |  | CS_CUR_SP |  |  |  |  |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | _SPCFD | Dashboard_Project_D |  | V_PRJ_DLVR_ |  |  |  | MV_CONTRA |  | CS_CUR_SPCFD_ |  |  |
|  |  |  |  |  |  | CFD_CMPL |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  | _CMPLT | elivery |  | CNTRCT |  |  |  | CTS |  | CMPLTN_DT |  |  |
|  |  |  |  |  |  | TN_DT |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | N_DT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | CN_DT_ | Dashboard_Project_D | V_PRJ_DLVR_ | CN_DT_AC |  | MV_CONTRA |  | CN_DATE_ACCE |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | ACCEPT |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | CEPTED |  | CTS |  | PTED |  |  |
|  | ED |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | ORIG_N |  |  |  |  |  |  |  | ORIG_NBR |  |  |  |  |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | BR_DAY | Dashboard_Project_D |  | V_PRJ_DLVR_ |  |  |  | MV_CONTRA |  | ORIG_NBR_DAY |  |  |
|  |  |  |  |  |  | _DAYS_ALL |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  | S_ALLO | elivery |  | CNTRCT |  |  |  | CTS |  | S_ALLOWED |  |  |
|  |  |  |  |  |  | OWED |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | WED |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | CN_MN | Dashboard_Project_D |  | V_PRJ_DLVR_ |  |  |  |  | MV_CONTRA |  | CONSTRUCTION |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  |  |  |  |  |  | CN_MNGR |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  | GR | elivery |  | CNTRCT |  |  |  | CTS |  | _MANAGER |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | RESIDE | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | RESIDENT_ |  | MV_CONTRA |  |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | NT_EN |  |  |  |  |  |  |  |  | RESIDENT_ENG |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | ENG |  | CTS |  |  |  |  |
|  | G |  |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | DEL_OB | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | DEL_OB_V |  | MV_CONTRA |  | DELIVERY_ON_B |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  |  |  |  |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  | _VAR | elivery |  | CNTRCT |  | AR |  | CTS |  | UDG_VARIANCE |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | DEL_OB | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | DEL_OB_ST |  | MV_CONTRA |  | DELIVERY_ON_B |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | _STATU |  |  |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | ATUS |  | CTS |  | UDG_STATUS |  |  |
|  | S |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | DEL_OB | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | DEL_OB_EX |  | MV_CONTRA |  | DELIVERY_ON_B |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | _EXPLA |  |  |  |  |  |  |  |  | UDG_EXPLANAT |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | PLANATION |  | CTS |  |  |  |  |
|  | NATION |  |  |  |  |  |  |  |  | ION |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | DEL_OB | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | DEL_OB_C |  | MV_CONTRA |  | DELIVERY_ON_B |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | _CRIT_F |  |  |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | RIT_FLG |  | CTS |  | UDG_CRIT_FLG |  |  |
|  | LG |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | DEL_OB | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | DEL_OB_PR |  | MV_CONTRA |  | DELIVERY_ON_B |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | _PRJ_P |  |  |  |  |  |  |  |  | UDG_PRJ_PRIOR |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | J_PRIORITY |  | CTS |  |  |  |  |
|  | RIORITY |  |  |  |  |  |  |  |  | ITY |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | DEL_OT | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | DEL_OT_V |  | MV_CONTRA |  | DELIVERY_ON_T |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | _VARIA |  |  |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | ARIANCE |  | CTS |  | IME_VARIANCE |  |  |
|  | NCE |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | DEL_OT | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | DEL_OT_ST |  | MV_CONTRA |  | DELIVERY_ON_T |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | _STATU |  |  |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | ATUS |  | CTS |  | IME_STATUS |  |  |
|  | S |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |

| VDOT Dashboard 4.0 User Guide | 3 |
| --- | --- |

|  | VDOT |  |  |  |  |  | VDOT |  |  | Dashboard |  |  | DashboardM |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CSV |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DashboardMart |  |  |  |  |
|  |  |  |  | VDOT CSV File |  |  | DasboardMar |  |  | Mart View |  |  | art Data |  |  |  |  |  | Datawarehouse Source Data Object |  |
|  | Field |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Field Name |  |  |  |  |
|  |  |  |  |  |  |  | t View |  |  | Field Name |  |  | Object |  |  |  |  |  |  |  |
|  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | DEL_OT | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | DEL_OT_EX |  | MV_CONTRA |  | DELIVERY_ON_T |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | _EXPLA |  |  |  |  |  |  |  |  | IME_EXPLANATI |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | PLANATION |  | CTS |  |  |  |  |
|  | NATION |  |  |  |  |  |  |  |  | ON |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | DEL_OT | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | DEL_OT_EA |  | MV_CONTRA |  | DELIVERY_ON_T |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | _EARLY |  |  |  |  |  |  |  |  | IME_EARLY_WA |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | RLY_WARN |  | CTS |  |  |  |  |
|  | _WARN |  |  |  |  |  |  |  |  | RN |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | DEL_OT | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | DEL_OT_CR |  | MV_CONTRA |  | DELIVERY_ON_T |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | _CRIT_F |  |  |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | IT_FLG |  | CTS |  | IME_CRIT_FLG |  |  |
|  | LG |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | DEL_OT | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | DEL_OT_PR |  | MV_CONTRA |  | DELIVERY_ON_T |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | _PRJ_P |  |  |  |  |  |  |  |  | IME_PRJ_PRIORI |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | J_PRIORITY |  | CTS |  |  |  |  |
|  | RIORITY |  |  |  |  |  |  |  |  | TY |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  |  |  | Dashboard_Project_D | V_PRJ_DLVR_ |  |  |  |  | MV_CONTRA |  |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | SOURCE |  |  |  | SOURCE |  |  |  | SOURCE |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  |  |  | CTS |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | UNAUDI | Dashboard_Project_D | V_PRJ_DLVR_ |  | UNAUDITE |  | MV_CONTRA |  | UNAUDITED_FI |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | TED_FN |  |  |  | D_FNL_COS |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  |  |  | CTS |  | NAL_COST |  |  |
|  | L_COST |  |  |  |  | T |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | PRJ_DE | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | PRJ_DEL_F |  | MV_CONTRA |  | PROJECT_DELIV |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  |  |  |  |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  | L_FY | elivery |  | CNTRCT |  | Y |  | CTS |  | ERY_FY |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | PRJ_DE | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | PRJ_DEL_C |  | MV_CONTRA |  | PROJECT_DELIV |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  |  |  |  |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  | L_CY | elivery |  | CNTRCT |  | Y |  | CTS |  | ERY_CY |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | CS_TYP | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | CS_TYPE_O |  | MV_CONTRA |  | CS_TYPE_OF_DA |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | E_OF_D |  |  |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | F_DAYS |  | CTS |  | YS |  |  |
|  | AYS |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  |  |  | Dashboard_Project_D | V_PRJ_DLVR_ |  |  |  |  | MV_CONTRA |  | RESIDENCY_CO |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | n/a |  |  |  | n/a |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  |  |  | CTS |  | DE |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | RESIDE | Dashboard_Project_D | V_PRJ_DLVR_ |  | RESIDENCY |  | MV_CONTRA |  | RESIDENCY_NA |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | NCY_N |  |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | _NAME |  | CTS |  | ME |  |  |
|  | AME |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  |  |  | Dashboard_Project_D | V_PRJ_DLVR_ |  |  |  |  | MV_CONTRA |  | CITY_COUNTY_C |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | n/a |  |  |  | n/a |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  |  |  | CTS |  | ODE |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | COUNT | Dashboard_Project_D |  | V_PRJ_DLVR_ |  | COUNTY_CI |  | MV_CONTRA |  | CITY_COUNTY_ |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | Y_CITY_ |  |  |  |  |  |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  | TY_DESC |  | CTS |  | DESC |  |  |
|  | DESC |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  |  |  | Dashboard_Project_D | V_PRJ_DLVR_ |  |  |  |  | MV_CONTRA |  |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | ROUTE |  |  |  | ROUTE |  |  |  | ROUTE |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  |  |  | CTS |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
| VDOT Dashboard 4.0 User Guide |  |  |  |  |  |  |  |  |  | 4 |  |

|  | VDOT |  |  |  |  |  | VDOT |  |  | Dashboard |  |  | DashboardM |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CSV |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DashboardMart |  |  |  |  |
|  |  |  |  | VDOT CSV File |  |  | DasboardMar |  |  | Mart View |  |  | art Data |  |  |  |  |  | Datawarehouse Source Data Object |  |
|  | Field |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Field Name |  |  |  |  |
|  |  |  |  |  |  |  | t View |  |  | Field Name |  |  | Object |  |  |  |  |  |  |  |
|  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | RESIDE |  |  |  |  |  |  |  | RESIDENT_ |  |  |  |  |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | NT_EN | Dashboard_Project_D |  | V_PRJ_DLVR_ |  |  |  | MV_CONTRA |  | RESIDENT_ENG_ |  |  |
|  |  |  |  |  |  | ENG_PHON |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  | G_PHO | elivery |  | CNTRCT |  |  |  | CTS |  | EMAIL |  |  |
|  |  |  |  |  |  | E |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | NE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | RESIDE |  |  |  |  |  |  |  | RESIDENT_ |  |  |  |  |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | NT_EN | Dashboard_Project_D |  | V_PRJ_DLVR_ |  |  |  | MV_CONTRA |  | RESIDENT_ENG_ |  |  |
|  |  |  |  |  |  | ENG_EMAI |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  | G_EMAI | elivery |  | CNTRCT |  |  |  | CTS |  | PHONE |  |  |
|  |  |  |  |  |  | L |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | L |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Dashboard_Project_D | V_PRJ_DLVR_ |  |  |  |  | MV_CONTRA |  |  |  |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | n/a |  |  |  | n/a |  |  |  | RENEWABLE |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  |  |  | CTS |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  |  |  | Dashboard_Project_D | V_PRJ_DLVR_ |  |  |  |  | MV_CONTRA |  | CONTRACT_STA |  | CDMART.CONTRACT_DIM, CDMART.CONTRACT_PROJECT_FACT, |
|  | n/a |  |  |  | n/a |  |  |  |  |  | CDMART.CONTRACT_PROJECT_DIM, CDMART.CONST_CONTR_VENDOR_DIM, |
|  |  | elivery |  | CNTRCT |  |  |  | CTS |  | TUS |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | ODS.CONTRACT, ODS.CONST_EXPENDITURE, ODS.LAD_CONTRACT |
|  | ACCOM | Dashboard_Project_D | V_PRJ_DEVEL |  | ACCOMPLI |  | MV_PROJECT |  | ACCOMPLISHME |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  | PLISHM |  |  |  |  |  |  |  |  |  |  |
|  |  | evelopment |  | OPMENT |  | SHMENT |  | S |  | NT_DESC |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | ENT |  |  |  |  |  |  |  |  |  |  |  |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | ACTUAL_ADV_D |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | ATE |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | ADIMIN | Dashboard_Project_D | V_PRJ_DEVEL |  | ADIMINIST |  | MV_PROJECT |  | ADMINISTER_BY |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  | ISTERED |  |  |  |  |  |  |  |  |  |  |
|  |  | evelopment |  | OPMENT |  | ERED_BY |  | S |  | _DESC |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | _BY |  |  |  |  |  |  |  |  |  |  |  |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | AREA_LOCATIO |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | N_NAME |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | CN_END_DATE |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | CN_START_DAT |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | E |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | COMMENTS |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | JURISDI | Dashboard_Project_D |  | V_PRJ_DEVEL |  | JURISDICTI |  | MV_PROJECT |  | COUNTY_NAME |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  | CTION | evelopment |  | OPMENT |  | ON |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | CURRENT_CN_E |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | STIMATE |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | CURRENT_PE_E |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | STIMATE |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | CURRENT_RW_E |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | STIMATE |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | CALEND | Dashboard_Project_D |  | V_PRJ_DEVEL |  | CALENDAR |  | MV_PROJECT |  |  |  |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  | AR_YEA |  |  |  |  |  |  |  |  | CURRENT_YEAR |  |  |
|  |  | evelopment |  | OPMENT |  | _YEAR |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | R |  |  |  |  |  |  |  |  |  |  |  |  |

| VDOT Dashboard 4.0 User Guide | 5 |
| --- | --- |

|  | VDOT |  |  |  |  |  | VDOT |  |  | Dashboard |  |  | DashboardM |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CSV |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DashboardMart |  |  |  |  |
|  |  |  |  | VDOT CSV File |  |  | DasboardMar |  |  | Mart View |  |  | art Data |  |  |  |  |  | Datawarehouse Source Data Object |  |
|  | Field |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Field Name |  |  |  |  |
|  |  |  |  |  |  |  | t View |  |  | Field Name |  |  | Object |  |  |  |  |  |  |  |
|  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | DASHB |  |  |  |  |  |  |  | DASHBOAR |  |  |  |  |  |  |  |  |  |
|  | OARD_ | Dashboard_Project_D |  | V_PRJ_DEVEL |  |  |  | MV_PROJECT |  | DASHBOARD_C |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  |  |  |  |  | D_CONTAC |  |  |  |  |  |  |
|  | CONTA | evelopment |  | OPMENT |  |  |  | S |  | ONTACT |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  |  |  |  |  |  | T |  |  |  |  |  |  |
|  | CT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | DASHB | Dashboard_Project_D | V_PRJ_DEVEL |  | DASHBOAR |  | MV_PROJECT |  | DASHBOARD_C |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  | OARD_ |  |  |  |  |  |  |  |  |  |  |
|  |  | evelopment |  | OPMENT |  | D_EMAIL |  | S |  | ONTACT_EMAIL |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | EMAIL |  |  |  |  |  |  |  |  |  |  |  |
|  | DASHB | Dashboard_Project_D | V_PRJ_DEVEL |  | DASHBOAR |  | MV_PROJECT |  | DASHBOARD_C |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  | OARD_ |  |  |  |  |  |  |  | ONTACT_PHON |  |  |
|  |  | evelopment |  | OPMENT |  | D_PHONE |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | PHONE |  |  |  |  |  |  |  |  | E |  |  |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | DEFICIENT |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | DESCRI | Dashboard_Project_D |  | V_PRJ_DEVEL |  | DESCRIPTI |  | MV_PROJECT |  | DESCRIPTION |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  | PTION | evelopment |  | OPMENT |  | ON |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | DISTRICT_CODE |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | DISTRIC | Dashboard_Project_D |  | V_PRJ_DEVEL |  | DISTRICT |  | MV_PROJECT |  | DISTRICT_CODE |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  | T | evelopment |  | OPMENT |  |  |  | S |  | _DESC |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | DOZIP |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | DW_EFF_BEG_D |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | ATE |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | DW_EFF_END_D |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | ATE |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | EST_CONST_CO |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | MP_DATE |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | FUNCTIONAL_CL |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | ASS_DESC |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | IN_PWA |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | JURISDICTION_D |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | ESC |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | MPO | Dashboard_Project_D | V_PRJ_DEVEL |  | MPO |  | MV_PROJECT |  | MPO_DESC |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | NON_V |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | DOT_PR |  |  |  |  |  |  |  | NON_VDOT |  |  |  |  |  |  |  |  |  |
|  | OJECT_ | Dashboard_Project_D | V_PRJ_DEVEL |  | _PROJECT_ |  | MV_PROJECT |  | NONVDOT_CON |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  | MANAG | evelopment |  | OPMENT |  | MANAGER |  | S |  | TACT_MAIL |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | ER_EM |  |  |  |  |  |  |  | _EMAIL |  |  |  |  |  |  |  |  |  |
|  | AIL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | NON_V | Dashboard_Project_D |  | V_PRJ_DEVEL |  | NON_VDOT |  | MV_PROJECT |  | NONVDOT_CON |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |

| VDOT Dashboard 4.0 User Guide | 6 |
| --- | --- |

|  | VDOT |  |  |  |  |  | VDOT |  |  | Dashboard |  |  | DashboardM |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CSV |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DashboardMart |  |  |  |  |
|  |  |  |  | VDOT CSV File |  |  | DasboardMar |  |  | Mart View |  |  | art Data |  |  |  |  |  | Datawarehouse Source Data Object |  |
|  | Field |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Field Name |  |  |  |  |
|  |  |  |  |  |  |  | t View |  |  | Field Name |  |  | Object |  |  |  |  |  |  |  |
|  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | DOT_PR | evelopment |  | OPMENT |  | _PROJECT_ |  | S |  | TACT_NAME |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | OJECT_ |  |  |  |  |  |  |  | MANAGER |  |  |  |  |  |  |  |  |  |
|  | MANAG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | NON_V |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | DOT_PR |  |  |  |  |  |  |  | NON_VDOT |  |  |  |  |  |  |  |  |  |
|  | OJECT_ | Dashboard_Project_D | V_PRJ_DEVEL |  | _PROJECT_ |  | MV_PROJECT |  | NONVDOT_CON |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  | MANAG | evelopment |  | OPMENT |  | MANAGER |  | S |  | TACT_PHONE |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | ER_PHO |  |  |  |  |  |  |  | _PHONE |  |  |  |  |  |  |  |  |  |
|  | NE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | PPMS_STATE_P |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | ROJECT |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | PROGR | Dashboard_Project_D | V_PRJ_DEVEL |  | PROGRAM |  | MV_PROJECT |  | PREVENTATIVE_ |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  | AM_MA |  |  |  | _MANAGE |  |  |  | MN_PROGRAM |  |  |
|  |  | evelopment |  | OPMENT |  |  |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | NAGER |  |  |  |  | R |  |  |  | MATIC |  |  |
|  | VDOT_P |  |  |  |  |  |  |  | VDOT_PRO |  |  |  |  |  |  |  |  |  |
|  | ROJECT | Dashboard_Project_D |  | V_PRJ_DEVEL |  |  |  | MV_PROJECT |  | PROJECT_MANA |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  |  |  |  |  | JECT_MAN |  |  |  |  |  |  |
|  | _MANA | evelopment |  | OPMENT |  |  |  | S |  | GER |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  |  |  |  |  |  | AGER |  |  |  |  |  |  |
|  | GER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | PROJECT_PURP |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | OSE |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | PROJEC | Dashboard_Project_D |  | V_PRJ_DEVEL |  | PROJECT_S |  | MV_PROJECT |  | PROJECT_STATU |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  | T_STAT |  |  |  |  |  |  |  |  |  |  |  |
|  |  | evelopment |  | OPMENT |  | TATUS |  | S |  | S_CODE |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | US |  |  |  |  |  |  |  |  |  |  |  |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | PROJECT_STATU |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | S_DESC |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | RECORD_TYPE |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | RECORD_TYPE_ |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | DESC |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | REGION_CODE_ |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | DESC |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | RESIDE | Dashboard_Project_D |  | V_PRJ_DEVEL |  | RESIDENCY |  | MV_PROJECT |  | RESIDENCY_DES |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  | NCY | evelopment |  | OPMENT |  |  |  | S |  | C |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | RNS_RO |  |  |  |  |  |  |  | RNS_ROUT |  |  |  |  |  |  |  |  |  |
|  | UTE_CO | Dashboard_Project_D |  | V_PRJ_DEVEL |  |  |  | MV_PROJECT |  | RNS_ROUTE_CO |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  |  |  |  |  | E_COMMO |  |  |  |  |  |  |
|  | MMON | evelopment |  | OPMENT |  |  |  | S |  | MMON_NM |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  |  |  |  |  |  | N_NM |  |  |  |  |  |  |
|  | _NM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | RNS_ROUTE_ID |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | ROUTE | Dashboard_Project_D | V_PRJ_DEVEL |  | ROUTE |  | MV_PROJECT |  | ROUTE |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |

| VDOT Dashboard 4.0 User Guide | 7 |
| --- | --- |

|  | VDOT |  |  |  |  |  | VDOT |  |  | Dashboard |  |  | DashboardM |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CSV |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DashboardMart |  |  |  |  |
|  |  |  |  | VDOT CSV File |  |  | DasboardMar |  |  | Mart View |  |  | art Data |  |  |  |  |  | Datawarehouse Source Data Object |  |
|  | Field |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Field Name |  |  |  |  |
|  |  |  |  |  |  |  | t View |  |  | Field Name |  |  | Object |  |  |  |  |  |  |  |
|  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | ROUTE_FORMA |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | TTED |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | SCENARIO_MOD |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | E |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | SCENARIO_TYPE |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | SCOPE_ | Dashboard_Project_D | V_PRJ_DEVEL |  | SCOPE_OF_ |  | MV_PROJECT |  | SCOPE_OF_WO |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  | OF_WO |  |  |  |  |  |  |  |  |  |  |
|  |  | evelopment |  | OPMENT |  | WORK |  | S |  | RK_DESC |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | RK |  |  |  |  |  |  |  |  |  |  |  |
|  | SMART | Dashboard_Project_D |  | V_PRJ_DEVEL |  | SMART_SC |  | MV_PROJECT |  | SMART_SCALE |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  | _SCALE | evelopment |  | OPMENT |  | ALE |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | SMART |  |  |  |  |  |  |  | SMART_SC |  |  |  |  |  |  |  |  |  |
|  | _SCALE | Dashboard_Project_D |  | V_PRJ_DEVEL |  |  |  | MV_PROJECT |  | SMARTSCALE_C |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  |  |  |  |  | ALE_COHO |  |  |  |  |  |  |
|  | _COHO | evelopment |  | OPMENT |  |  |  | S |  | OHORT |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  |  |  |  |  |  | RT |  |  |  |  |  |  |
|  | RT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | SPONSOR |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | ROAD_S | Dashboard_Project_D |  | V_PRJ_DEVEL |  | ROAD_SYST |  | MV_PROJECT |  | STATE_HIGHWA |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  | YSTEM | evelopment |  | OPMENT |  | EM |  | S |  | Y_DESC |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | STATE_ |  |  |  |  |  |  |  | STATE_OF_ |  |  |  |  |  |  |  |  |  |
|  | OF_GO | Dashboard_Project_D |  | V_PRJ_DEVEL |  |  |  | MV_PROJECT |  | STATE_OF_GOO |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  |  |  |  |  | GOOD_REP |  |  |  |  |  |  |
|  | OD_REP | evelopment |  | OPMENT |  |  |  | S |  | D_REPAIR |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  |  |  |  |  |  | AIR |  |  |  |  |  |  |
|  | AIR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | STIP_GROUPING |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | _DESC |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | SYP_SCENARIO_ |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | ID |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | TARGET_ADV_D |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | ATE |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | TOWN |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | TOWN_NAME |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | n/a | Dashboard_Project_D | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | UNTRIMMED_U |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  | PC |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | UPC | Dashboard_Project_D | V_PRJ_DEVEL |  | UPC |  | MV_PROJECT |  | UPC |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | VDOT_P |  |  |  |  |  |  |  | VDOT_PRO |  |  |  |  |  |  |  |  |  |
|  | ROJECT | Dashboard_Project_D |  | V_PRJ_DEVEL |  | JECT_MAN |  | MV_PROJECT |  | VDOT_PM_CON |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  | _MANA | evelopment |  | OPMENT |  | AGER_EMA |  | S |  | TACT_MAIL |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | GER_E |  |  |  |  |  |  |  | IL |  |  |  |  |  |  |  |  |  |

| VDOT Dashboard 4.0 User Guide | 8 |
| --- | --- |

|  | VDOT |  |  |  |  |  | VDOT |  |  | Dashboard |  |  | DashboardM |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CSV |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DashboardMart |  |  |  |  |
|  |  |  |  | VDOT CSV File |  |  | DasboardMar |  |  | Mart View |  |  | art Data |  |  |  |  |  | Datawarehouse Source Data Object |  |
|  | Field |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Field Name |  |  |  |  |
|  |  |  |  |  |  |  | t View |  |  | Field Name |  |  | Object |  |  |  |  |  |  |  |
|  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | MAIL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | VDOT_P |  |  |  |  |  |  |  | VDOT_PRO |  |  |  |  |  |  |  |  |  |
|  | ROJECT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Dashboard_Project_D |  | V_PRJ_DEVEL |  | JECT_MAN |  | MV_PROJECT |  | VDOT_PM_PHO |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  | _MANA |  |  |  |  |  |  |  |  |  |  |  |
|  |  | evelopment |  | OPMENT |  | AGER_PHO |  | S |  | NE |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | GER_PH |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | NE |  |  |  |  |  |  |  |  |  |
|  | ONE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_PROJECT |  | WORKFLOW |  | ODS.UPC_PROJECT, ODS.DIM_DATE, ODS.UPC_TEMP_PROJECT, |
|  |  | evelopment |  | OPMENT |  |  |  | S |  |  |  | ODS.TEMP_UPC_LOOKUP, WLS.SYP_SCENARIO_PROJECT, ODS.PPMS_PROJECT_ACTIVITY |
|  | UPC | Dashboard_Project_D |  | V_PRJ_DEVEL |  | UPC |  | MV_ACTIVITI |  | UPC |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  |  |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | CODE | Dashboard_Project_D |  | V_PRJ_DEVEL |  | CODE |  | MV_ACTIVITI |  | ACTIVITY_CODE |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  |  |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | DW_EFF_BEG_D |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | ATE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | DW_EFF_END_D |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | ATE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | TASK | Dashboard_Project_D |  | V_PRJ_DEVEL |  | TASK |  | MV_ACTIVITI |  | ACTIVITY_DESC |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  |  |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | ACTUAL | Dashboard_Project_D |  | V_PRJ_DEVEL |  | ACTUAL_ST |  | MV_ACTIVITI |  | ACTUAL_BEGIN_ |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  | _START | evelopment_Activity |  | OPMENT_ACT |  | ART |  | ES |  | DATE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | ACTUAL | Dashboard_Project_D |  | V_PRJ_DEVEL |  | ACTUAL_FI |  | MV_ACTIVITI |  | ACTUAL_END_D |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  | _FINISH | evelopment_Activity |  | OPMENT_ACT |  | NISH |  | ES |  | ATE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | STATUS | Dashboard_Project_D |  | V_PRJ_DEVEL |  | STATUS |  | MV_ACTIVITI |  | ACTUAL_MAND |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | AYS |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | CHANGE_PLAN_ |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | DATES |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | COMMENTS |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  |  |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | DASHBOARD_A |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | CTIVITY |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | DISTRICT_CODE |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  |  |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | DISTRICT_CODE |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | _DESC |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | DURATION |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  |  |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | FUNCTION_COD |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | E |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | FUNCTION_DES |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | C |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |

| VDOT Dashboard 4.0 User Guide | 9 |
| --- | --- |

|  | VDOT |  |  |  |  |  | VDOT |  |  | Dashboard |  |  | DashboardM |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CSV |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DashboardMart |  |  |  |  |
|  |  |  |  | VDOT CSV File |  |  | DasboardMar |  |  | Mart View |  |  | art Data |  |  |  |  |  | Datawarehouse Source Data Object |  |
|  | Field |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Field Name |  |  |  |  |
|  |  |  |  |  |  |  | t View |  |  | Field Name |  |  | Object |  |  |  |  |  |  |  |
|  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | LAST_M | Dashboard_Project_D |  | V_PRJ_DEVEL |  | LAST_MOD |  | MV_ACTIVITI |  | LAST_MODIFIED |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  | ODIFIED |  |  |  |  |  |  |  |  |  |  |  |
|  |  | evelopment_Activity |  | OPMENT_ACT |  | IFIED_DATE |  | ES |  | _DATE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | _DATE |  |  |  |  |  |  |  |  |  |  |  |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | LAST_MODIFIED |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | _USER |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | LATEST_BEGIN_ |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | DATE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | LATEST_END_D |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | ATE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | LATEST_MANDA |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | YS |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | MILESTONE_CO |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | DE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | MILESTONE_DE |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | SC |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | NEW_MILESTON |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | E_DESC |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | NOTE |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  |  |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | ORIGINAL_BEGI |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | N_DATE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | ORIGINAL_END_ |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | DATE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | ORIGINAL_MAN |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | DAYS |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | PREVIOUS_BEGI |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | N_DATE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | PREVIOUS_END |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | _DATE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | PREVIOUS_MAN |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | DAYS |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | PLNNED | Dashboard_Project_D |  | V_PRJ_DEVEL |  | PLNNED_ST |  | MV_ACTIVITI |  | RCMD_SCH_BE |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  | _START | evelopment_Activity |  | OPMENT_ACT |  | ART |  | ES |  | G_DATE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | PLANNE | Dashboard_Project_D |  | V_PRJ_DEVEL |  | PLANNED_ |  | MV_ACTIVITI |  | RCMD_SCH_EN |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  | D_FINIS |  |  |  |  |  |  |  |  |  |  |  |
|  |  | evelopment_Activity |  | OPMENT_ACT |  | FINISH |  | ES |  | D_DATE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | H |  |  |  |  |  |  |  |  |  |  |  |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | RCMD_SCH_DEL |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | ETE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | REQUEST_BEGI |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | N_DATE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | REQUEST_END_ |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |

| VDOT Dashboard 4.0 User Guide | 10 |
| --- | --- |

|  | VDOT |  |  |  |  |  | VDOT |  |  | Dashboard |  |  | DashboardM |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CSV |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DashboardMart |  |  |  |  |
|  |  |  |  | VDOT CSV File |  |  | DasboardMar |  |  | Mart View |  |  | art Data |  |  |  |  |  | Datawarehouse Source Data Object |  |
|  | Field |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Field Name |  |  |  |  |
|  |  |  |  |  |  |  | t View |  |  | Field Name |  |  | Object |  |  |  |  |  |  |  |
|  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  |  | ES |  | DATE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | REQUESTED_M |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | ANDAYS |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | SMARTSCALE_A |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | CTIVITY |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | UNTRIMMED_U |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | PC |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | ACTIVITY_LABEL |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  |  |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | BASELINE_BEGI |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | N_DATE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | BASELINE_END_ |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | DATE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | RULE_NBR |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  |  |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | LATEST_CLOSED |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | _ACTIVITY |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  |  |  | Dashboard_Project_D |  | V_PRJ_DEVEL |  |  |  |  | MV_ACTIVITI |  | DVLPMNT_ONTI |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  | n/a |  |  |  |  | n/a |  |  |  | ME_CRITICAL_F |  |  |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  |  |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  |  |  |  |  |  |  |  |  |  |  |  | LAG |  |  |
|  |  |  | Dashboard_Project_D |  | V_PRJ_DEVEL |  |  |  |  | MV_ACTIVITI |  | DVLPMNT_ONTI |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  | n/a |  |  |  |  | n/a |  |  |  | ME_EARLY_WA |  |  |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  |  |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  |  |  |  |  |  |  |  |  |  |  |  | RN_FLAG |  |  |
|  |  |  | Dashboard_Project_D |  | V_PRJ_DEVEL |  |  |  |  | MV_ACTIVITI |  | DVLPMNT_ONTI |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  | n/a |  |  |  |  | n/a |  |  |  | ME_EXPLANATI |  |  |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  |  |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  |  |  |  |  |  |  |  |  |  |  |  | ON |  |  |
|  |  |  | Dashboard_Project_D |  | V_PRJ_DEVEL |  |  |  |  | MV_ACTIVITI |  | DVLPMNT_ONTI |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  | n/a |  |  |  |  | n/a |  |  |  | ME_ROLLUP_PR |  |  |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  |  |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  |  |  |  |  |  |  |  |  |  |  |  | IORITY |  |  |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | DVLPMNT_ONTI |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | ME_STATUS |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |
|  | n/a | Dashboard_Project_D |  | V_PRJ_DEVEL |  | n/a |  | MV_ACTIVITI |  | DVLPMNT_ONTI |  | ODS.PPMS_PROJECT_ACTIVITY, ODS.UPC_PROJECT, ODS.DIM_DATE, |
|  |  | evelopment_Activity |  | OPMENT_ACT |  |  |  | ES |  | ME_VARIANCE |  | ODS.UPC_TEMP_PROJECT, ODS.TEMP_UPC_LOOKUP |

<eof>

| VDOT Dashboard 4.0 User Guide | 11 |
| --- | --- |