## Sheet1
Run Of Show provided by Feyer Marketing
|  |  | ↓ Modify this field |  |  |  | ↓ Modify this field
Project Name |  |  | Project Fire Bird |  |  | Launch Date | 2021-06-01
[6 empty] | Days Until Launch | 75
↓ Modify this column | ↓ Modify this column
Needed X Days Prior to Launch | X Days Required to Complete Task | Task Start By Date | Task Complete By Date | Phase | Task | Champion | Status
-90 | 30 | 2021-02-01 | 2021-03-03 | Discover | Conduct market research | Marketing Mgr | Complete
-90 | 30 | 2021-02-01 | 2021-03-03 | Discover | Conduct focus groups or other qualitative research | Marketing Mgr | Scheduled
-90 | 14 | 2021-02-17 | 2021-03-03 | Discover | Create positioning plan | Marketing Mgr | Complete
-90 | 7 | 2021-02-24 | 2021-03-03 | Discover | Create business case for product | Marketing Mgr | Scheduled
-90 | 7 | 2021-02-24 | 2021-03-03 | Discover | Determine pricing | Marketing Mgr | Scheduled
-90 | 2 | 2021-03-01 | 2021-03-03 | Discover | Tweak Creative and Publicity phase to meet needs of overall project | Marketing Mgr | Scheduled
-60 | 7 | 2021-03-26 | 2021-04-02 | Create | Create messaging plan and document (one-liner, elevator pitch, features, benefits, path to purchase, etc.) | Marketing Mgr | Scheduled
-45 | 14 | 2021-04-03 | 2021-04-17 | Create | Shoot and edit installation video and photos | Photographer | Scheduled
-45 | 14 | 2021-04-03 | 2021-04-17 | Create | Shoot and edit lifestyle promotion video and photos | Photographer | Scheduled
-45 | 7 | 2021-04-10 | 2021-04-17 | Create | Develop messaging and creative for "teaser" campaign | Marketing Mgr | Scheduled
-45 | 2 | 2021-04-15 | 2021-04-17 | Create | Create trade show new product submission and talking point plan | Marketing Mgr | Scheduled
-45 | 2 | 2021-04-15 | 2021-04-17 | Create | Reach out to media partners & writers about potential feature article to be written | Marketing Mgr | Scheduled
-30 | 7 | 2021-04-25 | 2021-05-02 | Create | Shoot and edit studio photos of product | Photographer | Scheduled
-30 | 7 | 2021-04-25 | 2021-05-02 | Create | Create website graphics and copy for product | Digital | Scheduled
-30 | 7 | 2021-04-25 | 2021-05-02 | Create | Record or develop new on-hold message for phone system | Marketing Mgr | Scheduled
-30 | 7 | 2021-04-25 | 2021-05-02 | Create | Plan, quote, create direct mail promotion plan | Marketing Mgr | Scheduled
-30 | 7 | 2021-04-25 | 2021-05-02 | Create | Create new draft of updated sales presentation | Designer | Scheduled
-30 | 4 | 2021-04-28 | 2021-05-02 | Create | Create one-page PDF sell sheet | Designer | Scheduled
-30 | 2 | 2021-04-30 | 2021-05-02 | Create | Write Press Release | Writer | Scheduled
-30 | 2 | 2021-04-30 | 2021-05-02 | Create | Write product data descriptions and copy | Writer | Scheduled
-30 | 2 | 2021-04-30 | 2021-05-02 | Create | Design and write email - distributor segment | Digital | Scheduled
-30 | 2 | 2021-04-30 | 2021-05-02 | Create | Stage assets and data into product information management system (ACES + PIES) | Product Data Mgr | Scheduled
-30 | 2 | 2021-04-30 | 2021-05-02 | Create | Create or tweak distributor catalog ad pages | Designer | Scheduled
-30 | 2 | 2021-04-30 | 2021-05-02 | Create | Create draft SKU, pricing, etc. spreadsheets | Product Data Mgr | Scheduled
-30 | 2 | 2021-04-30 | 2021-05-02 | Create | Create draft updated print application guide | Product Data Mgr | Scheduled
-30 | 2 | 2021-04-30 | 2021-05-02 | Create | Populate new item setup forms for direct customers | Product Data Mgr | Scheduled
-30 | 2 | 2021-04-30 | 2021-05-02 | Create | Create content for internal communication system (intranet, Korbit, internal TVs, bulletin boards, etc.) | Designer | Scheduled
-30 | 1 | 2021-05-01 | 2021-05-02 | Create | Design and write email - retailer segment | Digital | Scheduled
-30 | 1 | 2021-05-01 | 2021-05-02 | Create | Design and write email - consumer segment | Digital | Scheduled
-30 | 1 | 2021-05-01 | 2021-05-02 | Create | Design and write email - internal corporate segment | Writer | Scheduled
-30 | 1 | 2021-05-01 | 2021-05-02 | Create | Design employee e-mail signature product announcement graphic | Designer | Scheduled
-30 | 1 | 2021-05-01 | 2021-05-02 | Create | Evaluate promotion opportunities with distribution partners | Marketing Mgr | Scheduled
-30 | 1 | 2021-05-01 | 2021-05-02 | Create | Evaluate trade or distribution media advertising opportunities | Marketing Mgr | Scheduled
-30 | 1 | 2021-05-01 | 2021-05-02 | Create | Evaluate consumer level media advertising opportunities | Marketing Mgr | Scheduled
-30 | 0 | 2021-05-02 | 2021-05-02 | Create | Create draft updated print catalog and other materials | Designer | Scheduled
-30 | 0 | 2021-05-02 | 2021-05-02 | Publish | Begin traditional advertising campaigns | Marketing Mgr | Scheduled
-30 | 0 | 2021-05-02 | 2021-05-02 | Publish | Submit to trade show new product submission entries | Marketing Mgr | Scheduled
-30 | 0 | 2021-05-02 | 2021-05-02 | Publish | Launch "teaser" campaign | Marketing Mgr | Scheduled
-15 | 4 | 2021-05-13 | 2021-05-17 | Create | Create display advertising graphics package | Designer | Scheduled
-18 | 0 | 2021-05-14 | 2021-05-14 | Publish | Send email - internal corporate segment | Digital | Scheduled
-18 | 0 | 2021-05-14 | 2021-05-14 | Publish | Publish content to internal communication system (intranet, Korbit, internal TVs, bulletin boards, etc.) | Digital | Scheduled
-15 | 2 | 2021-05-15 | 2021-05-17 | Create | Create social media posting schedule and content | Marketing Mgr | Scheduled
-15 | 2 | 2021-05-15 | 2021-05-17 | Create | Create social media ads | Marketing Mgr | Scheduled
-15 | 2 | 2021-05-15 | 2021-05-17 | Create | Create paid search ads | Marketing Mgr | Scheduled
-14 | 0 | 2021-05-18 | 2021-05-18 | Publish | Send email - distributor segment | Digital | Scheduled
-14 | 0 | 2021-05-18 | 2021-05-18 | Publish | Distribute product data to Dci, SEMA Data Coop and direct partners | Product Data Mgr | Scheduled
-14 | 0 | 2021-05-18 | 2021-05-18 | Publish | Send new item setup forms and other assets to direct customers | Product Data Mgr | Scheduled
-14 | 0 | 2021-05-18 | 2021-05-18 | Publish | Distribute messaging and positioning plan to sales team | Marketing Mgr | Scheduled
-14 | 0 | 2021-05-18 | 2021-05-18 | Publish | Send distributor catalog ad pages | Marketing Mgr | Scheduled
-7 | 0 | 2021-05-25 | 2021-05-25 | Publish | Send email - retailer segment | Digital | Scheduled
-7 | 0 | 2021-05-25 | 2021-05-25 | Publish | Direct mail begin circulation | Marketing Mgr | Scheduled
-7 | 0 | 2021-05-25 | 2021-05-25 | Publish | Distribute or publish updated sales presentation | Marketing Mgr | Scheduled
0 | 0 | 2021-06-01 | 2021-06-01 | Publish | Send email - consumer segment | Digital | Scheduled
0 | 0 | 2021-06-01 | 2021-06-01 | Publish | Release Press Release and send to media contacts | Writer | Scheduled
0 | 0 | 2021-06-01 | 2021-06-01 | Publish | Publish installation and promotion videos | Photographer | Scheduled
0 | 0 | 2021-06-01 | 2021-06-01 | Publish | Publish product web pages & related content | Digital | Scheduled
0 | 0 | 2021-06-01 | 2021-06-01 | Publish | Publish announcement to social media | Digital | Scheduled
0 | 0 | 2021-06-01 | 2021-06-01 | Publish | Begin digital advertising campaigns | Marketing Mgr | Scheduled
0 | 0 | 2021-06-01 | 2021-06-01 | Publish | Publish phone system hold message updates | Marketing Mgr | Scheduled
0 | 0 | 2021-06-01 | 2021-06-01 | Publish | Send updated employee email signature to all staff | Marketing Mgr | Scheduled
0 | 0 | 2021-06-01 | 2021-06-01 | Publish | Distribute or publish SKU, pricing, etc. spreadsheets | Product Data Mgr | Scheduled
0 | 0 | 2021-06-01 | 2021-06-01 | Publish | Distribute or publish application guide | Designer | Scheduled
0 | 0 | 2021-06-01 | 2021-06-01 | Publish | Distribute or publish print catalog and other materials | Designer | Scheduled
30 | 2 | 2021-06-29 | 2021-07-01 | Review | Review top retailer websites to ensure new product has been loaded, follow-up if necessary | Marketing Mgr | Scheduled
30 | 2 | 2021-06-29 | 2021-07-01 | Review | Determine if secondary or additional launch touchpoints are necessary | Marketing Mgr | Scheduled
30 | 1 | 2021-06-30 | 2021-07-01 | Review | Analyze email open, click rates for each segment | Marketing Mgr | Scheduled
30 | 1 | 2021-06-30 | 2021-07-01 | Review | Analyze web traffic | Marketing Mgr | Scheduled
30 | 1 | 2021-06-30 | 2021-07-01 | Review | Analyze social media response to organic posts | Marketing Mgr | Scheduled
30 | 1 | 2021-06-30 | 2021-07-01 | Review | Analyze paid social media ads | Marketing Mgr | Scheduled
30 | 1 | 2021-06-30 | 2021-07-01 | Review | Analyze paid search engine ads | Marketing Mgr | Scheduled
30 | 1 | 2021-06-30 | 2021-07-01 | Review | Analyze overall press release pickup and articles written about new product | Marketing Mgr | Scheduled
90 | 7 | 2021-08-23 | 2021-08-30 | Review | Compile all analyses and evaluate opportunities for additional lines or applications | Marketing Mgr | Scheduled
90 | 2 | 2021-08-28 | 2021-08-30 | Review | Analyze sales data from first 90 days; revenue, margin, velocity | Marketing Mgr | Scheduled
90 | 2 | 2021-08-28 | 2021-08-30 | Review | Analyze online conversations regarding product in forums, social media, reviews, etc. for consumer sentiment and receptivity | Marketing Mgr | Scheduled
90 | 2 | 2021-08-28 | 2021-08-30 | Review | Collect sentiment received from new product at trade shows | Marketing Mgr | Scheduled
Formulas:
Task Start By Date = [Project Fire Bird]-[X Days Required to Complete Task]
Project Fire Bird = H3+[Project Name]