## Residential Construction Budget
New Home Construction Budget
Project Task |  | Worker hired | Planned start date | Planned end date | Deadline | Status | Priority | Task description | Est. Cost | Actual cost
GENERAL REQUIREMENTS
| Plans & Specifications (Architect/Designer/Builder/Premade) |  | 2022-06-10 | 2022-07-24 |  | Open | Low |  | 0 | 0
| Permits: Zoning, Building, Environemental |  | 2022-08-23 | 2022-10-06 |  | Open | Medium |  | 0 | 0
| Land Survey |  | 2022-08-23 | 2022-10-06 |  | Open | High |  | 0 | 0
| Financing and Closing Costs |  | 2022-10-21 | 2022-12-04 |  | Open | - |  | 0 | 0
| Legal Fees |  | 2022-10-21 | 2022-12-04 |  | Open | - |  | 0 | 0
| Other |  | 2022-11-21 | 2023-01-04 |  | Open | - |  | 0 | 0
[8 empty] | Total | 0 | 0
SITE PREP
| Demolition (Remodel) |  | 2023-01-05 | 2023-02-18 |  | Open | - |  | 0 | 0
| Jacking & Shoring (Remodel) |  | 2023-01-05 | 2023-02-18 |  | Open | - |  | 0 | 0
| Dust control, Surface Protection |  | 2023-01-05 | 2023-02-18 |  | Open | - |  | 0 | 0
| Dumpster & Removal |  | 2023-01-05 | 2023-02-18 |  | Open | - |  | 0 | 0
| Temporary Power |  | 2023-01-05 | 2023-02-18 |  | Open | - |  | 0 | 0
| Temporary Heat |  | 2023-01-05 | 2023-02-18 |  | Open | - |  | 0 | 0
| Tool/Equipment Rental |  | 2023-01-05 | 2023-02-18 |  | Open | - |  | 0 | 0
| Other |  | 2023-01-05 | 2023-02-18 |  | Open | - |  | 0 | 0
[8 empty] | Total | 0 | 0
ON-SITE WATER/SEWER
| Soil & Perc Tests |  | 2023-03-23 | 2023-05-06 |  | Open | - |  | 0 | 0
| Septic System Design |  | 2023-03-23 | 2023-05-06 |  | Open | - |  | 0 | 0
| Septic Permits, Inspections, Fees |  | 2023-03-23 | 2023-05-06 |  | Open | - |  | 0 | 0
| Septic System Installation, Tie in to House |  | 2023-03-23 | 2023-05-06 |  | Open | - |  | 0 | 0
| Dewatering (High Water Table) |  | 2023-03-23 | 2023-05-06 |  | Open | - |  | 0 | 0
| Well, Pump, Trenching, Plumbing to House |  | 2023-03-23 | 2023-05-06 |  | Open | - |  | 0 | 0
| Well Permits & Fees |  | 2023-03-23 | 2023-05-06 |  | Open | - |  | 0 | 0
| Other |  | 2023-03-23 | 2023-05-06 |  | Open | - |  | 0 | 0
[8 empty] | Total | 0 | 0
UTILITIES
| Town Water: Tap Fees & Hookup |  | 2023-04-24 | 2023-06-07 |  | Open | - |  | 0 | 0
| Town Sewer: Tap Fees & Hookup |  | 2023-04-24 | 2023-06-07 |  | Open | - |  | 0 | 0
| Electrical: Permit, Connection Fee, Installation |  | 2023-04-24 | 2023-06-07 |  | Open | - |  | 0 | 0
| Gas: Permit, Connection Fee, Installation |  | 2023-04-24 | 2023-06-07 |  | Open | - |  | 0 | 0
| LPN: Tank installation, Hookup |  | 2023-04-24 | 2023-06-07 |  | Open | - |  | 0 | 0
| Oil Tank Installation |  | 2023-04-24 | 2023-06-07 |  | Open | - |  | 0 | 0
| Telecom Hookup |  | 2023-04-24 | 2023-06-07 |  | Open | - |  | 0 | 0
| Other |  | 2023-04-24 | 2023-06-07 |  | Open | - |  | 0 | 0
[8 empty] | Total | 0 | 0
EXCAVATION & EARTHWORK
| Cut & Fill |  | 2023-05-23 | 2023-07-06 |  | Open | - |  | 0 | 0
| Blasting |  | 2023-05-23 | 2023-07-06 |  | Open | - |  | 0 | 0
| Removal of Stone/Dirt |  | 2023-05-23 | 2023-07-06 |  | Open | - |  | 0 | 0
| Rough Grading |  | 2023-05-23 | 2023-07-06 |  | Open | - |  | 0 | 0
| Trenching For Utility Hookups |  | 2023-05-23 | 2023-07-06 |  | Open | - |  | 0 | 0
| Foundation Excavation |  | 2023-05-23 | 2023-07-06 |  | Open | - |  | 0 | 0
| Foundation Footing Drains |  | 2023-05-23 | 2023-07-06 |  | Open | - |  | 0 | 0
| Ponds |  | 2023-05-23 | 2023-07-06 |  | Open | - |  | 0 | 0
| Other Site Drainage |  | 2023-06-23 | 2023-08-06 |  | Open | - |  | 0 | 0
| Compaction |  | 2023-06-23 | 2023-08-06 |  | Open | - |  | 0 | 0
| Top Soil |  | 2023-06-23 | 2023-08-06 |  | Open | - |  | 0 | 0
| Finish Grading |  | 2023-06-23 | 2023-08-06 |  | Open | - |  | 0 | 0
| Seeding/Sod |  | 2023-06-23 | 2023-08-06 |  | Open | - |  | 0 | 0
| Other |  | 2023-06-23 | 2023-08-06 |  | Open | - |  | 0 | 0
[8 empty] | Total | 0 | 0
FOUNDATION
| Footings/Pads |  | 2023-08-23 | 2023-10-06 |  | Open | - |  | 0 | 0
| Foundation walls/stem walls/grade beams |  | 2023-08-23 | 2023-10-06 |  | Open | - |  | 0 | 0
| Piers |  | 2023-08-23 | 2023-10-06 |  | Open | - |  | 0 | 0
| Slabs - Foundation, Basement, Garage |  | 2023-08-23 | 2023-10-06 |  | Open | - |  | 0 | 0
| Steel Reinforcing |  | 2023-08-23 | 2023-10-06 |  | Open | - |  | 0 | 0
| Anchor Bolts, Hold Downs |  | 2023-08-23 | 2023-10-06 |  | Open | - |  | 0 | 0
| Foundation Windows |  | 2023-08-23 | 2023-10-06 |  | Open | - |  | 0 | 0
| Damproofing, Water-proofing |  | 2023-08-23 | 2023-10-06 |  | Open | - |  | 0 | 0
| Foundation Drain Board |  | 2023-08-23 | 2023-10-06 |  | Open | - |  | 0 | 0
| Slab insulation: Edge/Blow |  | 2023-08-23 | 2023-10-06 |  | Open | - |  | 0 | 0
| Exterior Foundation Insulation |  | 2023-08-23 | 2023-10-06 |  | Open | - |  | 0 | 0
| Exterior Insulation Coating/ Protection |  | 2023-08-23 | 2023-10-06 |  | Open | - |  | 0 | 0
| Other |  | 2023-08-23 | 2023-10-06 |  | Open | - |  | 0 | 0
[8 empty] | Total | 0 | 0
OTHER MASONRY/PAVING
| Patios |  | 2023-09-25 | 2023-11-08 |  | Open | - |  | 0 | 0
| Exterior Stairs |  | 2023-09-25 | 2023-11-08 |  | Open | - |  | 0 | 0
| Masonry Chimneys |  | 2023-09-25 | 2023-11-08 |  | Open | - |  | 0 | 0
| Fireplaces/Hearths |  | 2023-09-25 | 2023-11-08 |  | Open | - |  | 0 | 0
| Driveway |  | 2023-09-25 | 2023-11-08 |  | Open | - |  | 0 | 0
| Walkways |  | 2023-09-25 | 2023-11-08 |  | Open | - |  | 0 | 0
| Other |  | 2023-09-25 | 2023-11-08 |  | Open | - |  | 0 | 0
[8 empty] | Total | 0 | 0
ROUGH FRAMING
| Sill & Seal |  | 2023-10-23 | 2023-12-06 |  | Open | - |  | 0 | 0
| Steel/Wood Carrying Beam, Lolly Columns |  | 2023-10-23 | 2023-12-06 |  | Open | - |  | 0 | 0
| Floor Framing |  | 2023-10-23 | 2023-12-06 |  | Open | - |  | 0 | 0
| Exterior & Interior Walls, Rough Stairs |  | 2023-10-23 | 2023-12-06 |  | Open | - |  | 0 | 0
| Sheathing, Subflooring |  | 2023-10-23 | 2023-12-06 |  | Open | - |  | 0 | 0
| Roof Framing/Trusses |  | 2023-10-23 | 2023-12-06 |  | Open | - |  | 0 | 0
| Subfascia |  | 2023-10-23 | 2023-12-06 |  | Open | - |  | 0 | 0
| Steel Framing Connectors |  | 2023-10-23 | 2023-12-06 |  | Open | - |  | 0 | 0
| Nails, Screws, Fasteners |  | 2023-10-23 | 2023-12-06 |  | Open | - |  | 0 | 0
| Prep for Plaster, Drywall |  | 2023-10-23 | 2023-12-06 |  | Open | - |  | 0 | 0
| Rough Framing - Labor Only |  | 2023-10-23 | 2023-12-06 |  | Open | - |  | 0 | 0
| Other |  | 2023-10-23 | 2023-12-06 |  | Open | - |  | 0 | 0
[8 empty] | Total | 0 | 0
EXTERIOR
| Exterior Foam Sheathing |  | 2023-11-22 | 2024-01-05 |  | Open | - |  | 0 | 0
| Weather Barrier (Tyvek, etc.) |  | 2023-11-22 | 2024-01-05 |  | Open | - |  | 0 | 0
| Membrance & Flashing |  | 2023-11-22 | 2024-01-05 |  | Open | - |  | 0 | 0
| Vinyl or Composite Siding |  | 2023-11-22 | 2024-01-05 |  | Open | - |  | 0 | 0
| Wood Siding |  | 2023-11-22 | 2024-01-05 |  | Open | - |  | 0 | 0
| Brick Veneer |  | 2023-11-22 | 2024-01-05 |  | Open | - |  | 0 | 0
| Stone Veneer |  | 2023-11-22 | 2024-01-05 |  | Open | - |  | 0 | 0
| Stucco |  | 2023-11-22 | 2024-01-05 |  | Open | - |  | 0 | 0
| Fascia, Frieze, Corner Boards, Water Table |  | 2023-11-22 | 2024-01-05 |  | Open | - |  | 0 | 0
| Soffit/Gable Vents |  | 2023-11-22 | 2024-01-05 |  | Open | - |  | 0 | 0
| Window/Door Trim |  | 2023-11-22 | 2024-01-05 |  | Open | - |  | 0 | 0
| Other Exterior Trim |  | 2023-11-22 | 2024-01-05 |  | Open | - |  | 0 | 0
| Exterior Paint, Stain, Caulk |  | 2023-11-22 | 2024-01-05 |  | Open | - |  | 0 | 0
| Exterior, labor-only |  | 2023-11-22 | 2024-01-05 |  | Open | - |  | 0 | 0
| Other |  | 2023-11-22 | 2024-01-05 |  | Open | - |  | 0 | 0
[8 empty] | Total | 0 | 0
WINDOWS/EXTERIOR DOORS
| Membrane & Flashing |  | 2024-01-06 | 2024-02-19 |  | Open | - |  | 0 | 0
| Exterior doors, prehung |  | 2024-01-06 | 2024-02-19 |  | Open | - |  | 0 | 0
| Exterior door slabs |  | 2024-01-06 | 2024-02-19 |  | Open | - |  | 0 | 0
| Exterior door frames, sills |  | 2024-01-06 | 2024-02-19 |  | Open | - |  | 0 | 0
| Sidelights, transoms |  | 2024-01-06 | 2024-02-19 |  | Open | - |  | 0 | 0
| Locksets, knobs, door hardware |  | 2024-01-06 | 2024-02-19 |  | Open | - |  | 0 | 0
| Patio doors: sliding or hinged |  | 2024-01-06 | 2024-02-19 |  | Open | - |  | 0 | 0
| Windows |  | 2024-01-06 | 2024-02-19 |  | Open | - |  | 0 | 0
| Garage Doors & Opener |  | 2024-01-06 | 2024-02-19 |  | Open | - |  | 0 | 0
| Other |  | 2024-01-06 | 2024-02-19 |  | Open | - |  | 0 | 0
[8 empty] | Total | 0 | 0
PLUMBING
| Drain/Waste/Vent |  | 2024-02-20 | 2024-04-04 |  | Open | - |  | 0 | 0
| Water Supply Piping |  | 2024-02-20 | 2024-04-04 |  | Open | - |  | 0 | 0
| Gas Piping |  | 2024-02-20 | 2024-04-04 |  | Open | - |  | 0 | 0
| Water Treatment |  | 2024-02-20 | 2024-04-04 |  | Open | - |  | 0 | 0
| Water Heater |  | 2024-02-20 | 2024-04-04 |  | Open | - |  | 0 | 0
| Fixtures: Toilets, Tubs, Sinks, Showers |  | 2024-02-20 | 2024-04-04 |  | Open | - |  | 0 | 0
| Faucets, Mixing Valves, Shower Heads |  | 2024-02-20 | 2024-04-04 |  | Open | - |  | 0 | 0
| Disposal |  | 2024-02-20 | 2024-04-04 |  | Open | - |  | 0 | 0
| Other |  | 2024-02-20 | 2024-04-04 |  | Open | - |  | 0 | 0
[8 empty] | Total | 0 | 0
ELECTRICAL
| Service, Panel, Sub-Panels |  | 2024-03-25 | 2024-05-08 |  | Open | - |  | 0 | 0
| Rough Wiring |  | 2024-03-25 | 2024-05-08 |  | Open | - |  | 0 | 0
| Phone, Cable, Internet Wiring |  | 2024-03-25 | 2024-05-08 |  | Open | - |  | 0 | 0
| Lighting Fixtures |  | 2024-03-25 | 2024-05-08 |  | Open | - |  | 0 | 0
| Low-Voltage Fixtures/Transformers |  | 2024-03-25 | 2024-05-08 |  | Open | - |  | 0 | 0
| Exterior Lighting |  | 2024-03-25 | 2024-05-08 |  | Open | - |  | 0 | 0
| Devices: outlets, switches, dimmers |  | 2024-03-25 | 2024-05-08 |  | Open | - |  | 0 | 0
| Lighting control system |  | 2024-03-25 | 2024-05-08 |  | Open | - |  | 0 | 0
| Doorbell System |  | 2024-03-25 | 2024-05-08 |  | Open | - |  | 0 | 0
| Smoke, CO2 Alarms |  | 2024-03-25 | 2024-05-08 |  | Open | - |  | 0 | 0
| Intercom system |  | 2024-03-25 | 2024-05-08 |  | Open | - |  | 0 | 0
| Security system |  | 2024-03-25 | 2024-05-08 |  | Open | - |  | 0 | 0
| Home theater/Entertainment |  | 2024-03-25 | 2024-05-08 |  | Open | - |  | 0 | 0
| Other |  | 2024-03-25 | 2024-05-08 |  | Open | - |  | 0 | 0
[8 empty] | Total | 0 | 0
HVAC
| Furnace/Heat Pump |  | 2024-05-09 | 2024-06-22 |  | Open | - |  | 0 | 0
| Central AC |  | 2024-05-09 | 2024-06-22 |  | Open | - |  | 0 | 0
| Air Handler |  | 2024-05-09 | 2024-06-22 |  | Open | - |  | 0 | 0
| Ductwork, Grilles, Registers |  | 2024-05-09 | 2024-06-22 |  | Open | - |  | 0 | 0
| Air Filter |  | 2024-05-09 | 2024-06-22 |  | Open | - |  | 0 | 0
| Boiler, Piping |  | 2024-05-09 | 2024-06-22 |  | Open | - |  | 0 | 0
| Radiators |  | 2024-05-09 | 2024-06-22 |  | Open | - |  | 0 | 0
| Whole-House Ventilation (HRV, ERV, Exhaust Only, Other) |  | 2024-05-09 | 2024-06-22 |  | Open | - |  | 0 | 0
| HVAC Controls |  | 2024-05-09 | 2024-06-22 |  | Open | - |  | 0 | 0
| Solar hot water |  | 2024-06-08 | 2024-07-22 |  | Open | - |  | 0 | 0
| Other |  | 2024-06-08 | 2024-07-22 |  | Open | - |  | 0 | 0
[8 empty] | Total | 0 | 0
INSULATION & AIR-SEALING
| Roof/Attic Insulation |  | 2024-02-21 | 2024-04-05 |  | Open | - |  | 0 | 0
| Roof/Eave Baffles |  | 2024-02-21 | 2024-04-05 |  | Open | - |  | 0 | 0
| Wall Cavity Insulation |  | 2024-02-21 | 2024-04-05 |  | Open | - |  | 0 | 0
| Foam Board Insulation |  | 2024-02-21 | 2024-04-05 |  | Open | - |  | 0 | 0
| Spray Foam Insulation |  | 2024-02-21 | 2024-04-05 |  | Open | - |  | 0 | 0
| Basement Insulation |  | 2024-02-21 | 2024-04-05 |  | Open | - |  | 0 | 0
| Air Sealing |  | 2024-02-21 | 2024-04-05 |  | Open | - |  | 0 | 0
| Energy Diagnostics (Blower Door, Infrared) |  | 2024-02-21 | 2024-04-05 |  | Open | - |  | 0 | 0
| Other |  | 2024-02-21 | 2024-04-05 |  | Open | - |  | 0 | 0
[8 empty] | Total | 0 | 0
DRYWALL/PLASTER
| Walls |  | 2024-03-25 | 2024-05-08 |  | Open | - |  | 0 | 0
| Ceilings, Soffits |  | 2024-03-25 | 2024-05-08 |  | Open | - |  | 0 | 0
| Decorative Plaster |  | 2024-03-25 | 2024-05-08 |  | Open | - |  | 0 | 0
| Drywall Labor Only |  | 2024-03-25 | 2024-05-08 |  | Open | - |  | 0 | 0
| Other |  | 2024-03-25 | 2024-05-08 |  | Open | - |  | 0 | 0
[8 empty] | Total | 0 | 0
INTERIOR FINISH
| Interior Doors, prehung |  | 2024-04-23 | 2024-06-06 |  | Open | - |  | 0 | 0
| Interior Door slabs |  | 2024-04-23 | 2024-06-06 |  | Open | - |  | 0 | 0
| Interior Door frames, thresholds |  | 2024-04-23 | 2024-06-06 |  | Open | - |  | 0 | 0
| Door knobs, hardware |  | 2024-04-23 | 2024-06-06 |  | Open | - |  | 0 | 0
| Chair Rail, Other |  | 2024-04-23 | 2024-06-06 |  | Open | - |  | 0 | 0
| Wainscotting, Paneling |  | 2024-04-23 | 2024-06-06 |  | Open | - |  | 0 | 0
| Built-in Shelving, Cabinets |  | 2024-04-23 | 2024-06-06 |  | Open | - |  | 0 | 0
| Closet Shelving, Hardware |  | 2024-04-23 | 2024-06-06 |  | Open | - |  | 0 | 0
| Stairs, Railings, Newels |  | 2024-04-23 | 2024-06-06 |  | Open | - |  | 0 | 0
| Interior Painting, Staining |  | 2024-04-23 | 2024-06-06 |  | Open | - |  | 0 | 0
| Wood Flooring |  | 2024-04-23 | 2024-06-06 |  | Open | - |  | 0 | 0
| Carpeting |  | 2024-04-23 | 2024-06-06 |  | Open | - |  | 0 | 0
| Resilient/Vinyl Flooring |  | 2024-04-23 | 2024-06-06 |  | Open | - |  | 0 | 0
| Other Flooring |  | 2024-04-23 | 2024-06-06 |  | Open | - |  | 0 | 0
| Acoustical, Metal, Decorative Ceilings |  | 2024-04-23 | 2024-06-06 |  | Open | - |  | 0 | 0
| Interior Carpentry Labor Only |  | 2024-04-23 | 2024-06-06 |  | Open | - |  | 0 | 0
[8 empty] | Total | 0 | 0
KITCHEN & BATH
| Kitchen Cabinets |  | 2024-06-07 | 2024-07-21 |  | Open | - |  | 0 | 0
| Bath Cabinets |  | 2024-06-07 | 2024-07-21 |  | Open | - |  | 0 | 0
| Cabinet Pulls, Hardware |  | 2024-06-07 | 2024-07-21 |  | Open | - |  | 0 | 0
| Countertop, Backsplash |  | 2024-06-07 | 2024-07-21 |  | Open | - |  | 0 | 0
| Ceramic Tile, Stone |  | 2024-06-07 | 2024-07-21 |  | Open | - |  | 0 | 0
| Raised Tub Platform |  | 2024-06-07 | 2024-07-21 |  | Open | - |  | 0 | 0
| Tub Enclosure |  | 2024-06-07 | 2024-07-21 |  | Open | - |  | 0 | 0
| Shower enclosure/doors |  | 2024-07-07 | 2024-08-20 |  | Open | - |  | 0 | 0
| Medicine Cabinets |  | 2024-07-07 | 2024-08-20 |  | Open | - |  | 0 | 0
| Mirrors |  | 2024-07-07 | 2024-08-20 |  | Open | - |  | 0 | 0
| Towel hangers, toilet paper holders, accessories |  | 2024-07-07 | 2024-08-20 |  | Open | - |  | 0 | 0
| K&B Labor Only |  | 2024-07-07 | 2024-08-20 |  | Open | - |  | 0 | 0
| Other |  | 2024-07-07 | 2024-08-20 |  | Open | - |  | 0 | 0
[8 empty] | Total | 0 | 0
PORCHES & DECKS
| Open Porch |  | 2024-08-21 | 2024-10-04 |  | Open | - |  | 0 | 0
| Screen Porch |  | 2024-09-19 | 2024-11-02 |  | Open | - |  | 0 | 0
| Wood or Composite Deck |  | 2024-09-19 | 2024-11-02 |  | Open | - |  | 0 | 0
| Fencing |  | 2024-09-19 | 2024-11-02 |  | Open | - |  | 0 | 0
| Other Outdoor Structures |  | 2024-09-19 | 2024-11-02 |  | Open | - |  | 0 | 0
| Other |  | 2024-09-19 | 2024-11-02 |  | Open | - |  | 0 | 0
[8 empty] | Total | 0 | 0
APPLIANCES
| Refrigerator |  | 2024-11-03 | 2024-12-17 |  | Open | - |  | 0 | 0
| Range, Cooktop |  | 2024-11-03 | 2024-12-17 |  | Open | - |  | 0 | 0
| Microwave |  | 2024-11-03 | 2024-12-17 |  | Open | - |  | 0 | 0
| Range Hood |  | 2024-11-03 | 2024-12-17 |  | Open | - |  | 0 | 0
| Dishwasher |  | 2024-11-03 | 2024-12-17 |  | Open | - |  | 0 | 0
| Washer/Dryer |  | 2024-11-03 | 2024-12-17 |  | Open | - |  | 0 | 0
| Other |  | 2024-11-03 | 2024-12-17 |  | Open | - |  | 0 | 0
[8 empty] | Total | 0 | 0
[8 empty] | Grand Total | 0 | 0