Draft Transition Plan for Home and Community-Based Services (HCBS), Health Home Care Management for Individuals with Intellectual and/or Developmental Disabilities (I/DD), and the Development of Specialized Managed Care

New York State Department of Health

New York State Office for People With Developmental Disabilities

December 5, 2017

Page 1 of 57

Contents

I.	Purpose	4

A.	Overview	4

B.	Organization of this Transition Plan and the Timeline for 1115 Actions	4

C.	Stakeholder Outreach and Engagement	6

- Phase I: I/DD Targeted HCBS and I/DD populations move into the 1115 Demonstration and

Transition to Health Home Services – July 1, 2018	8

A.	Transition of HCBS Services to the 1115	8

1.	Purpose	8

2.	Overview of Phase I - HCBS Services	8

3.	Service and Program Changes	9

4.	Continuity of Care for Individuals, Families and Providers	10

5.	Administrative Processes, Operations and Oversight	12

6.	Proposed Timeline associated with Phase I/HCBS Services	15

B.	Care Management Transitions to Health Homes – July 1, 2018	16

1.	Purpose	16

2.	Overview of Phase I – CCO/HH Services	16

3.	Service and Program Changes	17

- Continuity of Care Provisions for Individuals, Families, Medicaid Service Coordination

(MSC) Service Coordinators and MSC Providers	19

5.	Administrative Processes, Operations and Oversight	22

6.	Proposed Timeline Associated with Phase I Actions/Health Homes	28

III.	Phase II and III: Voluntary and Mandatory Managed Care Enrollment	29

A.	Purpose	29

B.	Overview of Phase II and III	30

C.	Service and Program Changes	31

D.	Continuity of Care Provisions for Individuals, Families and Providers	32

1.	Individuals and Families	32

2.	Providers	33

E.	Administrative Processes, Operations and Oversight	33

1.	Voluntary Individual Enrollment	33

2.	Mandatory Enrollment	34

F.	Oversight, Enrollee Protections and Enrollment Education in Managed Care	35

G.	Development of Specialized Managed Care Plans	36

H.	Quality Review of Managed Care	38

Page 2 of 57

1.	State’s Quality Strategy	38

2.	Plans’ Performance Improvement Projects (PIPs)	39

3.	External Quality Review Organization (EQRO)	39

I.	Proposed Timeline Associated with Phase II Actions	39

Attachment A: Health Home Checklist

Attachment B: Health Home Comprehensive Care Management and HCBS Care Management

Attachment C: CCO/HH Informational Sessions for MSC Staff

Attachment D: Health Home Implementation Timeline/Transition Plan for Individuals

Attachment E: Life Plan Template

Page 3 of 57

- Purpose

A.Overview

With federal and state approval, beginning July 1, 2018, New York State will initiate the transformation of the State's system of services for people with intellectual and/or developmental disabilities (I/DD) to better integrate services, promote the better use of resources to meet growing and changing needs, and become truly person centered. This transformation will include:

Providing comprehensive Health Home care management for individuals with I/DD provided by entities called Care Coordination Organizations/Health Homes (CCO/HHs) and transition from case management through State Plan Medicaid Service Coordination (MSC) and Plan of Care Support Services (PCSS);

Moving the federal authorization for Home and Community-Based Services (HCBS) now provided under the OPWDD Comprehensive 1915(c) Waiver to New York State’s 1115 Medicaid Redesign Team (MRT) Waiver; and

Initiating the transition to managed care (MC) for individuals with I/DD.

This document describes the planned activities associated with the I/DD service system transformation that will occur over a five-year period. The Transition Plan is available for a public comment period from December 5, 2017 through January 5, 2018. Based on public comment, this Transition Plan will be amended and submitted to the federal Centers for Medicare and Medicaid Services (CMS) for their review and approval. The trajectory to full implementation of managed care for the I/DD population will depend on the experiences and the outcomes of the early phases of the transition, and this plan will be updated and shared as the program further develops. Comments may be submitted to HHIDD@health.ny.gov.

- Organization of this Transition Plan and the Timeline for 1115 Actions

The Transition Plan is organized into two main sections. The first section describes the actions leading to the July 1, 2018 transition of the HCBS authority to the 1115 and the initiation of Health Home services. The subsequent section describes the implementation of specialized managed care for individuals with I/DD. The Transition Plan reflects a technical change from the submitted 1115 Waiver Application. To facilitate a timely federal approval, all activities associated with managed care are consolidated within the final two phases of the Application.

Page 4 of 57

The major phases described in this Transition Plan are described below.

| Phase | Timing | Description |
| --- | --- | --- |
| Phase I | 2018 | I/DD Targeted HCBS and I/DD populations are |
|  |  | moved under the 1115 Demonstration (July) |
|  |  | I/DD population transition to Health Homes (July) |
|  |  | New I/DD-led Mainstream Managed Care Plans |
|  |  | (Early Adopters) begin operation as Mainstream |
|  |  | Managed Care Plan (Health care benefit only, no |
|  |  | IDD services)1 |
| Phase II | 2019 | Early adopter I/DD Specialized Managed Care |
|  |  | Plans may begin voluntary enrollment with I/DD |
|  |  | benefit. Other Specialized Plans may be |
|  |  | approved. |
|  |  | Downstate Voluntary Enrollment into MC Plans |
|  | 2020 | Rest of State Voluntary Enrollment into MC Plans |
| Phase III | 2021 | Downstate Mandatory Enrollment into MC Plans |
|  | 2022 | Rest of State Mandatory Enrollment into MC |
|  |  | Plans |

Each section is organized to describe key policy and implementation topics associated with a phase of the Transition Plan. The key policy and implementation topics addressed are:

Overview Purpose

Service and Program Changes

Continuity of Care Provisions for Individuals, Families and Providers Administrative Processes, Operations and Oversight

Proposed Timeline associated with actions

- Early Adopters are entities that are controlled by not for profit entities with experience coordinating care and delivering I/DD services in New York State.

Page 5 of 57

C. Stakeholder Outreach and Engagement

The State is committed to a transparent transition process with extensive opportunities for public engagement on important issues surrounding the People First Care Coordination initiative, also referred to as Care Coordination Organization/Health Homes (CCO/HHs), that will combine services for developmental disabilities with health, wellness, and behavioral health services to create a single, integrated and individualized Life Plan. A Care Coordination Organization/Health Home (CCO/HH) is a Health Home that is tailored to meet the needs of individuals with I/DD. The CCO/HH will provide care management and coordination services that are tailored specifically to help people with I/DD and their families coordinate all services. CCO/HHs work with individuals with I/DD and their families to bring together health care and developmental disability service providers to develop an integrated, comprehensive care plan (known as a "Life Plan") that includes health and behavioral health services, community and social supports, and other services. CCO/HHs will assist individuals and their families with accessing services that support healthy, well–rounded and fulfilling lives.

There are four formal advisory bodies that support decision-making regarding the transition of the OPWDD service system to the 1115 Waiver.

Developmental Disability Advisory Council (DDAC) is a standing advisory body, established by New York State law, that has the ongoing responsibility to advise OPWDD in development of its comprehensive state plan and on the ongoing improvement, policies, goals, budgets and operations of the developmental disabilities services system.

Joint Advisory Council (JAC) is established in Mental Hygiene Law Section 13.40(f) and advises the Commissioners of the OPWDD and the Department of Health (DOH) regarding the design of managed care models that will provide services to individuals with developmental disabilities.

The Transformation Panel has advised the Commissioner of OPWDD on the Transformation Agenda, offering managed care in our system and ensuring its long-term fiscal sustainability for people currently receiving services and those who will need to access our services in the coming years.

The Medicaid Managed Care Advisory Review Panel (MMCARP) was created by Chapter 649 of the Laws of 1996 to monitor enrollment of Medicaid recipients in managed care plans and ensure access to care in these health care delivery systems.

Page 6 of 57

The State has developed a transition team that is comprised of staff from both DOH and OPWDD to routinely solicit feedback from external stakeholders. Throughout the transition period, the State will deliver educational materials through a variety of ways including, but not limited to, brochures and other educational materials in print, in-person presentations, and web-based formats to explain what will be changing in relation to the CCO/HH and 1115 Waiver transition and how individuals can access CCO/HH services.

Where indicated, both timely and adequate notices will be delivered to all affected individuals during each phase of this transition period. All materials will be written in plain language and made available in a manner consistent with State accessibility protocols. Medicaid Service Coordination (MSC) Service Coordinators who will transition to the role of CCO/HH Care Managers will be the primary source of information for families as they have established relationships and routine contact. To facilitate and support this method of education, the State will provide information to OPWDD Regional Offices (DDROs), MSC Service Coordinators and Care Managers. The State will issue separate guidance for providers as needed to ensure a smooth transition.

Through July 2018, the State will provide informational sessions via webinars or in public forums for stakeholders on the transition to CCO/HH care management and the change in authorization of HCBS from the 1915(c) authority to the 1115 Waiver authority. Web-based information sessions for all MSCs and appropriate DDRO staff is scheduled to begin no later than January 1, 2018 (see Attachment C). CCOs/HHs will assume responsibility for trainings for MSC staff and providers, with support provided as needed by OPWDD.

A dedicated webpage has been established on the OPWDD website at: https://opwdd.ny.gov/opwdd_services_supports/care_coordination_organiza tions, containing materials from webinars conducted with stakeholders and providers, letters and announcements to stakeholders and providers, a frequently asked questions (FAQs) document and links to the DOH website which contain additional information.

DOH has created a webpage specific to the CCO/HHs serving individuals

with I/DD at:

https://www.health.ny.gov/health_care/medicaid/program/medicaid_health_

homes/idd/, as well as  a webpage specific to the transition of HCBS for

individuals with I/DD at:

https://www.health.ny.gov/health_care/medicaid/program/medicaid_health_

homes/idd/draft_idd_1115_waiver.htm.

Page 7 of 57

Stakeholders are encouraged to register for the OPWDD stakeholder distribution list to stay informed about upcoming changes by sending in their email address at: https://opwdd.ny.gov/jointheconversation.

- Phase I: I/DD Targeted HCBS and I/DD populations move into the 1115 Demonstration and Transition to Health Home Services – July 1, 2018

  - Transition of HCBS Services to the 1115

- Purpose

The transition to the 1115 Waiver will support the continuity of current services and support increased flexibility and person-centered service delivery. Over time, OPWDD will develop new approaches to service delivery and value-based payment strategies within I/DD Specialized Managed Care Plans.

- Overview of Phase I - HCBS Services

This phase accomplishes the transition of the OPWDD Comprehensive 1915(c) Home and Community Based Services (HCBS) Waiver, funding, providers and plan of care requirements from the existing authority to the 1115 Waiver. Under the 1115, these services will remain available only to eligible individuals with I/DD and therefore will be identified in the 1115 Waiver as, “I/DD targeted HCBS services.” All services under the current OPWDD Comprehensive 1915(c) Waiver will remain available to individuals once the transition to the 1115 Waiver authority has occurred, except for Plan of Care Support Services or PCSS. Changes to PCSS and continuity of care provisions for individuals now receiving that service are described in the section of this document describing care management transitions beginning on page 19.

Except for PCSS, the transition to the 1115 Waiver will have no impact on individuals, families, and the authorization of HCBS services. HCBS will be available through both the fee for service (FFS) and managed care delivery systems as individuals with I/DD transition into managed care over the course of the next several years. The 1115 Waiver will also become the HCBS authority for the individuals enrolled in the Fully Integrated for Duals Advantage Plan for Individuals with Intellectual and Developmental Disabilities (FIDA-IDD). Individuals living in Intermediate Care Facilities (ICF/IIDs) will also transition under the 1115 Waiver authority. HCBS services definitions (other than for care coordination as described below),

Page 8 of 57

will not initially change with the transition to the 1115 Waiver. Any future changes to provider reimbursement rates will be subject to appropriate public notice.

- Service and Program Changes

Comprehensive care management, which will include care management and plan of care requirements for 1115 HCBS services, will be provided by CCO/HHs as authorized under the Health Home State Plan Amendment and the 1115 Waiver authority. Individuals who are now eligible for MSC or PCSS services will be eligible for CCO/HH services. Individuals who opt out of care management services provided by the CCO/HH will receive HCBS care management provided by the CCO as further described beginning on page 24 of this document. CCO/HHs will bill CCO/HH rates authorized by the State Plan, in accordance with public notice. The rate for the HCBS care management will be authorized by the 1115, in accordance with public notice.

Beginning July 1, 2018, the following services previously provided under the OPWDD Comprehensive 1915(c) Waiver will be transitioned to 1115 Waiver authority. These services will be available through the FFS delivery system under the 1115.

Habilitation

  - Residential

  - Day

  - Community

  - Prevocational (site-based and community)

  - Pathway to Employment

  - Supported Employment Respite

Adaptive Devices – Assistive Technology Environmental Modifications

HCBS care management (replacing PCSS) Family Education and Training

Services to Support Self-Direction

  - Fiscal Intermediary

- Support Brokerage

  - Individual Directed Goods and Services (IDGS) Community Transition Services

Live-In Caregiver

Intensive Behavioral Support Vehicle Modifications

Page 9 of 57

In addition to the OPWDD 1915(c) Comprehensive Waiver services identified above, individuals will continue to access OPWDD-specialized and other State Plan services including ICF/IID services, Day Treatment, Article 16 Clinic Services, Independent Practitioner Services for Individuals with Intellectual and Developmental Disabilities (IPSIDD) and Community First Choice Option (CFCO) services. The State will provide further guidance on the implementation of CFCO services.

Effective with the July 1, 2018 transition to the 1115 Waiver and the development of CCO/HHs, both MSC targeted case management services and PCSS will be end-dated. The transition associated with the end of these services and the initiation of CCO/HH services and HCBS care management under the 1115 Waiver is described in the next section of this Transition Plan (beginning on Page 16).

Effective with federal approval and the transition to the 1115 Waiver, federal financial participation will be available for crisis services delivered by OPWDD approved providers of START (Systemic, Therapeutic Assessment, Resources and Treatment) services. START is a community-based program that provides crisis prevention and response services to individuals with I/DD who present with complex behavioral and mental health needs, and to their families and others in the community who provide support.

- Continuity of Care for Individuals, Families and Providers a. Individuals and Families

Individuals with I/DD receiving services through the OPWDD Comprehensive 1915(c) Waiver will transition to the 1115 Waiver through a series of carefully organized and communicated steps. Individuals and families will be well informed of their options and rights throughout the transition.

To ensure that this change has no immediate impact on individuals enrolled in the OPWDD Comprehensive 1915(c) Waiver and to promote a seamless transition, all existing 1915(c) plans of care known as Individualized Service Plans (ISPs) (prior to July 1, 2018) will remain in place, and services will be considered authorized under the 1115 Waiver authority. Any change in a person’s OPWDD services will remain subject to NYCRR 633.12 and fair hearing rights following the transition to the 1115.

Page 10 of 57

The State will continue to use all current OPWDD Comprehensive 1915(c) Waiver protocols for referral, screening, and intake into Waiver program services, including determining the ICF level of care (LOC). The Medicaid eligibility application processes will also remain the same as it does today by going through the LDSS.

Individual eligibility for HCBS Waiver services under the 1115 Waiver is unchanged. Individuals with I/DD who are currently in receipt of OPWDD Comprehensive HCBS, at the time of transition to the 1115 Waiver, will experience no interruption in care. As is the process today, the individual must continue to meet the annual LOC requirement. In recognition of the transition activities underway in the Spring of 2018, OPWDD and DOH propose in the Transition Plan a temporary extension for the completion of the annual LOC redeterminations that are due in May through July 2018. As reflected in the timeline on page 28, LOC redeterminations that are due in May, June or July of 2018 will be extended and must be completed no later than September 30, 2018.

After the transition to the 1115 Waiver, individuals will be eligible for I/DD HCBS Services when they meet the ICF LOC, are Medicaid enrolled, and live in a residential setting as described in Part 14 NYCRR 635-10. HCBS eligible residential settings are the individual’s own or family home, or an OPWDD certified community-based residence meeting federal HCBS setting requirements or subject to heightened scrutiny. Similarly, all individuals newly identified by providers, Local Departments of Social Services (LDSS) or local government units as being potentially eligible for HCBS after July 1, 2018, will experience no additional changes in the process for completing the supporting documentation, Medicaid eligibility application, and intake processes necessary to establish Medicaid eligibility and access services.

The State will waive deeming of income and resources (if applicable) for all medically needy children for Family of One populations under this 1115 Waiver Demonstration Amendment. This provision allows the State to continue the current practice of evaluating the eligible child’s income and resources and not the family’s income and resources when establishing financial eligibility for Medicaid. In addition, to meet maintenance of effort requirements with respect to Medicaid eligibility, as the State transitions to the 1115 Waiver authority, OPWDD’s DDROs will continue to assist individuals/families in obtaining Medicaid eligibility via their LDSS and HCBS eligibility through the DDRO.

Page 11 of 57

ICF-IIDs will also transition into the 1115 waiver and will continue to be paid at the current rate described in the State Plan. Individuals living in ICF-IIDs will continue to receive services in accordance with their comprehensive functional assessment.

b.  Providers

It is anticipated that all providers that are certified for the delivery of

OPWDD Comprehensive 1915(c) HCBS services will be designated as

I/DD HCBS providers under the 1115 Waiver effective July 1, 2018.

Requests from entities that want to be newly established as I/DD HCBS

Services providers under the 1115 Waiver and are not currently an

approved OPWDD provider, will follow existing application processes as

described at:

https://opwdd.ny.gov/opwdd_services_supports/service_providers/how_to

_become_a_service_provider.

The Early Alert procedures currently in place within OPWDD to oversee provider fiscal, governance and compliance practices will remain in place during and after the transition to the 1115 Waiver. Any provider currently under review by the Early Alert committee will remain in this status until the entity complies in full with OPWDD’s recommendations and provides evidence to show that issues of concern have been corrected and a system has been put in place to prevent recurrence. As is now the practice, during or after the transition to the 1115 Waiver, if a provider is identified as having unacceptable fiscal, governance or compliance practices and the provider is unable or unwilling to make necessary changes, negative action may be taken against them by OPWDD including the transfer of services or the revocation of operating certificates.

- Administrative Processes, Operations and Oversight

a.  HCBS Enrollment

The State will maintain the current OPWDD HCBS Eligibility Determination criteria. The criteria and assessment tools used under the OPWDD Comprehensive 1915(c) Waiver will continue to be used throughout the transition process and under the 1115 Waiver authority.

If an individual with I/DD chooses to apply for I/DD HCBS, the individual must first meet the following criteria for OPWDD HCBS enrollment, as determined by the DDRO:

Page 12 of 57

Have an intellectual or developmental disability in accordance with the definition found in New York State Mental Hygiene Law Section 1.03 (22),

Medicaid eligibility,

Eligibility for ICF LOC,

Reside in an appropriate living arrangement or obtain residence in an appropriate setting prior to enrollment. Individuals must reside in their own or family home, Family Care home, Community Residence (CR), or Individualized Residential Alternative (IRA).

The CCO/HH will continue to work with the DDRO regarding the processing of HCBS eligibility determinations as is current practice for MSC agencies. On July 1, 2018, the State will continue to work with the local government unit, LDSS and provider referral processes to identify individuals with I/DD newly in need of HCBS. OPWDD will work with CCO/HHs regarding the streamlining of eligibility processes under the 1115 Waiver.

For individuals with I/DD who are enrolled in Medicaid and newly in need of HCBS, a referral will continue to be made directly to the individual’s local OPWDD DDRO. The DDRO will continue to perform the following responsibilities as the OPWDD system transition to CCO/HHs:

OPWDD HCBS Eligibility Determination and discussion of the available OPWDD HCBS providers within the individual’s/family’s region to choose from for the delivery of HCBS.

Make the OPWDD HCBS Eligibility Determination using the targeted and functional criteria established for the Developmental Disability LOC population.

For individuals with I/DD who are not yet Medicaid eligible, the DDRO will continue to refer individuals with I/DD who do not have Medicaid eligibility and need services to their LDSS to assist with applying for Medicaid prior to pursuing HCBS service enrollment.

DOH and OPWDD will provide extensive communication through Administrative Directive Memorandum (ADM), General Information System (GIS), desk aids and frequently asked questions (FAQs) as guidance to the LDSS on the new policies and processes associated with the termination of the 1915(c) Waiver program and transition to 1115 Waiver authority.

Page 13 of 57

The LDSS will continue to be responsible for establishing Medicaid eligibility for individuals with I/DD or referring community eligible applicants as appropriate to the New York State of Health (New York’s health benefits exchange). Medicaid eligibility rules will remain unchanged by this transition.

b.  Provider Billing and Payment

The State will ensure systems for eligibility, enrollment, cost reporting, and claims payment to support the transition by developing population identifiers on State eligibility systems to support Medicaid managed care enrollment and ensure access to services. The State will also develop changes to claims and billing systems to authorize FFS reimbursement, ensure defined allowable scope of benefits, and to monitor expenditures.

During the initial transition to the 1115 Waiver, the existing rates and fees paid for State Plan and HCBS Waiver services will continue. Future changes will be subject to public notice requirements.

Existing Information Technology provider and program identifiers and reporting codes associated with HCBS services in the OPWDD Tracking and Billing System (TABS) will remain unchanged with the initial transition to the 1115 Waiver. PCSS program codes will be closed for further enrollments effective July 1, 2018 as is further described in the Section of this document describing the transition of care management services.

c.  Oversight

For services under the jurisdiction of OPWDD, the current oversight, incident reporting requirements and quality standards for State and voluntary-operated State Plan and HCBS services will not change with the transition to the 1115 Waiver. OPWDD is modifying its current regulations to refer to the 1115 Waiver as appropriate. With this minor change, the current regulatory framework continues to apply to services under the jurisdiction of OPWDD and includes the following regulations:

14 NYCRR 701 – Justice Center Criminal History Information Checks

14 NYCRR 633 – Protection of Individuals Receiving Services 14 NYCRR 635 – General Quality Control and Administrative

Requirements

14 NYCRR 624 – Reportable Incidents and Notable Occurrences 14 NYCRR 625 – Events and Situations

Page 14 of 57

14 NYCRR 681 - Intermediate Care Facilities with Intellectual Disabilities

14 NYCRR 636Person Centered Planning (for matters related to Habilitation services)

The OPWDD Division of Quality Improvement will continue its surveillance and survey of programs and services under the auspice of OPWDD. Any future changes will be subject to advance public notice, and engagement and training of provider agency staff will be provided. OPWDD is actively seeking input on regulatory streamlining of operations and oversight to enhance access to, and operations of services.

- Proposed Timeline associated with Phase I/HCBS Services

The timeline below outlines the major elements associated with the transition of I/DD services to the 1115 Waiver. Dates will be adjusted as needed.

Proposed Phase I Timeline – HCBS Services

| Target |  |  | Action |
| --- | --- | --- | --- |
| Date |  |  |  |
| 6/7/2017 |  |  | Tribal Notifications to amend MRT 1115 |
|  |  |  | Waiver to include DD services |
|  |  |  | Federal Public Notice of intent to submit |
| 6/14/2017 |  |  | Amendment to transition HCBS services & |
|  |  |  | I/DD population |
| 6/15/2017 |  |  | Publication of the OPWDD Commissioner’s |
|  |  |  | Policy Paper on Managed Care |
| 7/21/17 |  |  | 1115 Draft Waiver Amendment published for |
|  |  |  | 30-Days |
| 7/24/17 |  |  | OPWDD/DOH joint message to State |
|  |  |  | partners regarding 1115 Draft Waiver |
|  |  |  | Amendment. |
|  |  |  | Final 1115 Waiver submission for IDD |
| 8/31/2017 |  |  | population |
|  |  |  | & publication of Response to 1115 Waiver |
|  |  |  | public comments |
| 11/2/2017- |  | Regional forums regarding CCO/HH |
| 12/6/2017 |  |  | implementation planning and 1115 transition |
| 12/5/2017 |  |  | Transition Plan posted to web/ for Public |
|  |  |  | Comment through 1/5/2018 |
|  |  |  | Page 15 of 57 |

| 12/13/17 | Series of twice-monthly informational |
| --- | --- |
|  | webinars for MSCs presented by OPWDD |
|  | and NYSDOH begin |
| 1/1/18 – | Guidance Document for CCO/HHs Training |
| 1/15/18 | Requirements and Curricula |
|  | Recommendations for Care Managers |
|  | scheduled for release by OPWDD and |
|  | NYSDOH. |
| 1/30/2018 | Submission to CMS of 1915c Amendment to |
|  | transition 1915c Waiver to 1115 Waiver |
| 3/1/2018 | Webexes begin with Service Coordinators |
|  | regarding the transition to 1115 Waiver and |
|  | the 6/1 mailing to enrollees |
| 6/1/2018 | Notice sent to all 1915(c) enrollees regarding |
|  | continuity of care and the 7/1/18 transition to |
|  | the 1115 authority |
| 7/1/2018 | 1915c authority transitions to 1115 Waiver |
| ongoing | Joint Advisory Council meetings |
| ongoing | Commissioner’s Transformation Panel |
| ongoing | Developmental Disability Advisory Committee |
| ongoing | Medicaid Managed Care Advisory Review |
|  | Panel (MMCARP) |

- Care Management Transitions to Health Homes – July 1, 2018

- Purpose

The purpose of the activities associated with this phase include the transition of MSC and PCSS to comprehensive, holistic care management CCO/HH model authorized under the proposed State Plan Amendment.

- Overview of Phase I – CCO/HH Services

To ensure the expertise of existing MSC Service Coordinators are incorporated into the CCO/HH model, this phase will accomplish transitioning the service of care coordination now provided by MSC agencies to the Health Home model (i.e., CCO/HHs), transition current MSC Service Coordinators and the individuals now receiving MSC or PCSS under the 1915(c) Waiver to the CCO/HHs under the authorization of the 1115 Waiver and State Plan Amendment.

Page 16 of 57

Health Home Care Managers, including MSC Service Coordinators who transition to Health Home, will be responsible for developing a person-centered, individual and family-driven, comprehensive care plan that includes all the medical, behavioral health (mental health and substance use) and community and social supports and services, including HCBS authorized under the 1115 waiver. The CCO/HHs will be responsible for working with individuals and their families to develop and oversee the enhanced Individualized Service Plans, called Life Plans. See Attachment E for additional information on Life Plans.

All individuals receiving MSC will have the opportunity to transition to Health Home care management provided by a CCO/HH. Individuals receiving HCBS and choosing not to enroll in CCO/HH care management will receive HCBS care management (i.e., a care plan that includes only HCBS services and is developed in accordance with HCBS care planning requirements and authorized under the 1115 Waiver). The HCBS care management will also be provided by the CCO/HH. This HCBS care management is an ‘opt-out’ service for individuals who choose not to receive the comprehensive care management provided by the CCO/HH under the Health Home model. More information regarding HCBS care management appears below in part V of this section.

More details on the development and composition of CCO/HHs is available

at

https://www.health.ny.gov/health_care/medicaid/program/medicaid_health_

homes/idd/docs/hhidd_application_part_1.pdf.

- Service and Program Changes

a.  Health Home Core Services

The Health Home State Plan requires that six Health Home core services be provided by designated CCO/HH providers. Under the provisions of the State Plan and Health Home standards and requirements developed by the State in accordance with the State Plan, CCO/HHs will deliver core services in a manner that meets the person-centered needs of individuals with I/DD, the Valued Outcomes of OPWDD and the programmatic objectives of the People First Transformation. The six core services are:

Page 17 of 57

- Comprehensive Care Management

This service includes the creation, execution, and updates of an individualized, person-centered plan of care for each enrollee (the

Life Plan). The Life Plan is the individual’s care plan that is electronic and supported by a care planning information system and addresses all service needs. The goal of initial and ongoing assessment and care management services is to integrate primary, behavioral and specialty health care and community support services in a manner that addresses all clinical and non-clinical needs, promotes wellness and management of chronic conditions in pursuit of optimal health outcomes and supports enrollees’ wishes. See Attachment E for additional information regarding the Life Plan.

- Care Coordination and Health Promotion

This service includes the education and engagement of an individual in making decisions that promote his/her maximum independent living skills and lifestyle choices that achieve the following goals: good health, proactive management of chronic conditions, early identification of risk factors, and appropriate screening for emerging health problems. Materials are adapted to each individual’s comprehension level, and Care Managers will provide the support necessary for the individual to understand and implement care coordination and health promotion practices.

- Comprehensive Transitional Care

This service includes the facilitation of services for the individual and his/her family and/or representative when the individual is transitioning between levels of care (including but not limited to hospital, nursing facility, ICF/IDD, rehabilitation facility, community based group home, family or self-care and for teenagers transitioning out of residential schools) or when an individual is electing to transition to a new Health Home provider.

- Individual and Family Support

This service includes the coordination of information and services to support enrollees and enrollees’ family and/or representative to maintain and promote quality of life, with a focus on community living options. Access and linkages to supports for families is included.

- Referral to Community and Social Support Services

This service includes providing information and assistance to engage and refer enrollees and enrollee support members (including family members and/or representatives and others) to community based resources (regardless of funding source), that can help meet the

Page 18 of 57

needs identified on the enrollee’s person-centered Life Plan. The service is also intended to include activities that connect and monitor an individual’s community activities and opportunities, develop relationships with others, and foster independence and integration, including employment.

  - Use of Health Information Technology (HIT) to Link Services The CCO/HHs are required to meet the HIT standards in the delivery of the Health Home core services. This includes an electronic Life Plan.

- Regional Designation of CCO/HHs

The State’s goal is to provide CCO/HH services statewide, including a choice of CCO/HH in regions wherever possible. The final Application was released on September 30, 2017, and potential applicants are required to submit completed applications by November 30, 2017. A copy of the Application is available at the following link: https://www.health.ny.gov/health_care/medicaid/program/medicaid_health_ homes/idd/. The State anticipates CCO/HHs will be designated on or before February 28, 2018.

Interested applicants were asked to submit initial information regarding their organizational structure and the MSC agencies with which they plan to establish formal relationships. The name and contact information and the potential service area for each emerging CCO/HH is available at: https://www.health.ny.gov/health_care/medicaid/program/medicaid_health_ homes/idd/letters_of_interest.htm.

- Continuity of Care Provisions for Individuals, Families, Medicaid Service Coordination (MSC) Service Coordinators and MSC Providers

a.  Individuals and Families

The enrollment process to transition to CCO/HHs from MSC and PCSS is designed to ensure that care management under MSC and PCSS provided to individuals with I/DD today are not disrupted and there is continuity of care between the person receiving services and their current service coordinator/ provider. Upon affiliation with a designated CCO/HH, today’s MSC service coordinators may begin to reach out to individuals and families and educate them on the benefits of enrolling in a CCO/HH. This process is expected to begin on April 1, 2018, with the expectation that consents to enroll in CCO/HH are completed by June 30, 2018. A detailed timeline is

Page 19 of 57

included on page 28 and in Attachment D. Individuals will have the choice of CCO/HH. Individuals who opt out of Health Home care coordination services will receive HCBS care management from a CCO/HH of their choice.

Individuals will be able to request a different CCO/HH prior to being enrolled in the CCO/HH and at any time following initial enrollment. To ensure there is no disruption of services during the transition process, once a CCO/HH is selected, a request to select a different CCO/HH submitted between June 15, 2018 and July 31, 2018 will be processed and effective September 1, 2018.

Once enrolled in a CCO/HH, individuals can request a different Care Manager at any time. CCO/HH applicants must establish a process for requesting a change in Care Manager and must inform enrollees of this process. Eligible individuals not currently enrolled in an MSC program have the option to enroll with a CCO/HH of their choice.

b.  MSC Service Coordinators

CCO/HH Care Managers must meet the following qualifications:

A Bachelor’s degree with two years of relevant experience, or A License as a Registered Nurse with two years of relevant

experience, which can include any employment experience and is not limited to care management/service coordination duties or

A Master’s degree with one year of relevant experience.

CCO/HH Care Manager qualifications will be waived for existing MSC Service Coordinators who apply to serve as Care Managers in CCO/HHs. This will facilitate continuity of care for the individuals receiving service coordination and ensure an adequate number of needed Care Managers.

In accordance with CCO/HH requirements and State standards, CCO/HHs will be required to provide Health Home core services training for all current MSC Service Coordinators who transition to the Health Home program. Documentation of the employee’s prior status as an MSC Service Coordinator may include a resume or other record created by the MSC agency or CCO/HH demonstrating that the person was employed as an MSC Service Coordinator prior to July 1, 2018. It is anticipated that most MSC Service Coordinators will transition to CCO/HHs, with any additionally needed training provided by the CCO/HHs. The CCO/HH will be responsible for ensuring that all “grandfathered” MSCs are adequately

Page 20 of 57

trained for Care Management responsibilities within one year of contracting with an MSC agency.

CCO/HHs are required to ensure that all CCO/HH Care Managers are

qualified to provide and meet the standards and requirements of CCO/HH

care management and deliver the six core Health Home services.  All

CCO/HHs must ensure Care Managers are trained in skill building areas

identified in the in the CCO/HH Application and can employ the skills

aligned with each area in the delivery of Health Home care management.

The CCO/HH Application is available at

https://www.health.ny.gov/health_care/medicaid/program/medicaid_health_

homes/idd/.  In January 2018, the State will provide CCO/HHs with

guidance on skill standards, learning objectives, training development

resources and any OPWDD mandated trainings.  All CCO/HH applicants

must submit their training plans for review to the State for meeting these

requirements during the readiness review period.

In addition to structural and systemic readiness activities for CCO/HHs, additional information will be provided to assist the Care Managers serving individuals with I/DD and families during the transition. The State will work closely with the agencies to assure that MSC Service Coordinators, and ultimately Care Managers, have the tools necessary to help families transition into CCO/HH. A series of informational sessions for MSC Service Coordinators and Supervisors is scheduled to begin in December (see Attachment C).

c.  MSC Provider Agencies

To ensure a smooth transition, during the first year of operations, CCO/HHs with appropriate firewalls and supervisory structures in place, may provide I/DD Health Home care management services through a contract or may directly employ Care Managers. CCO/HHs will be responsible for developing an infrastructure that supports the effective delivery of person-centered care management services and is consistent with State standards and requirements. They will need to define the supervisory structure and qualifications that will support that infrastructure. After one year of operation, all Care Managers (including former MSC Service Coordinators)

Page 21 of 57

providing care management under a designated CCO/HH must be directly employed by the CCO/HH and may not provide HCBS, with the exception of Care Managers who are affiliated with an MSC agency that is operated by a federally recognized Tribe.

- Administrative Processes, Operations and Oversight

  - Education & Choice with the Transition to CCO/HH Services

CCO/HH care management is an optional benefit, and individuals have the right to choose a CCO/HH or to opt out. The State is developing CCO/HH consent forms as well as consumer information regarding CCO/HHs and enrollment consent forms. The forms will be used to effectuate enrollment and the sharing of information among service providers and the team engaged in implementing the individual’s Life Plan.

Following the initial designation of CCO/HHs by the State, anticipated to occur no later than February 28, 2018, MSC Service Coordinators will begin talking with individuals and families about the transition to CCO/HH. By this time, the MSC Service Coordinator and MSC agency will have completed its affiliation with one of the CCO/HHs. The MSC Service Coordinator, who will transition to the role of a CCO/HH Care Manager, will assist individuals and families with information and the signing of consent forms in preparation for the enrollment in CCO/HH services effective July 1, 2018. These discussions are anticipated to occur between April 1, 2018 and June 30, 2018. CCO/HH Care Managers will explain the transition in general terms. All CCOs/HHs will be engaged in training and technical assistance that will include the standards and requirements for delivering CCO/HH care management in accordance with the State Plan and State guidance, as well as requirements and training around the use of HIT, electronic care management records, and other CCO/HH systems. All CCO/HHs and Care Managers will be trained on the requirements for developing care plans that include HCBS and State Plan services.

Under the State’s Transition Plan, there will be a choice of CCO/HHs available across the State where possible.

OPWDD will prepare, and the CCO/HH will distribute through its affiliated MSC agencies, informational letters to all individuals receiving MSC and PCSS, informing them of the benefits of CCO/HH services. This letter will specify with which CCO/HH their current MSC provider agency has affiliated. In addition, this letter will explain the option to receive HH services from alternative CCO/HHs in the region

Page 22 of 57

or to elect to opt-out of Health Home services and instead receive HCBS care management service as described on page 24 of this Plan. As part of the responsibilities of MSC, service coordinators will be responsible for ensuring an individual has received the CCO/HH informational letter. The MSC Service Coordinator will talk with the individual and family about what the transition means for the individual and what choices are available for the person relative to their need for care management.

Once a CCO/HH is selected, the individual will sign a consent form and at that point can indicate the providers with which information can be shared. The individual will be given a copy of the enrollment form, and the enrollment will become effective July 1, 2018.

To initiate and bill for Health Home services, Care Managers will be required to complete the Health Home Services Checklist, Attachment A, which is designed to assist Care Managers in ensuring the necessary actions items are completed to initiate a smooth transition into Health Home services for the individuals they serve. The purpose of completing the Checklist is to educate enrollees and their families on Health Home services and to understand the current service needs of the enrollee and their families. This process is essential to the successful delivery of Health Home core services and will confirm continuity of care and identify additional areas for needed services. These tasks must be completed in partnership with the Health Home enrollee and his/her designated representative, in either a face-to-face meeting or telephone conversation, and must occur between April 1 and June 30, 2018. An enrollee may change CCO/HHs at any time.

The enrollee’s Individualized Service Plan (ISP) will remain current until the initial comprehensive person-centered-planning meeting is held to establish the enrollee’s Life Plan. In addition to obtaining the current ISP and any other available assessment or supporting documentation, the Care Manager must also complete the following activities:

Confirm and identify the members of the Interdisciplinary Team (IDT), in which the primary I/DD providers (i.e. residential, day, and community habilitation providers) are mandatory members.

Confirm and identify all providers responsible for providing care to the enrollee. These providers will include, but are not limited to providers of medical and behavioral health services and specialists, I/DD services, Long Term Services and Supports, and social and community services.

Schedule the date, time and location of the care planning meeting and identify the IDT members who will be participating.

Page 23 of 57

The team must be comprised of the individual and/or their family member and/or their representative, the Care Manager, primary providers of I/DD services and other providers as requested by the enrollee and/or their family member and/or representative.

- Procedures for Individuals Who Opt Out of Health Home Services

Individuals with I/DD who wish to receive HCBS services, but are opting out of CCO/HH services, will instead receive HCBS care management. HCBS care management will be authorized under the 1115 Waiver and will provide the necessary development and management of HCBS services in a person’s HCBS care plan. Attachment B outlines the differences between HH care management and HCBS care management. Individuals will have the choice of receiving CCO/HH care management from a CCO/HH in their region, or opting out and receiving HCBS care management that will be provided by CCO. For the remainder of this document, this service will be referred to as CCO/HCBS care management or CCO/HCM. As with CCO/HH services, the CCO/HCM may contract with existing MSC agencies for up to a year (July 1, 2018 – June 30, 2019) for the delivery of the opt-out care management service.

HCBS care management will only provide the following essential functions to ensure the person’s continued access to HCBS services:

Developing and monitoring HCBS plans of care known as Life Plans for individuals with I/DD who opt out of Health Home;

Educating individuals about their freedom of choice of available CCOs/HHs; and

Performing annual LOC HCBS redeterminations, for individuals with I/DD who opt out of CCO/HH care management.

In addition, it is anticipated that as the CCO/HCM who is providing HCBS care management develops a relationship with the member and the family there will be the opportunity to develop interest in the receipt of the more comprehensive CCO/HH care management provided under the Health Home model. CCO/HCM must comply with the requirements for person-centered planning described in 14 NYCRR 636-1 regarding care plan development and monitoring, freedom of choice and the annual LOC

Page 24 of 57

redetermination process, including required assessment tools used during redetermination, ongoing care coordination and/or monitoring. The State will also provide access and training on appropriate systems to make CCO/HH referrals as appropriate and monitor access to care.

The payment for HCBS Care Management will be made to the CCO/HCM on a quarterly basis, in the amount of $243.40/quarter (see Attachment B).

- Readiness and System Operations

DOH and OPWDD will be seeking Applications from qualified parties interested in becoming designated CCO/HHs to serve individuals with I/DD per the timetable on page 28.

As a first step in the Application process, the State released “Part I” of the draft CCO/HH Application to serve individuals with I/DD for stakeholder review and comment from June 30, 2017 to August 11, 2017 on the DOH website at: https://www.health.ny.gov/health_care/medicaid/program/medicaid_health_ homes/idd/.

The Final Application includes an additional section “Part II.” Part II is the CCO/HH Application to serve individuals with I/DD. Qualified parties interested in becoming designated as a CCO/HH serving individuals with I/DD are required to complete and submit the Application. The State provided access to an electronic version of Part II of the Application. All Applicants will be required to electronically submit the Application, the Health Home Network Partner List, and other requirements.

Applications will be reviewed by a team of State staff from DOH and OPWDD. In reviewing Applications, the review team will consider the comprehensiveness of the Application. Areas of review and focus will include: the comprehensiveness of the Applicant’s network of providers, including the inclusion of qualified Care Managers and current MSC Service Coordinators and providers’ expertise in providing physical, behavioral health and community supports services to the individuals with I/DD; the demonstrated ability to meet the standards and requirements of the Health Home, including the delivery of the six core services; the demonstrated ability to promote inclusion and cultural competence by establishing sufficient partnerships with entities serving various cultural groups in the region in which the CCO/HH will be designated to operate.

Page 25 of 57

Based on the Applicant’s demonstrated level of comprehensiveness and competency, a CCO/HH will be “initially designated” beginning no later than March 2018, to serve individuals with I/DD, subject to the completion and review by the State of readiness activities and any other requirements identified by the State team. Upon completion and approval of those activities by the State, the CCO/HH will be formally designated and may begin operations.

CCO/HH Applicants must demonstrate they are controlled (at least 51 percent) by one or more non-profit organizations with a history of providing or coordinating developmental disability, health, and long term care services to persons with I/DD, including MSC and/or I/DD long term supports and services (LTSS). New York State’s expectation is that the governance structure and leadership of the CCO/HH (board members and officers) will have extensive experience coordinating care for individuals with I/DD in New York State, prior experience in overseeing and operating entities that have delivered MSC or HCBS Waiver services to individuals with I/DD, and are in good standing with the State. In addition, the CCO/HH must establish an advisory body that reports to the CCO/HH leadership and is made up of individuals served by the CCO/HH and their family-members and/or representatives.

Additional information regarding the CCO/HH Application, readiness review

process, and designation process is described in Part I of the CCO/HH

Application. Part I of the Application

(https://www.health.ny.gov/health_care/medicaid/program/medicaid_health_

homes/idd/) provides stakeholders and qualified parties interested in

becoming designated by the State as a CCO/HH with important information

about the Health Home care management program, including:

The important role designated CCO/HHs will have in providing person-centered, integrated care management to the I/DD community and their option to have a leadership role in the development and implementation of I/DD Specialized Managed Care Plans;

The anticipated schedule for CCO/HH designation, readiness and implementation activities;

How the existing Health Home model, including Health Home eligibility criteria, will be tailored to meet the unique needs of individuals with I/DD; and

State requirements and standards for serving individuals with I/DD in Health Homes and delivering the six core Health Home services, including:

Page 26 of 57

- Comprehensive assessments for the I/DD population to identify medical, behavioral, and social and community

services;

- Using a Life Plan to create and implement the Health Home person-centered plan and comprehensive planning process required by the Health Home model;

    - Health Home HIT and other systems requirements; o Per member, per month (PMPM) rates for CCO/HH; o Care Manager and network requirements; and

o  Performance management and quality oversight.

- Provider Billing and Payment

The State will provide technical guidance to entities that have submitted CCO/HH Applications and meet the minimum requirements outlined in section A of Part II of the CCO/HH Application. This information will detail how to obtain a Medicaid Provider Identification Number and describe other important information for becoming a provider of HH services.

For individuals transitioning from MSC to CCO/HH services, the most recent DDP2 completed within the last 24 months and filed in the OPWDD

Tracking and Billing System (TABS) will be used to calculate the individual’s

HH payment tier, on a monthly basis for the CCO/HH. In the rare case where two DDP2s are filed on the same (most recent) date, the following hierarchy will be used: residential program; day program; and MSC program. The DDP2 will be applied to the CCO/HH tier on a prospective basis. Enrollments into eMedNY will be effectuated, and once the data is uploaded into eMedNY, the appropriate Restriction/Exception (R/E) codes will be applied to ensure compliance with current billing protocol.

- Oversight

OPWDD CCO/HHs will be subject to ongoing performance monitoring and management. CCO/HHs will be required to undergo a re-designation process (designations are active for up to three years), based on key performance measures identified by the State and unique to individuals with I/DD. In the interim years, case reviews, site visits, routine calls, data and standards compliance reviews and monthly Health Home discussions with OPWDD and DOH will occur. Additionally, the State requires Health Homes to report, review, track and address complaints and critical incidents in accordance with published guidance.

Underperforming Health Homes, in accordance with severity of underperformance, will be subject to remediation measures up to and including revocation of CCO/HH authority. Remediation measures could

Page 27 of 57

include the submission of performance improvement plans, and routine review of policies and procedures, network guidance and Health Home operations.

- Proposed Timeline Associated with Phase I Actions/Health Homes

The anticipated schedule for the implementation of CCO/HHs for individuals with I/DD is as follows:

|  | Proposed Phase I Timeline |
| --- | --- |
| Target | Action |
| Date |  |
| June 30, 2017 | Draft I/DD Health Home Application Released |
| August 11, | Due Date to Submit Comments on Draft Health |
| 2017 | Home Application to Serve Individuals with I/DD |
| August 4, 2017 | Due Date to Submit Letter of Interest |
| October 6, | Final Health Home Application to Serve |
| 2017 | Individuals with I/DD Released |
| November 30, | Due Date to Submit Health Home Application to |
| 2017 | Serve Individuals with I/DD |
| December 2017 | State Webinars, Training, and Other Readiness |
| Through June | Activities |
| 30, 2018 |  |
| February | Initial approval of CCO/HHs is announced, |
| 28, 2018 | including listing of MSC affiliated providers. |
|  | Readiness and preparatory enrollment |
|  | activities begin. |
| March 1, | Initial CCO/HH designation/informational letter |
| 2018 to | distributed to all individuals receiving MSC and |
| March 30, | PCSS informing them of benefits of CCO/HH |
| 2018 | services |
| April 1, 2018 to | Health Home and Network Partner Readiness |
| June 30, 2018 | Activities |

Page 28 of 57

| April 1, 2018 to | MSC Service Coordinator conducts |
| --- | --- |
| June 30, 2018 | outreach/discussions with individuals and families, |
|  | Care Managers begin preliminary enrollment activities. |
|  | CCO/HH enrollment choices and processing occur, |
|  | although the effective date for enrollment is no earlier |
|  | than July 1, 2017 for enrollments effective July 1, |
|  | 2018. |
|  | For individuals transitioning to the CCO/HH, with an |
| May 1- | annual LOC redetermination due in June or July 2018, |
| September 30, | there will be a grace period for completion of the |
| 2018 | redetermination – these must be completed no later |
|  | than September 30, 2018. |
|  | Effective date for CCO/HH enrollment for members |
| July 1, 2018 | transitioning from MSC and PCSS, date to begin |
|  | CCO/HH care management for new individuals |
| July 1, 2018 | CCO/HH Enrollments into eMedNY effectuated. Data |
|  | is uploaded into eMedNY, and the appropriate R/E |
|  | codes will be applied to ensure compliance with |
|  | current billing protocol |
| July 1, 2018 to | The individual, family and Care Manager convene the |
|  | IDT and transition the current Individualized Service |
| December 31, |  |
|  | Plan (ISP) to a Life Plan. |
| 2018 |  |

III.  Phase II and III: Voluntary and Mandatory Managed Care Enrollment

- Purpose

The State's system of services for people with I/DD must change to better integrate services, promote the better use of resources to meet growing and changing needs, improve system flexibility and become truly person-centered. The development of managed care that is grounded in the tradition of specialized I/DD services will better support the needs of the population as it ages, ensure better access to cross-system care, and promote value based payment strategies that will drive continued improvement in I/DD services.

Page 29 of 57

As the State is working toward the development of specialized managed care options for individuals with I/DD, it must be acknowledged that today there are over 23,000 individuals with I/DD in New York State who have opted to enroll in Mainstream Managed Care for access to other Medicaid-funded acute health care services. The goal is to offer continuity of care for individuals and families for both HCBS services and for those 23,000 people who have already voluntarily enrolled in an existing Managed Care Plan.

In cases where an individual already is enrolled in an existing Mainstream Managed Care Plan, either individually or as part of the family’s health benefits plan, the individual will be able to access cross-system services including OPWDD specialized services through their existing Mainstream Managed Care Plan. For individuals remaining in Mainstream Managed Care, I/DD Targeted HCBS will be reimbursed through FFS until the I/DD contract amendments are effective with the Mainstream Managed Care Plans.

In all cases, whether an individual is now enrolled in a Mainstream Managed Care Plan, newly enrolls in an existing Mainstream Managed Care Plan or a newly established I/DD Specialized Managed Care Plan, the care management will be provided by CCO/HHs. Thus, the CCO/HHs established in Phase I will either apply to become I/DD Specialized Managed Care Plans or existing Mainstream Managed Care Plans will contract with CCO/HHs for the delivery of care management functions. In addition to newly created Specialized Plans, Dual Eligibles (Medicare-Medicaid enrollees) will continue to have access to either of the existing I/DD dual managed care opportunities in the down state area, the FIDA-IDD and the ArchCare Program of All-Inclusive Care for the Elderly (PACE) service.

- Overview of Phase II and III

The final phases of the 1115 Waiver implementation will focus on the

development of Specialized Medicaid Managed Care Plans with a focus on

I/DD services. The goal is the creation of a model of care that enables qualified

Specialized I/DD Managed Care Plans (in this document referred to as

“Specialized Managed Care Plans”) throughout the State to meet the needs of

individuals with I/DD. The State anticipates the release of a qualification

document to certify I/DD experienced, provider-led I/DD Specialized Managed

Care Plans. In addition, Mainstream Medicaid Managed Care Plans may qualify

to operate a separate line of business, by demonstrating the capacity to offer

the specialized I/DD services. The transition of the I/DD population to managed

care will initially occur on a voluntary enrollment basis with the establishment of

I/DD Specialized Managed Care Plans.

Page 30 of 57

- Service and Program Changes

The 1115 Waiver is designed to initiate managed care operations for the I/DD population to support the development of Value Based Payment (VBP) strategies. At the same time, there are important protections that are built into the transition process to ensure that individuals, families, providers and Managed Care Plans are all prepared for operations in the managed care system that meets the needs of individuals with I/DD.

Care Managers who work within the I/DD managed care environment, will first gain experience working in a comprehensive care planning environment with a CCO/HH while in FFS, beginning in 2018. In addition to this opportunity to prepare and develop the workforce prior to engaging in managed care, there are four important elements that are built into the 1115 Waiver application that support the readiness of all stakeholders to participate in managed care:

Individuals and families will have a period of time of voluntary enrollment in managed care, prior to the State implementing any mandatory enrollment.

Medicaid Managed Care Plans will be able to gain experience in managing the HCBS benefit before they will be ‘at risk’ for any HCBS services. (This is sometimes called ‘pay and report’ -- where a plan authorizes services, receives the FFS Medicaid rate from the State for HCBS services, which it will pass through to HCBS providers.)

During the voluntary enrollment period, the OPWDD DDROs will work in collaboration with Managed Care Plans to ensure plans are prepared to manage the HCBS benefit.

Providers of HCBS will be guaranteed the Medicaid payment rate from Managed Care Plans for a period-of-time.

The proposed Medicaid Managed Care implementation for individuals with I/DD is as follows:

2018: Early adopter plans may begin operation as a Mainstream Managed Care plan that provides Healthcare services, but does not include I/DD specialized services in the benefit package. No change in the current enrollment exemptions. Enrollment is voluntary for the I/DD population.

2019: Voluntary enrollment into I/DD Specialized Managed Care Plans. These may be early adopter plans with an expanded benefit package that includes I/DD benefits. May also include other newly created Specialized plans that did not begin operations as a Mainstream Managed Care Plan (assessing the outcomes of managed care for individuals with I/DD prior to implementing mandatory enrollment).

Page 31 of 57

2020: Voluntary enrollment is expanded Statewide. Begin review of Mainstream Medicaid Managed Care plans to offer I/DD Specialized plan line of business and readiness for all Mainstream Medicaid Managed Care Plans that were not Early Adopter I/DD Specialized plans in 2019, and other I/DD Specialized Managed Care Plans.

2021: Downstate mandatory enrollment will proceed in a region when the State confirms that there is choice of plans in a community that can support the needs of individuals with I/DD and promoting a Value Based Payment (VBP) methodology that furthers the transformation outcome of the Commissioner’s Transformation Panel.

2022: Remainder of State mandatory enrollment will proceed in a region when the State confirms that there is sufficient choice of plans that are capable of supporting the needs of individuals with I/DD and promoting a VBP methodology that furthers the transformation outcome of the Commissioner’s Transformation Panel.

2023: I/DD residential services become a part of the capitation rate for

Downstate I/DD Specialized Managed Care Plans and Mainstream Managed Care Plans. I/DD Targeted HCBS move to some form of risk basis within I/DD Specialized Managed Care Plans and Mainstream Managed Care Plans

2024: I/DD residential services become a part of the capitation rate for the Rest of State I/DD Specialized Managed Care Plans. I/DD Targeted HCBS move to some form of risk basis within I/DD Specialized Managed Care Plans and Mainstream Managed Care Plans

- Continuity of Care Provisions for Individuals, Families and Providers

- Individuals and Families

In addition to the timeframes above, which guarantee payment to providers, the continuity of care provisions identified below are in place to ensure that a person’s current care plan remains in place when he or she enrolls in a Managed Care Plan. These protections remain in place after the period when HCBS services are included in the capitation rate.

With respect to a person receiving non-residential HCBS services operated, certified, funded, authorized or approved by the OPWDD, the Managed Care Plan must pay the current provider of non-residential services at the rates established by the State for ninety days, to ensure continuity of care.

Page 32 of 57

With respect to a person living in a residential facility operated or certified by OPWDD, the Managed Care Plan must offer a contract with the provider of residential services at the rates established by the State for so long as such individual lives in that residence pursuant to an approved plan of care.

Plans must allow FFS individuals with I/DD newly enrolling in the Managed Care Plan to continue with their current provider for a current behavioral health episode of care for up to 24 months, regardless of that provider’s participation with the Managed Care Plan.

There are important design elements related to enrollment education, grievance and appeal rights and independent ombudsman services that support individuals and families. These elements are described in the following section (page 35).

- Providers

The protections above guarantee that, at a minimum, the provider is paid the established Medicaid Rate. A provider may waive these provisions to participate in advanced-level VBP strategies at an earlier date. The individual will always have a choice of provider within the Managed Care Plan’s network, and hence none of the provider protections described above diminish a person’s rights to request a change in the services described in his or her Life Plan and/or a change in service provider. I/DD HCBS services operated by a federally recognized Tribe will continue to be paid, at a minimum, the established Medicaid Rate.

- Administrative Processes, Operations and Oversight

- Voluntary Individual Enrollment

Under the 1115 Waiver, beginning in July, 2018, individuals with I/DD who were previously exempt from enrollment in Mainstream Managed Care may continue to enroll voluntarily in a plan and will receive HCBS from the FFS system. While gearing up for approval and enrollment into an I/DD Specialized Managed Care Plan, the State will provide technical assistance to OPWDD HCBS providers regarding contracting with Managed Care Plans prior to the transition of the OPWDD service system to managed care.

The transition of the I/DD population to managed care will occur initially on a voluntary enrollment basis, beginning in 2018, and be phased in throughout the State. Beginning in 2018, individuals with I/DD may enroll in

Page 33 of 57

available ‘early adopter’ plans that offer healthcare services and do not include I/DD services. In 2019, individuals with I/DD who were previously excluded (or exempt) from enrollment in Medicaid Managed Care based on a developmental or intellectual disability, will be able to voluntarily enroll in a Specialized Managed Care Plan and receive both State Plan as well as OPWDD HCBS from the Medicaid Managed Care delivery system. Those individuals who enrolled previously in Mainstream Medicaid Managed Care will be offered the choice to transfer to a Specialized Managed Care Plan. Individuals with I/DD who are otherwise exempt from enrollment in a Mainstream Managed Care Plan prior to 2021 for downstate residents and 2022 for individuals residing in the rest of the state will continue to have the option of enrolling in a Mainstream Managed Care Plan or receiving Medicaid benefits from the Medicaid FFS delivery system.

- Mandatory Enrollment

Beginning in 2021 (implementing downstate prior to upstate), the transition to mandatory managed care will proceed in a region when the State confirms that there is a sufficient choice of I/DD Specialized Managed Care Plans in a community that can support the needs of individuals with I/DD and promoting a VBP methodology that furthers the transformation

outcomes of the Commissioner’s Transformation Panel. Managed care enrollment for individuals with I/DD will be on a voluntary basis with enrollment into an I/DD Specialized Managed Care Plan. Voluntary enrollment in a Specialized Managed Care Plan will continue until two or more Managed Care Plans are available, offering individuals a choice in plans. At that time, mandatory enrollment into a Managed Care Plan will begin for individuals with I/DD unless they are otherwise exempt from Mandatory enrollment. Native Americans with Medicaid coverage may enroll in Medicaid managed care plans but are not required to do so. This exemption from mandatory enrollment for Native Americans will continue.

Individuals identified as required to enroll in a Managed Care Plan will be given prior written notice. An initial notification letter will inform the individual that the way services are received will soon change and that he/she will need to enroll in a Managed Care Plan. This initial notification will occur 30 days prior to a mandatory notice being sent to the individual. The notice will include an informational brochure about managed care,

available Managed Care Plans, and contact information for the State’s enrollment broker.

Mandatory notices will be sent to individuals indicating they have 60 days to choose a Managed Care Plan and enroll. The notice will include an enrollment packet, available Managed Care Plans in their region and the

Page 34 of 57

enrollment broker contact information. Additional reminder notices will be sent 45 and 30 days to individuals who are scheduled to transition to a plan and have not yet chosen a plan. If the individual does not choose a plan within 60 days, one will be auto-assigned for them using the state’s approved auto-assigned algorithm. The plan auto-assignment algorithm will include, but is not limited to, geographic accessibility and the plan’s affiliation with individuals’ current providers.

- Oversight, Enrollee Protections and Enrollment Education in Managed Care

During both the voluntary and mandatory enrollment period, the current regulatory framework continues to apply to services under the jurisdiction of OPWDD and includes the regulations identified above (page 14). The OPWDD Division of Quality Improvement will continue its surveillance and survey of programs and services under the auspice of OPWDD.

In accordance with existing law and regulation, the State will ensure individuals receive timely and adequate notice whenever a determination is made regarding Medicaid eligibility, HCBS eligibility, or Health Home eligibility, fully explaining all appeal and fair hearing rights. Everyone will receive similar beneficiary protections under Medicaid managed care, including the right to file complaints, timely and adequate notice, and the right to appeal and to ask for a fair hearing if the managed care plan denies a requested service, or approves less than the requested amount of a service, and, in the case of reduction, suspension or termination of current services, the right to have benefits continue while the managed care appeal or fair hearing is being decided. .

Individuals and families will be provided conflict-free advice and assistance from New York Medicaid Choice (currently a contract provided by Maximus Inc.). New York Medicaid Choice provides unbiased assistance and education related to enrollment and plan options through a call center and at various locations throughout New York State with in-person meetings and presentations. There are unique protocols now in place to assist individuals with enrollment in the FIDA-IDD, and these protocols will be evaluated and expanded to assist with the enrollment into new managed care options.

New York State maintains a contract with the Independent Consumer Advocacy Network (ICAN) program to provide direct assistance to all Medicaid long-term care recipients in navigating their coverage and in understanding and exercising their rights and responsibilities in managed care. ICAN has trained

Page 35 of 57

health counselors who answer a toll-free telephone hotline to answer questions about Medicaid Managed Care Plans. ICAN currently has a specialized counselor assisting people with I/DD with issues related to services available for the Fully Integrated Duals Advantage Plan (FIDA-IDD). The contract will be reevaluated and updated to reflect changing enrollment of the I/DD population in managed care.

- Development of Specialized Managed Care Plans

The State will conduct a desk review, followed by on-site readiness reviews, to ensure that the required components of serving individuals with I/DD have been met by the applicant. The readiness review process will address each Specialized Managed Care Plan’s capacity to serve the enrollees, including but not limited to, adequate network capacity, staff hiring plans including job description, training schedule and materials, policies and procedures, practice guidelines, and operational readiness to provide intensive levels of support. Onsite Readiness Reviews will be conducted in Spring of 2018. A team comprised of State agency staff will visit each Specialized Managed Care Plan and review their organization’s preparedness for the transition.

A list of OPWDD HCBS providers for individuals with I/DD will be provided to I/DD Specialized Managed Care Plans to facilitate network development and the contracting process under the FFS model prior to the OPWDD service system transition to managed care.

Specialized Managed Care Plan Applicants will be notified of their status (qualified, conditionally qualified pending corrective actions) at least three months in advance of enrolling individuals. The State will monitor corrective actions and work with conditionally qualified I/DD Specialized Managed Care Plans to ensure qualification standards and requirements are met during the three-month period prior to implementing enrollment. Plans that remain conditionally qualified at implementation will continue to be monitored and may be subject to additional conditions and safeguards ensuring enrollee access to services.

The State oversees Managed Care Plans using a combination of desk reviews and on-site reviews guided by a survey tool. Plan reporting will be expanded to include key metrics related to individuals with I/DD and HCBS benefits affected by this transition. The State will continue to monitor timely access to care standards by incorporating the requirements set forth by this transition in ongoing monitoring and surveillance activities.

Page 36 of 57

Each Managed Care Plan undergoes a Public Health Law Article 44 operational review. An on-site, comprehensive operational survey is conducted every two years, beginning one year after certification. In the off year of the comprehensive operational survey, a targeted survey is conducted to assess implementation of a Plan of Correction (or citations found during the operational survey), as well as the review of new or revised policies or organizational changes. These surveys are completed to comply with statutes, regulations, provisions within the Medicaid Managed Care Model Contract, and standards outlined in Medicaid qualification documents. Surveys include desk reviews of written material, which may include review of networks, policies and procedures, staff qualifications, and on-site reviews, which may include review of claim systems, and interviews with staff at various levels. If deficiencies are cited, the Medicaid Managed Care Plan is required to implement a corrective action plan, which is re-evaluated during the next survey. The State also conducts periodic focused surveys, including but not limited to: network capacity assessment; evaluations of access and availability of the provider network; testing of member services phone lines; review of provider directory information and accuracy; and compliance with fair hearing directives

The following areas will be incorporated into the Readiness requirements:

I/DD Specialized Managed Care Plans will have sufficient member services support to respond to questions related to HCBS for individuals with I/DD and provider network participation. The State expects member services staff to be adequately trained and any additional staff needed to support the volume of calls to be hired.

To begin authorization of new services, I/DD Specialized Managed Care Plans will be ready to accept Life Plans from a CCO. For those individuals newly enrolling into a Specialized Managed Care Plans, prior to sharing the individual’s Life Plan with the Specialized Managed Care Plans, the CCO must obtain consent to share the individual’s Life Plan with the Specialized Managed Care Plan.

I/DD Specialized Managed Care Plans will have all operational systems in place prior to enrolling individuals to ensure continuity of care provisions for transitioning members, to accept enrollments with new identifiers for HCBS-eligible individuals with I/DD, and pay HCBS claims and to collect data and report on issues daily.

Page 37 of 57

Three months in advance of enrolling individuals I/DD Specialized Managed Care Plans will:

- contract with (or amend contracts with) providers prior to enrolling individuals and begin claims testing with providers.

    - Test encounter data submissions and participate with the State in the provision of training to providers relating to claims submissions, network status, credentialing, etc. as contracts are executed.

- Quality Review of Managed Care

  - State’s Quality Strategy

As the Managed Care program evolves to bring forward specialized I/DD plans, strong adherence to the Transformation Panel’s goals and protections will be cornerstones of the quality strategy. Accompanying the Health-related measures, such as Healthcare Effectiveness Data and Information Set (HEDIS) and the Consumer Assessment of Healthcare Providers and Systems (CAHPS) satisfaction survey, monitoring of plan’s work to achieve person-centered goals and outcomes will be a focal point in establishing plan reporting requirements. Wellness, elimination of care fragmentation and individual attainment of goals will be measured by the National Core Indicators (NCI) and the Council on Quality and Leadership Personal Outcome Measures (NCI CQL POMs) and plan reported data to ensure this complex population is being appropriately served.

As part of the federal 1115 Waiver Authority, New York must develop and maintain a state quality strategy for assessing and improving the quality of health care and services furnished by managed care organizations (§ 1932(c)(1) of the Act). This quality strategy is intended to serve as a blueprint or road map for states and their contracted health plans in assessing the quality of care that beneficiaries receive, as well as for setting forth measurable goals and targets for improvement. The New York State quality strategy has evolved over time because of programmatic changes, member health needs, clinical practice guidelines, federal and state laws, lessons learned, and best practices.

The New York State quality strategy recognizes that, as I/DD Specialized Managed Care Plans develop and operationalize, additional managed care objectives need to be considered as part of the State’s Quality Strategy for the Medicaid Managed Care Program (Quality Strategy). As per Waiver requirements, the State is required to update the Quality Strategy upon any major changes to the Medicaid Managed Care program, making revisions available for public comment. Within 90 days of the 7/1/2018 amendment

Page 38 of 57

effective date, the State’s Quality Strategy will be revised and submitted to

CMS, reflecting changes in the transitioned care and services. Incorporated within the 90 days, will be a 30-day public comment period.

- Plans’ Performance Improvement Projects (PIPs) All Managed Care Plans must establish PIPs that:

Use objective measurements

Assess clinical and nonclinical areas

Implement system interventions to improve care Evaluate effectiveness

I/DD Specialized Managed Care Plans will be required to conduct one PIP annually using a report template that reflects CMS requirements for a PIP. With the expected implementation of 7/1/18, the initial selection of a PIP topic would take place prior to 1/1/20. Measurement data would be reported by 1/1/21. The DOH and the External Quality Review Organization (EQRO) support these collaborative efforts.

- External Quality Review Organization (EQRO)

An independent, External Quality Review Organization (EQRO) evaluates and reports on the quality, timeliness of, and access to, care and services provided by Medicaid Managed Care Plans. The EQRO conducts analysis and evaluation of aggregated information on quality, timeliness, and access to the services provided to Medicaid recipients. Required activities of the EQRO include an assessment of plan’s strengths and weaknesses, and recommending quality improvement projects. As phases II and III are implemented, the EQRO reports will be a valuable resource for improvement in the I/DD service system and a resource to Stakeholders.

- Proposed Timeline Associated with Phase II Actions

The timelines for voluntary and mandatory enrollment are described in prior sections of this Transition Plan. The table below identifies the target dates for the preparation, and where appropriate, public comment periods, for key policy documents related to the implementation of managed care for the I/DD population.

Page 39 of 57

Proposed Phase II & III Timeline

Target

Date

Action

|  | Entities seeking Early Adopter status apply for NYS |
| --- | --- |
| January 1, | HMO certification or amendment of HMO Certificate of |
|  | Authority for comprehensive health services plan, and |
| 2018 |  |
|  | qualification as comprehensive Medicaid managed |
|  | care plan |
| August 1, | Draft qualification document for I/DD Specialized |
| 2018 | Managed Care Plans released for public comment |
| November | FINAL qualification document for I/DD Specialized |
|  | Managed Care Plans released – Round 1 Early |
| 1, 2018 |  |
|  | Adopters |
|  | Early adopter plans may be approved as a |
|  | Mainstream Managed Care Plan (Healthcare benefits |
| December | only – these plans will later become a Specialized |
| 1, 2018 | Managed Care Plan at this date there are no |
|  | specialized I/DD benefits). Voluntary enrollment for |
|  | I/DD population |
| January 1, | Managed Care OPWDD Transition Policy & Related |
| 2019 | Guidance published in Draft for Public Comment |
| March 1, | Finalize Managed Care OPWDD Transition Policy & |
| 2019 | Related Guidance Finalized |
| March 1, | Early Adopter (if certified HMO/HMO application |
|  | submitted) I/DD Specialized Managed Care Plan |
| 2019 |  |
|  | Qualification Application Due |
| June 1, | Early Adopter successful applicants certified and |
| 2019 | qualified |

Page 40 of 57

Attachment A

Initiating Health Home Services:

Care Manager Checklist

The checklist below is designed to assist Care Managers in ensuring the necessary actions items are completed to initiate a smooth transition into Health Home services for the individuals they serve. The purpose of completing these tasks is to educate enrollees and their families on Health Home services and to understand the current service needs of the enrollee and their family. The following activities are essential to the successful delivery of Health Home core services and will confirm continuity of care and identify additional areas for needed services.

These tasks must be completed in partnership with the Health Home enrollee and their designated representative, in either a face-to-face meeting or telephone conversation, and must occur between April 1, 2018 and June 30, 2018. Enrollment in the CCO/HH is

Step One: Information Gathering

Upon enrollment into the Care Coordination Organization/Health Home (CCO/HH), the Care Manager must complete the following steps for everyone on their case load:

- Obtain the enrollee’s current Individualized Service Plan (ISP). This plan will remain effective until the initial comprehensive person-centered planning meeting is held to establish the enrollee’s Life Plan.

- Obtain available OPWDD assessment information, including the DDP2 and CAS summaries, from the OPWDD IT system (Choices)

- Confirm and identify the members of the Interdisciplinary Team (IDT), in which the primary I/DD providers (i.e. residential, day, and community habilitation providers) are mandatory members.

- Confirm and identify all Providers responsible for providing care to the enrollee. These providers will include but are not limited to medical, behavioral health, specialists, I/DD services, Long Term Services and Supports, and social and community services.

- Schedule the date, time and location of the Life Plan review meeting and the IDT members who will be participating.

Date of Person-Centered-Planning Meeting: Click or tap to enter a date.

Step Two:

Care Coordination Organizations/Health Homes (CCO/HHs) are required to provide the following six Health Home Core Services. The tasks referenced below are examples of core service activities that must be completed during the initial transition period to CCO/HH. Care Managers will be responsible for educating and identifying areas of service need for enrollees and their families.

Comprehensive Care Management

- Inform enrollee and their family of the care manager’s responsibility to create, document, execute and update the individualized, person-centered plan of care.

- Identify enrollee’s current service needs, providers, supports, goals, and engagement actives.

Page 41 of 57

Care Coordination and Health Promotion

- Educate enrollee and their family on engagement and decision-making to promote independent living, as well as education on wellness promotion and prevention programs ☒ Coordinate and arrange for the provision of current additional needed services and ensure treatment adherence.

Comprehensive Transitional Care (note: CCO/HH services may be billed to eMedNY within 30 days of

discharge from a hospital or institutional setting.)

- Notify enrollee and their family of the established networks with local practitioners, health facilities including emergency rooms, hospitals, and residential/rehabilitation settings.

- Is the enrollee currently residing in a health facility? (i.e. hospital or residential/rehabilitation setting?

- Yes ☐ No

If yes, are the appropriate procedures currently in place to ensure timely access to follow-up care post discharge? ☐ Yes ☐ No

Enrollee and Family Support

- Educate enrollee and their family on support and self-help resources to increase knowledge, engagement, self-management and to improve adherence to prescribed treatment.

Currently, does the enrollee and family require additional education and support services?

  - Yes ☐ No

Referral to Community and Social Supports

- Advise enrollee and their family of available community-based resources and explain the care

manager’s role in managing appropriate referrals, access, engagement, follow-up and coordination. Currently, does enrollee require additional community-based resource support?

  - Yes ☐ No

Use of Health Information Technology (HIT) to Link Services

- Inform enrollee and their family of the purpose and utilization of HIT.

  - Has the enrollee signed a consent to share personal information? ☐ Yes ☐ No

X

Case Manager - Date

Page 42 of 57

Attachment B

Health Home Comprehensive Care Management and HCBS Care

Management

The chart below outlines the key program design standards and the requirements for Health Home Care Management and HCBS Care Management within CCO/HHs.

| Health Home Standards | HCBS Care Management (Opt Out) |
| --- | --- |
|  | Standards |
| Care Manager Responsibilities – | HCBS Care Manager Responsibilities – |
| Reach out to individuals and families to | Develop and monitor HCBS Life Plans for |
| educate them on the benefits of enrolling in a | individuals with I/DD who opt out of Health |
| Health Home | Home services |
| Complete the Health Home Services | Educate individuals about their freedom of |
| Checklist, to initiate Health Home Services, | choice of available CCO/HHs |
| educating and identifying areas of service | Perform annual LOC redeterminations, for |
| need for enrollees and their families | individuals with I/DD that opt out of CCO/HH |
| Developing a person-centered | care management |
| comprehensive care plan (Life Plan) and |  |
| coordinate annual LOC |  |
| Care Manager Qualifications – | HCBS Care Manager Qualifications – |
| A Bachelor’s degree with two years of | A Bachelor’s degree with two years of |
| relevant experience, OR | relevant experience, OR |
| A License as a Registered Nurse with two | A License as a Registered Nurse with two |
| years of relevant experience, which can | years of relevant experience, which can |
| include any employment experience and is | include any employment experience and is |
| not limited to care management/service | not limited to care management/service |
| coordination duties, OR | coordination duties, OR |
| A Master’s degree with one year of relevant | A Master’s degree with one year of relevant |
| experience | experience |
| Grandfathering of current MSC Service | Grandfathering of current MSC Service |
| Coordinators | Coordinators |
| Care Manager Training – | HCBS Care Manager Training – |
| CCO/HHs will be required to provide Health | Expectation is that all CCO/HH Care |
| Home core services training. | Managers will be trained in HH services. For |
| CCO/HHs must ensure Care Managers are | individuals they serve who are enrolled in |
| trained in skill building areas. | HCBS case management, they will adjust |
| CCO/HHs must ensure Care Managers are | activities accordingly. |
| trained on the requirements for developing |  |
| care plans that include HCBS and State Plan |  |
| Services. |  |
| Health Home Services – | HCBS Care Management Services - |
| Use of Health Information Technology – to |  |
| link services, and enhance communication | Coordinate and arrange provision of services |
| between providers |  |
| Coordinate and Provide access to chronic |  |
| disease self-management support to |  |
| individuals and families |  |

Page 43 of 57

| Health Home Standards | HCBS Care Management (Opt Out) |
| --- | --- |
|  | Standards |
| Coordinate access to mental health and |  |
| substance abuse services |  |
| Establish continuous quality improvement |  |
| program – to collect and report on data that |  |
| permits an evaluation of increased |  |
| coordination of care |  |
| Coordinate and arrange provision of services |  |
| Support adherence to treatment |  |
| recommendations |  |
| Monitor and evaluate individual’s needs |  |
| Identify community based resources |  |
| Billing and Payment – | Billing and Payment – |
| For individuals transitioning from MSC to | Opt Out Fee = $243 Proposed payment |
| CCO/HH services, the most recent DDP2 | schedule 1/quarter (4 times/calendar year) |
| completed within the last 24 months and |  |
| filed in TABS will be used to calculate the |  |
| individual’s HH payment tier, on a monthly |  |
| basis |  |
| The Monthly fee ranges between $317 - $598 |  |
| (Upstate) and $337 - $637 (Downstate) |  |
| Consent to Enroll – | Opt Out Consent to Enroll |
| A signed consent form will effectuate | An individual must consent to enroll in HCBS |
| enrollment and the sharing of information | Care Management. |
| among service providers and team |  |
| engagement in implementing the individual’s |  |
| Life Plan. |  |
| Lack of Decision | Lack of Decision |
| For an individual without a decision-maker or | For an individual without a decision-maker or |
| where a decision has not been made, | where a decision has not been made, |
| OPWDD will notify the person that OPWDD | OPWDD will notify the person that OPWDD |
| will make a decision on their behalf based on | will make a decision on their behalf based on |
| a set of criteria. Criteria will include review | a set of criteria. Criteria will include review |
| of current services to ensure continuity of | of current services to ensure continuity of |
| care. | care. |
| Life Plan Requirements | Life Plan Requirements |
| Developed using an Integrated Information | Does not require the use of an IT (electronic) |
| Technology or IT (electronic) system that | system |
| allows for prompt real-time notification(s), | Integrates HCBS services only |
| regarding any changes to the individual’s | Understandable and personal plan, with its |
| plan, to those providers in the individual’s | required attachments, for implementing |
| network. | decisions made during a person-centered |
| Integrates all preventive and wellness | planning process |
| services, medical and behavior healthcare, | The HCBS Care Management Life Plan is not |
| personal safe guards and habilitation to | required to include personal outcome |
| support each participant’s personal dreams | measures. |

Page 44 of 57

| Health Home Standards | HCBS Care Management (Opt Out) |
| --- | --- |
|  | Standards |
| Understandable and personal plan for | The HCBS Case Management Life Plan is not |
| implementing decisions made during person- | required to include a special considerations |
| centered planning; incorporating all service | section. |
| and habilitation plan(s), individual | The HCBS Case Management Life Plan is |
| safeguards, and Individual Plans of Protective | required to be accessible to the individual |
| Oversight in one comprehensive document. | and his/her family/representative with |
| The CCO/HH Life Plan identifies the Personal | appropriate consideration for language and |
| Outcome Measure(s) that best fit with the | literacy, via mail. |
| goal and valued outcome as determined by |  |
| the individual, Care Manager and/or the IDT. |  |
| The CCO/HH Life Plan includes, as applicable, |  |
| a Special Considerations section to provide |  |
| specific information in instances where an |  |
| individual makes an informed choice not to |  |
| follow specific medical or treatment advice |  |
| that may still need to be considered when |  |
| providing supports and services to assist the |  |
| person in achieving his/her valued outcome. |  |
| The CCO/HH Life Plan is required to be |  |
| accessible to the individual and his/her |  |
| family/representative with appropriate |  |
| consideration for language and literacy, |  |
| either electronically and/or via mail, based on |  |
| the individual’s preference. |  |

Page 45 of 57

Attachment C

CCO/HH Informational Sessions for MSC Staff

Below are Planned Topics for Information Sessions Scheduled to begin in

December 2017 and continue through the Transition Period

| Topic (Presentation |  |
| --- | --- |
| order may change) | Summary |
| People First Care | An introduction to the MSC Informational Series providing an overview of the |
| Coordination – What | transition to CCO/HH Care Management and the role of the MSCs |
| MSCs Need to Know |  |
| What is CCO/HH | An explanation of what CCO/HH Care Management is with specific information |
| Comprehensive Care | about how it is different than the current work of MSCs. Information will include the |
| Management and How | key differences between coordination of I/DD only services and the expanded role |
| is it Different from the | of Care Managers |
| Work of Today’s MSCs? |  |
| What is CCO/Health | An overview of the transition process, including: What is a CCO/HH? How does it |
| Home? | provide coordination services? How does it differ from Managed Care? |
| What is a Life Plan and |  |
| How Does It Compare | An introduction to Life Planning elements with comparison to |
| to an Individualized | Individualized Service Plans |
| Service Plan? |  |
| What Does an MSC |  |
| Need to Do to Help | A summary of details that MSCs need to know, or do, to help |
| Individuals Transition | individuals and families transition to CCO/HH |
| to CCO/HH? |  |
| Behavioral and Medical |  |
| Care Coordination: | A summary of the expanded role of Care Managers, based on the Guidelines and |
| How is it Different than |  |
|  | Learning Objectives |
| Medicaid Service |  |
| Coordination? |  |
| An Introduction of the | Announcement of the CCOs and what MSCs need to know about the organizations |
| CCOs for NYS |  |
| Voices from the Field – |  |
| MSCs Talk about Care | A panel of MSCs share their experiences as Care Managers |
| Coordination |  |

Page 46 of 57

| Topic (Presentation |  |
| --- | --- |
| order may change) | Summary |
| How CCO/HH Impact | Guidance on how the Front Door will be impacted by CCO/HH |
| Interactions with the |  |
| Front Door? |  |
| Cultural and Language |  |
| Competency – CCO/HH | Ensuring that Care Managers support all cultures, ethnicities and |
| Care Management For | languages in the shift to Care Coordination |
| All |  |

Page 47 of 57

Attachment D

Health Home Implementation Timeline/Transition Plan for Individuals

Overview:

This transition plan describes the timeline and activities for the transition of individuals currently receiving Medicaid Service Coordination to Health Home services on 7/1/18.

Prior to beginning any outreach to the people on their caseload, Medicaid Service Coordinators must receive training in Health Home services (suggestion that weekly training times leading up to HH Implementation be offered via WebEx or other public forum in partnership with the State and Designated CCO/HHs).

Training for all MSC providers and DDRO staff who will be involved in the CCO/HH enrollment process is scheduled to begin no later than January 1, 2018 and continue through February or until training is completed for all.

It is also necessary for CCO/HHs to participate in State implementation and operational trainings.

| Timeline | Actions |
| --- | --- |
| Contingent | Care Coordination Organizations/Health Home applications are received and reviewed, including |
| designation of | the listing of MSC affiliated providers. CCO/HHs are contingently designated and readiness |
| CCO/HHs | activities begin. |
| 2/28/18 |  |
| Initial CCO/HH | As part of the responsibilities of Medicaid Service Coordination, service coordinators will be |
| Designation / | responsible for ensuring an individual has received the HH informational letter that will be sent to |
| Informational Letter | all individuals receiving MSC, notifying them of the benefits of HH services and the July 1, 2018 |
|  | transition. Based on the defined affiliation of the individual’s MSC provider, confirmed via the |
| 3/1/18 – 3/15/18 | application process, the letter will specify the CCO/HH that is affiliated with the individual’s current |
|  | MSC provider. The Medicaid Service Coordinator will talk with the individual about what the |
|  | transition means for the individual and what choices are available for the person relative to their |
|  | need for coordination. |

48 | P a g e

|  | MSCs begin | The current service coordinator reviews with the individual the designation/information letter and begins |  |
| --- | --- | --- | --- |
|  | discussions with | discussing the individual’s affirmative choice of CCO/HH and facilitates obtaining a signed consent form. |  |
|  | individuals/families |  |  |
|  |  | Discussion with the individual/family must include the following key messages: |  |
|  | 4/1/18 – 6/30/18 | What is a CCO/HH? |  |
|  |  | What will change for the individual once enrollment occurs? |  |
|  |  | When will enrollment into the CCO/HH begin? |  |
|  |  | What happens if the individual does not choose or consent to CCO/HH services? |  |
|  | CCO/Health Home | Care Managers (i.e., MSC service coordinators prior to 7/1 transition) must contact each new enrollee |  |
|  | Enrollment Activities | no later than June 30th to complete the Checklist. For individuals transitioning from the MSC program, |  |
|  | Begin | the current care plan along with the Checklist will identify and confirm: |  |
|  |  | Members of the interdisciplinary team (IDT), including primary I/DD providers |  |
|  | 4/1/18 – 6/30/18 | The person’s providers and contact information |  |
|  |  | Consent form to share information electronically |  |
|  |  | A scheduled Life Plan meeting with the IDT at the location chosen by the person and informed |  |
|  |  | by the comprehensive assessment process |  |
|  | Data is uploaded | Once the individual affirmatively chooses to enroll into a CCO/HH for HH services, and consent |  |
|  | into eMedNY | is received, data is uploaded into eMedNY and the appropriate R/E codes will be applied to |  |
|  |  | ensure compliance with current billing protocol. |  |
|  | 7/1/18 - |  |  |
|  | Enrollment | For all enrollments approved and processed into eMedNY system, CCO/HHs will send a |  |
|  | Confirmation Letters | welcome letter to individuals confirming enrollment into the CCO/HH, including the start date, |  |
|  | (Medicaid Notice of | contact information for the CCO/HH, and any other pertinent information required by law and/or |  |
|  | Enrollment) | regulation. |  |
|  | 6/15/18 – |  |  |
|  | Comprehensive | Care Managers will complete the comprehensive assessment process at the time of their annual |  |
|  | Assessments for all | care plan review, but no later than 12/31/18. |  |
|  | transitioning |  |  |
|  | members completed |  |  |
|  | 7/1/18 - 12/31/18 |  |  |
|  | 49 ¦ P a g e |  |  |

Attachment E

Life Plan Template and Comparison to ISP

| Individualized Service | Care Coordination | HCBS Case Management |
| --- | --- | --- |
| Plan (ISP) | Organization/Health Home | Life Plan |
|  | Life Plan |  |
| The ISP does not require the | The Care Coordination | The HCBS Case Management |
| use of an IT (electronic) | Organization/ Health Home | Life Plan does not require |
| system. | (CCO/HH) Life Plan is required to | the use of an IT (electronic) |
|  | be a person-centered service plan | system. |
|  | that is developed using an |  |
|  | Integrated Information |  |
|  | Technology or IT (electronic) |  |
|  | system for preparing, |  |
|  | implementing and monitoring the |  |
|  | electronic life plan. |  |
| ISPs are not required to use | The integrated IT system will | The HCBS Case Management |
| an integrated IT system to | allow for prompt real-time | Life Plan is not required to |
| connect all providers with | notification(s), regarding any | use an integrated IT system |
| real-time notifications and | changes to the individual’s plan, | to connect all providers with |
| updates. | to those providers in the | real-time notifications and |
|  | individual’s network. | updates. |
| The ISP is required to | The CCO/HH electronic Life Plan | The HCBS Case Management |
| document HCBS Services and | will be required to integrate all | Life Plan only requires the |
| other community and social | preventive and wellness services, | integration of HCBS services. |
| supports. | medical and behavior healthcare, |  |
|  | personal safe guards and |  |
|  | habilitation to support each |  |
|  | participant’s personal dreams in a |  |
|  | state-of-the-art document. |  |
| The ISP is an understandable | The CCO/HH Life Plan is an | The HCBS Case Management |
| and personal plan, with its | understandable and personal | Life Plan is an |
| required attachments for | plan for implementing decisions | understandable and |
| implementing decisions | made during person-centered | personal plan, with its |
| made during a person- | planning; incorporating all | required attachments for |
| centered planning process. | service and habilitation plan(s), | implementing decisions |
|  | individual safeguards, and | made during a person- |
|  | Individual Plans of Protective | centered planning process. |
|  | Oversight in one comprehensive |  |
|  | document. |  |
| The ISP is not required to | The CCO/HH Life Plan identifies | The HCBS Case Management |
| include Personal Outcome | the Personal Outcome | Life Plan is not required to |
| Measures. | Measure(s) that best fit with the | include personal outcome |
|  | goal and valued outcome as | measures. |
|  | determined by the individual, |  |
|  | Care Manager and/or the IDT |  |
| The ISP is not required to | The CCO/HH Life Plan includes, as | The HCBS Case Management |
| include a special | applicable, a Special | Life Plan is not required to |
| considerations section. | Considerations section to provide | include a special |
|  | specific information in instances | considerations section. |

50 | P a g e

|  | where an individual makes an |  |
| --- | --- | --- |
|  | informed choice not to follow |  |
|  | specific medical or treatment |  |
|  | advice that may still need to be |  |
|  | considered when providing |  |
|  | supports and services to assist |  |
|  | the person in achieving his/her |  |
|  | valued outcome. |  |
| The ISP is required to be | The CCO/HH Life Plan is required | The HCBS Case Management |
| accessible to the individual | to be accessible to the individual | Life Plan is required to be |
| and his/her | and his/her family/representative | accessible to the individual |
| family/representative, with | with appropriate consideration | and his/her |
| appropriate consideration for | for language and literacy, either | family/representative with |
| language and literacy, via | electronically and/or via mail, | appropriate consideration |
| mail. | based on the individual’s | for language and literacy, via |
|  | preference. | mail. |

51 | P a g e

Attachment E – Life Plan Template

[INSERT NAME]

Date of Birth: xx/xx/xxxx

Life Plan / ISP

Member Address:	Phone:

Medicaid #:

Medicare #:	Enrollment Date:

Plan Effective Dates:	Willowbrook Member:

|  |  | CCO |  |
| --- | --- | --- | --- |
|  | Address: | Phone: |  |
|  |  | Fax: |  |
|  | Provider ID: |  |  |
|  |  | Meeting History |  |

Plan Review Date

Reason For Meeting

Member Attendance

SECTION I

ASSESSMENT NARRATIVE SUMMARY

This section includes relevant personal history and appropriate contextual information, as well as skills, abilities, aspirations, needs, interests, reasonable accommodations, cultural considerations, meaningful activities, challenges, etc., learned during the person-centered planning process, record review and any assessments reviewed and/or completed.

52 | P a g e

My Home:

My Work:

My Health and My

Medications:

My Relationships:

53 | P a g e

SECTION II

OUTCOMES AND SUPPORT STRATEGIES

This section includes measurable/observable personal outcomes that are developed by the person and his/her IDT using person-centered planning. It describes provider goals and corresponding staff activities identified to meet the CCO goal/valued outcome. It captures the following information: goal description, valued outcomes, action steps, responsible party, service type, timeframe for action steps and Personal Outcome Measures. Evidence of achievement must be reflected in monthly notes from assigned providers.

CQL POMS Goal/ Valued Outcome

CCO

Goal/Valued

Outcome

Provider Assigned Goal

Provider / Location	Service Type

Frequency Quantity Time Frame Special Considerations

Action Step Labels: (G) = Goal, (S) = Support, (T) = Task

54 | P a g e

Section III

Individual Safeguards/Individual Plan of Protection (IPOP)

Compilation of all supports and services needed for a person to remain safe, healthy and comfortable across all settings (including Part 686 requirements for IPOP).

This section details the provider goals and corresponding staff activities required to maintain desired personal safety.

Goal/Valued Outcome

Provider Assigned Goal

Provider / Location

Service Type

Frequency	Quantity

Time Frame

Special Considerations

55 | P a g e

Section IV

HCBS Waiver and Medicaid State Plan Authorized Services

This section of the Life Plan includes a listing of all HCBS Waiver and State Plan services that have been authorized for the individual.

| Authorized Service | Provider/Facility | Effective Dates | Unit | Comments |
| --- | --- | --- | --- | --- |

56 | P a g e

Section V

All Supports and Services; Funded and Natural/Community Resources

This section identifies the services and support givers in a person’s life along with the needed contact information. Additionally, all Natural Supports and Community Resources that help the person be a valued individual of his or her community and live successfully on a day- to-day basis at home, at work, at school, or in other community locations should be listed with contact information as appropriate.

Name

Role

Address

Phone

57 | P a g e