Savings Tracker 2018-19

|  |  |  |  |  |  |  |  |  | Planned £000 |  |  |  |  | Forecast £000 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 850 | -1,498 | -474 | -893 | -981 | -4,768 | -2,399 | -757 | -555 | -601 | -4,312 | 456 |  |  |  |  |
|  |  |  |  |  |  | Investment | Original | Original | Original | Original | Original | Current | Current | Current | Current | Forecast | Variance |  | Direction |  |  |
|  | Reference | Title | Description | Committee |  |  |  |  |  |  | Forecast | Forecast | Forecast | Forecast |  | from Plan | RAG |  | Forecast Commentary | Links with partner organisations |
|  |  |  |  |  | 18-19 £000 | Phasing - Q1 | Phasing - Q2 | Phasing - Q3 | Phasing - Q4 | Saving 18-19 |  |  |  |  | Saving |  |  | of travel |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Phasing - Q1 | Phasing - Q2 | Phasing - Q3 | Phasing - Q4 |  | £000 |  |  |  |  |
|  |  |  |  | As part of the Organisational Review (C/R.6.102) a cross cutting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | A/R.6.001 | P&C Contribution to Organisational | review of mileage allowances in 2017-18 was undertaken and areas | P&C Cross | 0 | -63 | 0 | 0 | 0 | -63 | -63 | 0 | 0 | 0 | -63 | 0 | Green |  | On track | 0 |
|  |  | Review Mileage Saving | where mileage could be reduced without impacting front line | Committee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | services were identified. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Review the commissioning of the local assistance scheme and |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | A/R.6.178 | Local Assistance Scheme | resource requirement. The small saving of £21k identified does not | Childrens | 0 | -21 | 0 | 0 | 0 | -21 | -21 | 0 | 0 | 0 | -21 | 0 | Green |  | Achieved | 0 |
|  |  |  |  | reduce the service offer at all |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | A previous management restructure in the department has led to |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | A/R.6.201 | Staffing efficiencies in Commissioning | efficiencies in our commissioning team. This is the expected full | Childrens | 0 | -94 | 0 | 0 | 0 | -94 | -94 | 0 | 0 | 0 | -94 | 0 | Green |  | On track | 0 |
|  |  |  |  | year saving in 2018/19 of the new structure. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Further savings from the Children's Change programme - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | £594 in year savings. Original stretch target of additional |  |
|  |  |  |  | establishing new structures and ways of working to ensure that our |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | £295k due to shortfall of expected Government grant which |  |
|  | A/R.6.204 | Childrens Change Programme (later | service offer is responsive and timely - targeted to those in greatest | Childrens | 0 | -507 | 0 | 0 | -87 | -594 | -507 | 0 | 0 | -87 | -594 | 0 | Green |  | did not materialise in 2017/18 has now been covered off | 0 |
|  |  | phases) | need and towards those that we can ensure experience a de- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | through Business Planning. Children for Change Programme |  |
|  |  |  |  | escalation of need and risk as a result of effective, integrated, multi- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | is managing the £87k still to be made and expectation this |  |
|  |  |  |  | agency services delivered in a timely manner. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | will be achieved in Q4. |  |
|  |  |  |  | Saving to be made through re-tendering contracts, route reviews, |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A successful tender round resulted in 139k of savings. It is |  |
|  |  | Total Transport - Home to School |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | anticipated that some additional savings will be made, |  |
|  | A/R.6.210 |  | looking across client groups and managing demand for children | Childrens | 0 | -55 | -38 | -115 | -116 | -324 | -55 | -24 | -72 | -73 | -224 | 100 | Amber |  |  | 0 |
|  |  | Transport (Special) | requiring transport provision |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | however increasing demand means that it is unlikely that the |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | full savings target will be achieved in2018/19 |  |
|  |  |  |  | Personal Transport Budgets (PTBs) are discretionary payments to |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | parents/carers of children eligible for home to school transport in |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Total Transport - Home to School | exchange for full responsibility for transporting them safely to and |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | from school. By increasing the uptake of PTBs, through targeting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | An anticipated move to banded PTBs has not taken place so |  |
|  | A/R.6.214 | Transport (Special) - Moving towards |  | Childrens | 0 | 0 | 0 | -50 | -50 | -100 | 0 | 0 | 0 | 0 | 0 | 100 | Black |  |  | 0 |
|  |  |  | high cost journeys, revisiting the payment terms, improving the |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | savings are not expected to be achieved in 2018/19. |  |
|  |  | personal budgets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | approval processes, and better engagement with children and |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | parents about PTBs, this project will achieve efficiencies in the |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | transport provided. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | We want every child in Cambridgeshire to thrive and will target our |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | prioritised targeted services for vulnerable children and young |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | people. As an integral part of the Early Help Offer, our redesigned |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | services will provide support to families when they really need |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | them. We will provide a range of flexible services that are not |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | restricted to delivery from children's centre buildings, in order to |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | provide access to services when they are needed. We will also work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | in a more integrated way with partners across the 0-19 Healthy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Child Programme, to provide comprehensive targeted support to |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Children's Centres - Building a new | vulnerable families. All of this will be supported by an effective on |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | line resource tool as part of an improved on line offer for families. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | A/R.6.224 | service delivery model for |  | Childrens | 0 | 0 | 0 | 0 | 0 | -772 | -772 | 0 | 0 | 0 | -772 | 0 | Green |  | On track | 0 |
|  |  |  | The saving will be achieved by re-purposing some existing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Cambridgeshire Communities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | children's centre buildings and streamlining both our management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | infrastructure and back office, associated service running and |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | overhead costs. We intend to maintain the current level of front |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | line delivery. A total saving of £900k is planned, with £249k from |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Buildings and Infrastructure costs. Of the £249k saving, £128k will |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | be attributable to annual running costs of internally managed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | buildings. As this element of the budget is held by Corporate and |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Managed Services, this element of the total saving is therefore |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | shown in Table 3 for Corporate and Managed Services, business |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | plan reference F/R.6.110 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | A programme to transform the role of the local authority in |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | education in response to national developments and the local |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Strategic review of the LA's ongoing | context, (e.g. the increasing number of academies and a reduction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Saving reliant on wider implementaAon of Shared and |  |
|  | A/R.6.227 |  | in funding to local authorities) has been started. Savings will be | Childrens | 50 | -65 | 0 | -129 | -130 | -324 | -65 | 0 | -129 | -130 | -324 | 0 | Green |  |  | 0 |
|  |  | statutory role in learning | made by focusing on the LA’s core roles and functions; by |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Integrated Services. |  |
|  |  |  |  | developing joint working with Peterborough’s education services, |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | and with other authorities as appropriate |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Through the Total Transport transformation programme we are |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | A/R.6.244 | Total Transport - Home to School | scrutinising contract services to ensure the Council delivers the | Childrens | 0 | -138 | -29 | -88 | -87 | -342 | -138 | -29 | -88 | -87 | -342 | 0 | Green |  | On track | 0 |
|  |  | Transport (Mainstream) | most efficient mainstream school transport services whilst ensuring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | all eligible pupils receive free transport in line with the Council's |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | A/R.6.250 | Grants to Voluntary Organisations | Saving from the Home Start/Community Resilience Grant where | Childrens | 0 | -168 | 0 | 0 | 0 | -168 | -168 | 0 | 0 | 0 | -168 | 0 | Green |  | On track | 0 |
|  |  |  | the re-commissioning of this service ceased in 16/17. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Automation - Education and Children's | Reduction in staff costs in Education and Children’s services related |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | As yet no delivery plan in place for this saving and, due to the |  |
|  | A/R.6.251 |  |  | Childrens | 0 | -25 | -25 | -25 | -25 | -100 | 0 | 0 | 0 | 0 | 0 | 100 | Black |  | lead in time needed to achieve savings through automation, | 0 |
|  |  | Guidance | to more automated models of delivering advice and guidance. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | it is unlikely that any savings will be achieved in year. |  |
|  |  |  |  | Savings will be delivered through a number of workstreams as well |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | A/R.6.253 | LAC Placement Budget Savings | as working to reduce the number of children in care and improve | Childrens | 705 | -333 | -333 | -417 | -417 | -1,500 | -512 | -680 | -147 | -105 | -1,444 | 56 | Green |  | On track | 0 |
|  |  |  | the placement composition between in house and more expensive |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | external placements. Individual pieces of work that are likely to |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | A/R.6.254 | Looked After Children Transport | Increasing efficiency in LAC transport provision by identify high cost | Childrens | 50 | 0 | -20 | -40 | -40 | -100 | 0 | -20 | -40 | -40 | -100 | 0 | Green |  | On track | 0 |
|  |  |  |  | cohorts, managing demand and integrating routes. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  |  |  |  |  |  |  |  | Planned £000 |  |  |  |  | Forecast £000 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 850 | -1,498 | -474 | -893 | -981 | -4,768 | -2,399 | -757 | -555 | -601 | -4,312 | 456 |  |  |  |  |
|  |  |  |  |  | Investment | Original | Original | Original | Original | Original | Current | Current | Current | Current | Forecast | Variance |  | Direction |  |  |
|  | Reference | Title | Description | Committee |  |  |  |  |  |  | Forecast | Forecast | Forecast | Forecast |  | from Plan | RAG |  | Forecast Commentary | Links with partner organisations |
|  |  |  |  |  | 18-19 £000 | Phasing - Q1 | Phasing - Q2 | Phasing - Q3 | Phasing - Q4 | Saving 18-19 |  |  |  |  | Saving |  |  | of travel |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Phasing - Q1 | Phasing - Q2 | Phasing - Q3 | Phasing - Q4 |  | £000 |  |  |  |  |
|  |  | Delivering Greater Impact for Troubled | Our multi-agency Together for Families programme will deliver and |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | A/R.6.256 |  | evidence greater impact for more families and so will receive | Childrens | 45 | 0 | 0 | 0 | 0 | -150 | 0 | 0 | -75 | -75 | -150 | 0 | Green |  | On track | None |
|  |  | Families | increase ‘payment by results’ income from central government. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Additional automation initiatives currently being explored – |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | although these do relate to service areas (assistive technology, |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | As yet no delivery plan in place for this saving and, due to the |  |
|  |  | Automation - Admissions & Additional | domestic violence, mental health, looked after children, etc) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | A/R.6.257 |  |  | Childrens | 0 | -25 | -25 | -25 | -25 | -100 | 0 | 0 | 0 | 0 | 0 | 100 | Black |  | lead in time needed to achieve savings through automation, | 0 |
|  |  | Automation Initiatives | further work needs to be done to see where the automation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | it is unlikely that any savings will be achieved in year. |  |
|  |  |  | ‘enabler’ will release savings and ensure that these are not double |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | counted. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | A/R.7.101 | Early Years subscription package | Proposal to develop Early Years subscription package for trading | Childrens | 0 | -4 | -4 | -4 | -4 | -16 | -4 | -4 | -4 | -4 | -16 | 0 | Green |  | On track | 0 |
|  |  |  | with settings. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |