COACHELLA VALLEY WATER DISTRICT

CHANGE ORDER

NO. 1

| Specification No. | 2018-71 | File No. 0710.02.070 | Date: | April _____, 2019 |
| --- | --- | --- | --- | --- |
| Project Name: | WRP 10 Equalization Basin Floating Covert | Project ID No. | WR1039 |
| To: |  |  | Issued by: |  |
| Raven CLI Construction |  | Coachella Valley Water District |
| 330 W. Citrus Street, Unit 200 |  | Post Office Box 1058 |
| Colton, CA 92324 |  |  | Coachella, CA 92236 |

Pursuant to the Changes and Extra Work provisions of this Contract, you are directed as described below.

This Contract is modified to include the administrative changes described below.

| Description of Changes (Extra Work): |  |  |  | Contract Price |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Increase |  | (Decrease) |  |
| The Extra Work includes the following items: |  |  |  |  |  |  |  |
| 1. Labor, equipment and materials to demolish, remove and | $ 39,850 |  | ($ | ) |  |
| dispose of the existing HDPE liner |  |  |  |  |  |  |  |  |
| 2. Labor, equipment and materials to provide and install new 45 | $ 248,800 |  | ($ | ) |  |
| mil CSPE Black liner with 8 oz nonwoven geotextile |  |  |  |  |  |  |
| underlayment |  |  |  |  |  |  |  |  |  |
| 3. 2% Bonds/Insurance |  |  |  | $5,773 |  | ($ | ) |  |
|  | Change in Contract Price due to this Change Order: | $ 294,423.00 |  | ($ | ) |  |
|  |  |  | Original Contract Amount: $ 458,960.00 |  |  |  |
|  |  | Previously Approved Change Orders: $ 0.00 |  |  |  |
|  |  |  | New Contract Amount: $ 753,383.00 |  |  |  |
| Contractor's Proposal Attached: |  |  |  |  |  |  |  |  |
| Yes | See proposal dated | Not dated |  |  |  |  |  |  |  |
| No | Explain: |  |  |  |  |  |  |  |  |  |
| Engineer's Estimate Attached: |  |  |  |  |  |  |  |  |
| Yes | Date: |  |  |  |  |  |  |  |  |  |
| No | Explain: | Cost for work provided by Raven and reviewed by Lee & RO.. |  |  |  |
| Supplemental Plans and Specifications Attached: |  |  |  |  |  |  |  |
| Yes |  |  |  |  |  |  |  |  |  |  |
| No | Explain: | Plans and specifications provided upon completion by Lee & RO |  |  |  |
| Impact of this Change Order on Contract Time |  |  |  |  |  |  |  |
| Prior to this Change Order | 120 | Calendar days | Completion Date: | 03/312019 |  |
| Increase due to this Change Order: | 60 | Calendar days |  |  |  |  |  |  |
| Including this Change Order: | 180 | Calendar days | Completion Date: | 05/30/2019 |  |

Justification: Upon removal of the Equalization Basin Floating Cover, staff discovered the High Density Polyethylene (HDPE) liner has degraded and is in need of repair. In addition, the subgrade shows signs of erosion below the liner. CVWD staff and Lee & RO, the engineer or record, recommend replacement of the liner with a 45 mil chlorosulfonated polyethylene (CSPE) liner and 8 ounce nonwoven geotextile underlayment.

Raven Construction is directed to provide labor and material for the additional work as directed in this change order. Raven Construction shall follow the submittal procedures in the Contract when performing the work in this change order as requested by CVWD.

The Contractor shall complete the work in this change order for a lump sum of $288,650.00.

Change Order initiated by:	CVWD	Contractor	Other:

Prepared/Reviewed by:

Date:

Lee & RO

Engineer of Record

Prepared by:

Date:

Jignesh Ladhawala

Project Manager

Reviewed by:

Date:

N/A

Reviewed by:

Date:

Donnell Wilcox

Engineering Supervisor

Submitted by:

Date:

Armando Rodriguez

Engineering Manager

Approved by:

Date:

Carrie Oliphant

Director of Engineering

Approved by:

Date:

J. M. Barrett

General Manager

CONTRACTOR:

Contractor accepts the terms and conditions stated above as full and final settlement of any and all claims arising out of or related to the subject of this Change Order and acknowledges that the compensation (time and cost) set forth herein comprises the total compensation due for the work or change defined in the Change Order, including all impact on any unchanged work. By signing this Change Order, the Contractor acknowledges and agrees that the stipulated compensation includes payment for all Work contained in the Change Order, plus all payment for any acceleration or interruption of schedules, extended overhead costs, delay, and all impact or cumulative impact on all Work under this Contract. The signing of this Change Order acknowledges full mutual accord and satisfaction for the change and that the stated time and/or cost constitute the total equitable adjustment owed the Contractor as a result of the change. The Contractor hereby releases and agrees to waive all rights, without exception or reservation of any kind whatsoever, to file any further claim or request for equitable adjustment of any type, for any reasonably foreseeable cause that shall arise out of, or as a result of, this Change Order and/or its impact on the remainder of the Work under the Contract.

| Signature |  | Typed Name |
| --- | --- | --- |
| Phone |  | Date: |